## Cover
Job Cost & WIP Report
Boreal Ridge Construction Ltd. (fictional company)
Period ending September 30, 2026
SAMPLE DATA NOTICE | Representative rebuild of ERP cost reporting delivered for construction clients. The company, jobs, vendors and all figures are synthetic; client data is confidential.
Report date | 2026-09-30
SHEETS
WIP Schedule | Portfolio view: contract, cost to date, forecast cost, % complete, earned revenue, over/(under) billing, projected margin and fade, CPI and backlog for every job.
Job Detail | Pick a job number in the yellow cell to see its cost-code report, forecast overruns and labour productivity.
Cost Report | Cost-code level calculation that feeds both reports (one row per job / cost code budget line).
Monthly Cost | Monthly and cumulative cost by job from the job cost ledger, with a portfolio cost curve.
Data_* tabs | Raw ERP exports: job master, cost codes, budgets, PM progress, commitments, job cost detail, billings. Paste a new month's export over these tables to refresh.
METHOD
Earned value | Revised budget x PM-reported physical % complete for the cost code.
CPI | Earned value / actual cost. Below 1.00 means the work is costing more than budgeted.
Forecast cost (EAC) | Subcontract & material lines with a commitment: the greater of committed value and cost to date. Other lines in progress: cost to date + remaining budget / CPI. Lines not started: revised budget.
% complete (revenue) | Cost-to-cost method: cost to date / forecast cost.
Earned revenue | Revised contract x % complete.
Over/(under) billing | Billed to date - earned revenue. Positive = billings in excess of revenue (liability); negative = revenue in excess of billings (asset).
Margin fade | Projected margin % - bid margin %. Negative = profit eroding since bid.
COLOUR KEY
Blue on yellow | Input you can change (the job selector on Job Detail).
Black | Formula.

## WIP Schedule
Work-in-Progress Schedule
Boreal Ridge Construction Ltd. (fictional) · Period ending September 30, 2026 · Percentage-of-completion, cost-to-cost method
Job No | Job Name | PM | Status | Revised Contract | Revised Budget | Cost to Date | Committed | Forecast Cost (EAC) | Cost to Complete | % Complete | Earned Revenue | Billed to Date | Over/(Under) Billing | Projected Gross Profit | Projected Margin | Bid Margin | Margin Fade | CPI | Backlog
23-098 | Transit Bus Garage Upgrade | R. Singh | Substantially complete | 15462000 | 13811100 | 14275865.39 | 11358200 | 14408909.8655 | 133044.4755 | 99.08% | 15319231.8309 | 15319587.46 | 355.6291 | 1053090.1345 | 6.811% | 10.5% | -3.689% | 0.96597 | 142768.1691
24-101 | Leduc Distribution Warehouse | M. Okafor | In progress | 22245000 | 20085200 | 19031041.47 | 15186100 | 19799870.3972 | 768828.9272 | 96.12% | 21381226.6953 | 22246320.45 | 865093.7547 | 2445129.6028 | 10.99% | 9.5% | 1.492% | 1.027 | 863773.3047
24-104 | School Modernization - Phase 2 | J. Tremblay | In progress | 16538000 | 14705200 | 13766951.4 | 11693400 | 15394483.3254 | 1627531.9254 | 89.43% | 14789573.4752 | 14186235.47 | -603338.0052 | 1143516.6746 | 6.914% | 11% | -4.086% | 0.97174 | 1748426.5248
24-107 | Fabrication Shop Expansion | M. Okafor | In progress | 10160000 | 8928400 | 8639590.49 | 6548600 | 8812195.0883 | 172604.5983 | 98.04% | 9960995.9266 | 10159340.97 | 198345.0434 | 1347804.9117 | 13.27% | 12% | 1.266% | 1.0293 | 199004.0734
25-110 | Medical Office Building | S. Chen | In progress | 25580000 | 22973200 | 15913660.17 | 18195100 | 23781711.24 | 7868051.07 | 66.92% | 17116994.7797 | 18511137.53 | 1394142.7503 | 1798288.76 | 7.03% | 10% | -2.97% | 0.96603 | 8463005.2203
25-112 | Fire Hall No. 4 | R. Singh | In progress | 9026000 | 7983600 | 7797690.62 | 6175300 | 8177299.8142 | 379609.1942 | 95.36% | 8606992.1777 | 8359789.85 | -247202.3277 | 848700.1858 | 9.403% | 11.5% | -2.097% | 0.98619 | 419007.8223
25-115 | Recreation Centre Retrofit | J. Tremblay | In progress | 12065000 | 10763600 | 8582224.51 | 8139000 | 11519732.2815 | 2937507.7715 | 74.5% | 8988450.0944 | 8294926.02 | -693524.0744 | 545267.7185 | 4.519% | 10.5% | -5.981% | 0.94292 | 3076549.9056
25-118 | Cold Storage Facility | S. Chen | In progress | 18090000 | 16302200 | 13092123.99 | 12660900 | 16233742.963 | 3141618.973 | 80.65% | 14589150.7288 | 15322118.26 | 732967.5312 | 1856257.037 | 10.26% | 9.8% | 0.4612% | 1.0181 | 3500849.2712
25-121 | Seniors Residence | A. Dubois | In progress | 20405000 | 18541400 | 5364879.52 | 13169200 | 18538818.8166 | 13173939.2966 | 28.94% | 5904926.721 | 6001562.81 | 96636.089 | 1866181.1834 | 9.146% | 9% | 0.1457% | 1.0144 | 14500073.279
26-124 | Process Building | M. Okafor | In progress | 13400000 | 11858900 | 5372210.84 | 9211200 | 11951245.7896 | 6579034.9496 | 44.95% | 6023441.1143 | 6611526.58 | 588085.4657 | 1448754.2104 | 10.81% | 11.5% | -0.6884% | 0.99685 | 7376558.8857
26-127 | Retail Plaza | A. Dubois | In progress | 7650000 | 6693800 | 2201288.53 | 5000900 | 6607426.2289 | 4406137.6989 | 33.32% | 2548625.8448 | 2627509.26 | 78883.4152 | 1042573.7711 | 13.63% | 12.5% | 1.128% | 1.0347 | 5101374.1552
26-130 | Public Works Yard Building | R. Singh | In progress | 6300000 | 5607100 | 540737.58 | 3486800 | 5598962.2585 | 5058224.6785 | 9.658% | 608442.5286 | 614815.4 | 6372.8714 | 701037.7415 | 11.13% | 11% | 0.1276% | 1.0237 | 5691557.4714
Portfolio total |  |  |  | 176921000 | 158253700 | 114578264.51 | 120824700 | 160824398.0686 | 46246133.5586 | 71.24% | 125838051.9173 | 128254870.06 | 2416818.1427 | 16096601.9314 | 9.098% | 10.42% | -1.323% | 0.9925 | 51082948.0827
Red: margin fade worse than -2.0 pts, or CPI below 0.97. Over/(under) billing: positive = billings in excess of revenue (liability); negative = revenue in excess of billings (asset).
Green text = pulled from the job master (Data_Jobs). All other figures are formulas on the Cost Report and Data_ tabs.
Note on Q17: Contract-weighted average bid margin.

## Job Detail
Job Cost Detail
Pick a job number from the yellow drop-down to refresh this page.
| Job: | 25-115 | Recreation Centre Retrofit
|  | Project manager | J. Tremblay |  | Revised contract |  | 12065000 |  | Job CPI |  |  | 0.94292
|  | Client type | Municipal |  | Forecast cost (EAC) |  | 11519732.2815 |  | Labour productivity |  |  | 0.89318
|  | Status | In progress |  | Projected margin |  | 4.519% |  | Forecast over budget |  |  | 790532.2815
|  | Scheduled finish | 2027-03-26 |  | Bid margin |  | 10.5% |  | Cost to complete |  |  | 2937507.7715
[5 empty] | Margin fade |  | -5.981%
| Cost Code | Description | Cost Type | Original Budget | Budget Changes | Revised Budget | Actual Cost | Committed | % Complete | Earned Value | CPI | Forecast Cost (EAC) | Variance at Completion | Cost to Complete | Budget Hours | Actual Hours | Earned Hours
| 01-100 | General Conditions - Supervision | Labour | 957900 | 0 | 957900 | 766276.35 | 0 | 76.3% | 730877.7 | 0.9538 | 1004294.0367 | -46394.0367 | 238017.6867 | 10412 | 8329 | 7944.356
| 01-200 | Site Facilities & Temp Services | Other | 313200 | 43300 | 356500 | 275153.11 | 0 | 74.3% | 264879.5 | 0.96266 | 370327.2005 | -13827.2005 | 95174.0905 | 0 | 0 | 0
| 01-500 | Equipment Rental | Equipment | 275800 | 0 | 275800 | 267801.12 | 0 | 90.4% | 249323.2 | 0.931 | 296240.177 | -20440.177 | 28439.057 | 0 | 0 | 0
| 02-200 | Earthwork & Excavation | Subcontract | 410500 | 0 | 410500 | 395353.03 | 396500 | 100% | 410500 | 1.0383 | 396500 | 14000 | 1146.97 | 0 | 0 | 0
| 03-100 | Concrete Formwork | Labour | 545200 | 549300 | 1094500 | 1229218.83 | 0 | 100% | 1094500 | 0.8904 | 1229218.83 | -134718.83 | 0 | 14791 | 16611.2 | 14791
| 03-200 | Reinforcing Steel | Material | 452600 | 0 | 452600 | 446285.28 | 456400 | 100% | 452600 | 1.0141 | 456400 | -3800 | 10114.72 | 0 | 0 | 0
| 03-300 | Cast-in-Place Concrete | Material | 763100 | 0 | 763100 | 756596.67 | 767600 | 100% | 763100 | 1.0086 | 767600 | -4500 | 11003.33 | 0 | 0 | 0
| 04-200 | Masonry | Subcontract | 789900 | 0 | 789900 | 808032.22 | 811100 | 100% | 789900 | 0.97756 | 811100 | -21200 | 3067.78 | 0 | 0 | 0
| 05-100 | Structural Steel | Subcontract | 730300 | 0 | 730300 | 731077.8 | 735800 | 100% | 730300 | 0.99894 | 735800 | -5500 | 4722.2 | 0 | 0 | 0
| 06-100 | Rough Carpentry | Labour | 385900 | 0 | 385900 | 360969.68 | 0 | 75.1% | 289810.9 | 0.80287 | 480652.0373 | -94752.0373 | 119682.3573 | 5435 | 5084.1 | 4081.685
| 07-200 | Roofing & Insulation | Subcontract | 647300 | 57600 | 704900 | 657408.01 | 705400 | 95.4% | 672474.6 | 1.0229 | 705400 | -500 | 47991.99 | 0 | 0 | 0
| 08-100 | Doors, Frames & Hardware | Material | 438400 | 0 | 438400 | 46792.64 | 430700 | 11% | 48224 | 1.0306 | 430700 | 7700 | 383907.36 | 0 | 0 | 0
| 09-200 | Drywall & Finishes | Subcontract | 874500 | 0 | 874500 | 81208.9 | 884500 | 9.4% | 82203 | 1.0122 | 884500 | -10000 | 803291.1 | 0 | 0 | 0
| 15-000 | Mechanical | Subcontract | 1463800 | 0 | 1463800 | 1151483.07 | 1898700 | 60.7% | 888526.6 | 0.77164 | 1898700 | -434900 | 747216.93 | 0 | 0 | 0
| 16-000 | Electrical | Subcontract | 1065000 | 0 | 1065000 | 608567.8 | 1052300 | 58.7% | 625155 | 1.0273 | 1052300 | 12700 | 443732.2 | 0 | 0 | 0
| Job total |  |  | 10113400 | 650200 | 10763600 | 8582224.51 | 8139000 | 75.18% | 8092374.5 | 0.94292 | 11519732.2815 | -756132.2815 | 2937507.7715 | 30638 | 30024.3 | 26817.041
Cost codes not used on the selected job show as '-'. Red: forecast overrun above $25,000 or CPI below 0.95.
Note on M6: Earned hours / actual hours on self-performed labour codes. Above 1.00 = ahead of budgeted productivity.

## Monthly Cost
Monthly Job Cost
Posted cost by fiscal period from the job cost ledger (Data_JobCost).
Period | 23-098 | 24-101 | 24-104 | 24-107 | 25-110 | 25-112 | 25-115 | 25-118 | 25-121 | 26-124 | 26-127 | 26-130 | Portfolio | Cumulative
202406 | 39201.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39201.02 | 39201.02
202407 | 91276.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91276.61 | 130477.63
202408 | 184236.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 184236.51 | 314714.14
202409 | 245464.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 245464.58 | 560178.72
202410 | 342893.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 342893.6 | 903072.32
202411 | 384273.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 384273.5 | 1287345.82
202412 | 438101.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 438101.97 | 1725447.79
202501 | 558702.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 558702.16 | 2284149.95
202502 | 520964.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 520964.18 | 2805114.13
202503 | 667866.28 | 141082.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 808949.25 | 3614063.38
202504 | 701693.98 | 375657.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1077351.21 | 4691414.59
202505 | 744704.94 | 805086.61 | 66021.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1615812.8 | 6307227.39
202506 | 726320.95 | 878383.12 | 164577.98 | 99896.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1869178.89 | 8176406.28
202507 | 845618.87 | 1021952 | 334214.27 | 290282.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2492067.15 | 10668473.43
202508 | 886665.08 | 1127570.08 | 447882.78 | 473897.08 | 98662.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3034677.48 | 13703150.91
202509 | 866256.7 | 1332743.09 | 488620.92 | 551913.21 | 238124.31 | 44053.67 | 0 | 0 | 0 | 0 | 0 | 0 | 3521711.9 | 17224862.81
202510 | 915103.58 | 1590245.5 | 668495.42 | 676091.31 | 561081.87 | 183047.27 | 54833.63 | 0 | 0 | 0 | 0 | 0 | 4648898.58 | 21873761.39
202511 | 811349.49 | 1452995.17 | 801717.39 | 769053.1 | 699457.01 | 322802.99 | 172560.97 | 199159.44 | 0 | 0 | 0 | 0 | 5229095.56 | 27102856.95
202512 | 841222.34 | 1442866.13 | 875577.96 | 876180.45 | 883006.9 | 469451.92 | 405644.52 | 664831.16 | 0 | 0 | 0 | 0 | 6458781.38 | 33561638.33
202601 | 841540.1 | 1285805.78 | 992602.14 | 775864.69 | 1013457.55 | 605417.19 | 556844.83 | 886588.4 | 57698.23 | 0 | 0 | 0 | 7015818.91 | 40577457.24
202602 | 748578.96 | 1083398.96 | 968605.39 | 671385.52 | 1235878.04 | 635227.17 | 679393.45 | 973941.12 | 160395.04 | 0 | 0 | 0 | 7156803.65 | 47734260.89
202603 | 700971.61 | 1284077.11 | 1143630.62 | 736613.04 | 1492267.11 | 774958.46 | 875214.24 | 1283009.52 | 395486.06 | 158933.14 | 0 | 0 | 8845160.91 | 56579421.8
202604 | 487771.8 | 1255615.34 | 1332647.04 | 745721.74 | 1615476.54 | 864224.37 | 867987.23 | 1744825.94 | 534884.81 | 425052.2 | 0 | 0 | 9874207.01 | 66453628.81
202605 | 343624.93 | 1095473.51 | 1244070.87 | 677988.56 | 1631954.82 | 945844.42 | 890518.43 | 1738891.17 | 635978.04 | 695587.76 | 89882.88 | 0 | 9989815.39 | 76443444.2
202606 | 208891.19 | 880909.18 | 1159606.63 | 487977.06 | 1626153.94 | 857657.4 | 907777.69 | 1370718.87 | 695288.99 | 741853.4 | 305021.24 | 0 | 9241855.59 | 85685299.79
202607 | 112484.74 | 837995.75 | 1061773.88 | 420828.37 | 1595494.57 | 825836.93 | 1096050.7 | 1456574.1 | 845799.06 | 990712.91 | 466720.2 | 41892.12 | 9752163.33 | 95437463.12
202608 | 20085.64 | 670747.57 | 1086795.56 | 246752.74 | 1550724.9 | 767291.63 | 1125553.07 | 1485092.28 | 1002506.36 | 1235116.24 | 603506.35 | 199213.76 | 9993386.1 | 105430849.22
202609 | 0.08 | 468436.37 | 930111.3 | 139144.77 | 1671920.15 | 501877.2 | 949845.75 | 1288491.99 | 1036842.93 | 1124955.19 | 736157.86 | 299631.7 | 9147415.29 | 114578264.51
Total | 14275865.39 | 19031041.47 | 13766951.4 | 8639590.49 | 15913660.17 | 7797690.62 | 8582224.51 | 13092123.99 | 5364879.52 | 5372210.84 | 2201288.53 | 540737.58 | 114578264.51

## Cost Report
Cost Report — cost-code level (feeds WIP Schedule and Job Detail)
One row per budget line in the ERP export. Every value is a formula on the Data_ tabs.
Job No | Cost Code | Description | Cost Type | Original Budget | Budget Changes | Revised Budget | Actual Cost | Committed | % Complete | Earned Value | CPI | Forecast Cost (EAC) | Variance at Completion | Cost to Complete | Budget Hours | Actual Hours | Earned Hours
23-098 | 01-100 | General Conditions - Supervision | Labour | 1055600 | 0 | 1055600 | 1056376.08 | 0 | 98% | 1034488 | 0.97928 | 1077934.7755 | -22334.7755 | 21558.6955 | 11474 | 11482.4 | 11244.52
23-098 | 01-200 | Site Facilities & Temp Services | Other | 405700 | 0 | 405700 | 411510.56 | 0 | 100% | 405700 | 0.98588 | 411510.56 | -5810.56 | 0 | 0 | 0 | 0
23-098 | 01-500 | Equipment Rental | Equipment | 385500 | 0 | 385500 | 398775.35 | 0 | 100% | 385500 | 0.96671 | 398775.35 | -13275.35 | 0 | 0 | 0 | 0
23-098 | 02-200 | Earthwork & Excavation | Subcontract | 499000 | 0 | 499000 | 498175.49 | 504300 | 100% | 499000 | 1.0017 | 504300 | -5300 | 6124.51 | 0 | 0 | 0
23-098 | 03-100 | Concrete Formwork | Labour | 620700 | 0 | 620700 | 617156.55 | 0 | 100% | 620700 | 1.0057 | 617156.55 | 3543.45 | 0 | 8388 | 8339.6 | 8388
23-098 | 03-200 | Reinforcing Steel | Material | 564400 | 0 | 564400 | 540645.37 | 557000 | 100% | 564400 | 1.0439 | 557000 | 7400 | 16354.63 | 0 | 0 | 0
23-098 | 03-300 | Cast-in-Place Concrete | Material | 1018900 | 0 | 1018900 | 995639.07 | 1000500 | 100% | 1018900 | 1.0234 | 1000500 | 18400 | 4860.93 | 0 | 0 | 0
23-098 | 04-200 | Masonry | Subcontract | 820600 | 0 | 820600 | 793421.31 | 796800 | 100% | 820600 | 1.0343 | 796800 | 23800 | 3378.69 | 0 | 0 | 0
23-098 | 05-100 | Structural Steel | Subcontract | 1085900 | 121300 | 1207200 | 1212198 | 1239500 | 100% | 1207200 | 0.99588 | 1239500 | -32300 | 27302 | 0 | 0 | 0
23-098 | 06-100 | Rough Carpentry | Labour | 487700 | 41900 | 529600 | 545332.63 | 0 | 100% | 529600 | 0.97115 | 545332.63 | -15732.63 | 0 | 7459 | 7680.6 | 7459
23-098 | 07-200 | Roofing & Insulation | Subcontract | 887800 | 0 | 887800 | 874884.75 | 883100 | 100% | 887800 | 1.0148 | 883100 | 4700 | 8215.25 | 0 | 0 | 0
23-098 | 08-100 | Doors, Frames & Hardware | Material | 584500 | 357000 | 941500 | 944298.08 | 952900 | 100% | 941500 | 0.99704 | 952900 | -11400 | 8601.92 | 0 | 0 | 0
23-098 | 09-200 | Drywall & Finishes | Subcontract | 1215700 | 0 | 1215700 | 1176410.47 | 1208700 | 100% | 1215700 | 1.0334 | 1208700 | 7000 | 32289.53 | 0 | 0 | 0
23-098 | 15-000 | Mechanical | Subcontract | 2094400 | 0 | 2094400 | 2614554.53 | 2618700 | 100% | 2094400 | 0.80105 | 2618700 | -524300 | 4145.47 | 0 | 0 | 0
23-098 | 16-000 | Electrical | Subcontract | 1564500 | 0 | 1564500 | 1596487.15 | 1596700 | 100% | 1564500 | 0.97996 | 1596700 | -32200 | 212.85 | 0 | 0 | 0
24-101 | 01-100 | General Conditions - Supervision | Labour | 1406900 | 0 | 1406900 | 1315116.16 | 0 | 95.6% | 1344996.4 | 1.0227 | 1375644.5188 | 31255.4812 | 60528.3588 | 15292 | 14294.6 | 14619.152
24-101 | 01-200 | Site Facilities & Temp Services | Other | 580100 | 313000 | 893100 | 829880.5 | 0 | 93.3% | 833262.3 | 1.0041 | 889475.3483 | 3624.6517 | 59594.8483 | 0 | 0 | 0
24-101 | 01-500 | Equipment Rental | Equipment | 790300 | 0 | 790300 | 794792.13 | 0 | 100% | 790300 | 0.99435 | 794792.13 | -4492.13 | 0 | 0 | 0 | 0
24-101 | 02-200 | Earthwork & Excavation | Subcontract | 1483000 | 145300 | 1628300 | 1604276.29 | 1628400 | 100% | 1628300 | 1.015 | 1628400 | -100 | 24123.71 | 0 | 0 | 0
24-101 | 03-100 | Concrete Formwork | Labour | 1211100 | 0 | 1211100 | 1193886.12 | 0 | 100% | 1211100 | 1.0144 | 1193886.12 | 17213.88 | 0 | 16366 | 16133.5 | 16366
24-101 | 03-200 | Reinforcing Steel | Material | 989400 | 260000 | 1249400 | 1226368.23 | 1249400 | 100% | 1249400 | 1.0188 | 1249400 | 0 | 23031.77 | 0 | 0 | 0
24-101 | 03-300 | Cast-in-Place Concrete | Material | 1614300 | 0 | 1614300 | 1526053.11 | 1566400 | 100% | 1614300 | 1.0578 | 1566400 | 47900 | 40346.89 | 0 | 0 | 0
24-101 | 05-100 | Structural Steel | Subcontract | 3037500 | 0 | 3037500 | 3005417.51 | 3076400 | 100% | 3037500 | 1.0107 | 3076400 | -38900 | 70982.49 | 0 | 0 | 0
24-101 | 06-100 | Rough Carpentry | Labour | 359000 | 0 | 359000 | 359972.28 | 0 | 100% | 359000 | 0.9973 | 359972.28 | -972.28 | 0 | 5056 | 5069.8 | 5056
24-101 | 07-200 | Roofing & Insulation | Subcontract | 1116300 | 0 | 1116300 | 1059948.55 | 1083200 | 100% | 1116300 | 1.0532 | 1083200 | 33100 | 23251.45 | 0 | 0 | 0
24-101 | 08-100 | Doors, Frames & Hardware | Material | 389800 | 0 | 389800 | 354305.81 | 384200 | 94.2% | 367191.6 | 1.0364 | 384200 | 5600 | 29894.19 | 0 | 0 | 0
24-101 | 09-200 | Drywall & Finishes | Subcontract | 737800 | 0 | 737800 | 676117.96 | 727500 | 93.1% | 686891.8 | 1.0159 | 727500 | 10300 | 51382.04 | 0 | 0 | 0
24-101 | 15-000 | Mechanical | Subcontract | 2603000 | 0 | 2603000 | 2442068.79 | 2532000 | 96.7% | 2517101 | 1.0307 | 2532000 | 71000 | 89931.21 | 0 | 0 | 0
24-101 | 16-000 | Electrical | Subcontract | 3048400 | 0 | 3048400 | 2642838.03 | 2938600 | 91.5% | 2789286 | 1.0554 | 2938600 | 109800 | 295761.97 | 0 | 0 | 0
24-104 | 01-100 | General Conditions - Supervision | Labour | 1243700 | 25100 | 1268800 | 1263165.96 | 0 | 93.6% | 1187596.8 | 0.94017 | 1349536.2821 | -80736.2821 | 86370.3221 | 13791 | 13730.3 | 12908.376
24-104 | 01-200 | Site Facilities & Temp Services | Other | 445000 | 0 | 445000 | 450824.52 | 0 | 91.7% | 408065 | 0.90515 | 491629.7928 | -46629.7928 | 40805.2728 | 0 | 0 | 0
24-104 | 01-500 | Equipment Rental | Equipment | 362600 | 0 | 362600 | 381921.06 | 0 | 96.7% | 350634.2 | 0.91808 | 394954.5605 | -32354.5605 | 13033.5005 | 0 | 0 | 0
24-104 | 02-200 | Earthwork & Excavation | Subcontract | 542400 | 0 | 542400 | 549274.01 | 549400 | 100% | 542400 | 0.98749 | 549400 | -7000 | 125.99 | 0 | 0 | 0
24-104 | 03-100 | Concrete Formwork | Labour | 625800 | 0 | 625800 | 840920.34 | 0 | 100% | 625800 | 0.74418 | 840920.34 | -215120.34 | 0 | 8457 | 11363.8 | 8457
24-104 | 03-200 | Reinforcing Steel | Material | 525100 | 0 | 525100 | 493406.24 | 505200 | 100% | 525100 | 1.0642 | 505200 | 19900 | 11793.76 | 0 | 0 | 0
24-104 | 03-300 | Cast-in-Place Concrete | Material | 850700 | 0 | 850700 | 828817.94 | 833200 | 100% | 850700 | 1.0264 | 833200 | 17500 | 4382.06 | 0 | 0 | 0
24-104 | 04-200 | Masonry | Subcontract | 989600 | 0 | 989600 | 957529.88 | 978100 | 100% | 989600 | 1.0335 | 978100 | 11500 | 20570.12 | 0 | 0 | 0
24-104 | 05-100 | Structural Steel | Subcontract | 1228200 | 0 | 1228200 | 1231722.55 | 1257200 | 100% | 1228200 | 0.99714 | 1257200 | -29000 | 25477.45 | 0 | 0 | 0
24-104 | 06-100 | Rough Carpentry | Labour | 606300 | 0 | 606300 | 624042.35 | 0 | 100% | 606300 | 0.97157 | 624042.35 | -17742.35 | 0 | 8539 | 8789.6 | 8539
24-104 | 07-200 | Roofing & Insulation | Subcontract | 973800 | 177600 | 1151400 | 1107922.62 | 1108500 | 100% | 1151400 | 1.0392 | 1108500 | 42900 | 577.38 | 0 | 0 | 0
24-104 | 08-100 | Doors, Frames & Hardware | Material | 635200 | 0 | 635200 | 477588.26 | 643900 | 75.1% | 477035.2 | 0.99884 | 643900 | -8700 | 166311.74 | 0 | 0 | 0
24-104 | 09-200 | Drywall & Finishes | Subcontract | 1354700 | 84600 | 1439300 | 1175644.3 | 1857800 | 64.5% | 928348.5 | 0.78965 | 1857800 | -418500 | 682155.7 | 0 | 0 | 0
24-104 | 15-000 | Mechanical | Subcontract | 2291900 | 0 | 2291900 | 1885754.2 | 2206000 | 87.3% | 2000828.7 | 1.061 | 2206000 | 85900 | 320245.8 | 0 | 0 | 0
24-104 | 16-000 | Electrical | Subcontract | 1742900 | 0 | 1742900 | 1498417.17 | 1754100 | 86.4% | 1505865.6 | 1.005 | 1754100 | -11200 | 255682.83 | 0 | 0 | 0
24-107 | 01-100 | General Conditions - Supervision | Labour | 768500 | 203100 | 971600 | 957191.78 | 0 | 99.4% | 965770.4 | 1.009 | 962969.5976 | 8630.4024 | 5777.8176 | 10561 | 10404.2 | 10497.634
24-107 | 01-200 | Site Facilities & Temp Services | Other | 246700 | 0 | 246700 | 227884.93 | 0 | 94.6% | 233378.2 | 1.0241 | 240893.1607 | 5806.8393 | 13008.2307 | 0 | 0 | 0
24-107 | 01-500 | Equipment Rental | Equipment | 340900 | 35700 | 376600 | 370354.31 | 0 | 100% | 376600 | 1.0169 | 370354.31 | 6245.69 | 0 | 0 | 0 | 0
24-107 | 02-200 | Earthwork & Excavation | Subcontract | 642100 | 0 | 642100 | 634942.59 | 645600 | 100% | 642100 | 1.0113 | 645600 | -3500 | 10657.41 | 0 | 0 | 0
24-107 | 03-100 | Concrete Formwork | Labour | 523800 | 0 | 523800 | 518524.82 | 0 | 100% | 523800 | 1.0102 | 518524.82 | 5275.18 | 0 | 7078 | 7007.3 | 7078
24-107 | 03-200 | Reinforcing Steel | Material | 471200 | 109700 | 580900 | 569775.66 | 572900 | 100% | 580900 | 1.0195 | 572900 | 8000 | 3124.34 | 0 | 0 | 0
24-107 | 03-300 | Cast-in-Place Concrete | Material | 665100 | 0 | 665100 | 645637.53 | 660000 | 100% | 665100 | 1.0301 | 660000 | 5100 | 14362.47 | 0 | 0 | 0
24-107 | 05-100 | Structural Steel | Subcontract | 1231200 | 0 | 1231200 | 1193968.92 | 1229000 | 100% | 1231200 | 1.0312 | 1229000 | 2200 | 35031.08 | 0 | 0 | 0
24-107 | 06-100 | Rough Carpentry | Labour | 176500 | 0 | 176500 | 170853.2 | 0 | 100% | 176500 | 1.0331 | 170853.2 | 5646.8 | 0 | 2486 | 2406.4 | 2486
24-107 | 07-200 | Roofing & Insulation | Subcontract | 528300 | 0 | 528300 | 509900.4 | 522300 | 100% | 528300 | 1.0361 | 522300 | 6000 | 12399.6 | 0 | 0 | 0
24-107 | 08-100 | Doors, Frames & Hardware | Material | 153800 | 0 | 153800 | 150071.95 | 151000 | 100% | 153800 | 1.0248 | 151000 | 2800 | 928.05 | 0 | 0 | 0
24-107 | 09-200 | Drywall & Finishes | Subcontract | 294700 | 0 | 294700 | 278137.73 | 285800 | 100% | 294700 | 1.0595 | 285800 | 8900 | 7662.27 | 0 | 0 | 0
24-107 | 15-000 | Mechanical | Subcontract | 1203300 | 0 | 1203300 | 1131000.08 | 1172500 | 99.2% | 1193673.6 | 1.0554 | 1172500 | 30800 | 41499.92 | 0 | 0 | 0
24-107 | 16-000 | Electrical | Subcontract | 1333800 | 0 | 1333800 | 1281346.59 | 1309500 | 99.5% | 1327131 | 1.0357 | 1309500 | 24300 | 28153.41 | 0 | 0 | 0
25-110 | 01-100 | General Conditions - Supervision | Labour | 1916200 | 31300 | 1947500 | 1365242.44 | 0 | 70.5% | 1372987.5 | 1.0057 | 1936514.0993 | 10985.9007 | 571271.6593 | 21168 | 14839.4 | 14923.44
25-110 | 01-200 | Site Facilities & Temp Services | Other | 564300 | 309100 | 873400 | 654298.6 | 0 | 72.4% | 632341.6 | 0.96644 | 903727.3481 | -30327.3481 | 249428.7481 | 0 | 0 | 0
25-110 | 01-500 | Equipment Rental | Equipment | 584000 | 0 | 584000 | 489335.22 | 0 | 82.5% | 481800 | 0.9846 | 593133.6 | -9133.6 | 103798.38 | 0 | 0 | 0
25-110 | 02-200 | Earthwork & Excavation | Subcontract | 1048800 | 0 | 1048800 | 1007741.88 | 1013400 | 100% | 1048800 | 1.0407 | 1013400 | 35400 | 5658.12 | 0 | 0 | 0
25-110 | 03-100 | Concrete Formwork | Labour | 1195800 | 0 | 1195800 | 1244101.78 | 0 | 100% | 1195800 | 0.96118 | 1244101.78 | -48301.78 | 0 | 16159 | 16812.3 | 16159
25-110 | 03-200 | Reinforcing Steel | Material | 822400 | 0 | 822400 | 804629.42 | 808000 | 100% | 822400 | 1.0221 | 808000 | 14400 | 3370.58 | 0 | 0 | 0
25-110 | 03-300 | Cast-in-Place Concrete | Material | 1676400 | 0 | 1676400 | 1696698.96 | 1711500 | 100% | 1676400 | 0.98804 | 1711500 | -35100 | 14801.04 | 0 | 0 | 0
25-110 | 04-200 | Masonry | Subcontract | 750400 | 0 | 750400 | 703399.72 | 720700 | 100% | 750400 | 1.0668 | 720700 | 29700 | 17300.28 | 0 | 0 | 0
25-110 | 05-100 | Structural Steel | Subcontract | 2435200 | 0 | 2435200 | 3051539.5 | 3079300 | 100% | 2435200 | 0.79802 | 3079300 | -644100 | 27760.5 | 0 | 0 | 0
25-110 | 06-100 | Rough Carpentry | Labour | 921800 | 0 | 921800 | 603665.25 | 0 | 66.4% | 612075.2 | 1.0139 | 909134.4127 | 12665.5873 | 305469.1627 | 12983 | 8502.2 | 8620.712
25-110 | 07-200 | Roofing & Insulation | Subcontract | 1544900 | 0 | 1544900 | 1248558.64 | 1486700 | 85.5% | 1320889.5 | 1.0579 | 1486700 | 58200 | 238141.36 | 0 | 0 | 0
25-110 | 08-100 | Doors, Frames & Hardware | Material | 893600 | 0 | 893600 | 37275.84 | 908100 | 4.2% | 37531.2 | 1.0069 | 908100 | -14500 | 870824.16 | 0 | 0 | 0
25-110 | 09-200 | Drywall & Finishes | Subcontract | 1997100 | 492700 | 2489800 | 94023.73 | 2550500 | 3.7% | 92122.6 | 0.97978 | 2550500 | -60700 | 2456476.27 | 0 | 0 | 0
25-110 | 15-000 | Mechanical | Subcontract | 3272600 | 0 | 3272600 | 1629187.61 | 3362800 | 49.3% | 1613391.8 | 0.9903 | 3362800 | -90200 | 1733612.39 | 0 | 0 | 0
25-110 | 16-000 | Electrical | Subcontract | 2516600 | 0 | 2516600 | 1283961.58 | 2554100 | 50.9% | 1280949.4 | 0.99765 | 2554100 | -37500 | 1270138.42 | 0 | 0 | 0
25-112 | 01-100 | General Conditions - Supervision | Labour | 787900 | 0 | 787900 | 742454.25 | 0 | 94.7% | 746141.3 | 1.005 | 784006.5998 | 3893.4002 | 41552.3498 | 8564 | 8070.3 | 8110.108
25-112 | 01-200 | Site Facilities & Temp Services | Other | 232200 | 0 | 232200 | 218491.96 | 0 | 91.9% | 213391.8 | 0.97666 | 237749.6844 | -5549.6844 | 19257.7244 | 0 | 0 | 0
25-112 | 01-500 | Equipment Rental | Equipment | 205900 | 59600 | 265500 | 258929.42 | 0 | 100% | 265500 | 1.0254 | 258929.42 | 6570.58 | 0 | 0 | 0 | 0
25-112 | 02-200 | Earthwork & Excavation | Subcontract | 309200 | 0 | 309200 | 308006.35 | 315700 | 100% | 309200 | 1.0039 | 315700 | -6500 | 7693.65 | 0 | 0 | 0
25-112 | 03-100 | Concrete Formwork | Labour | 419000 | 0 | 419000 | 402636.38 | 0 | 100% | 419000 | 1.0406 | 402636.38 | 16363.62 | 0 | 5662 | 5440.6 | 5662
25-112 | 03-200 | Reinforcing Steel | Material | 280000 | 0 | 280000 | 284177.08 | 287900 | 100% | 280000 | 0.9853 | 287900 | -7900 | 3722.92 | 0 | 0 | 0
25-112 | 03-300 | Cast-in-Place Concrete | Material | 512100 | 0 | 512100 | 508704.12 | 518400 | 100% | 512100 | 1.0067 | 518400 | -6300 | 9695.88 | 0 | 0 | 0
25-112 | 04-200 | Masonry | Subcontract | 512600 | 0 | 512600 | 512065.15 | 520700 | 100% | 512600 | 1.001 | 520700 | -8100 | 8634.85 | 0 | 0 | 0
25-112 | 05-100 | Structural Steel | Subcontract | 696300 | 15200 | 711500 | 701679.6 | 705900 | 100% | 711500 | 1.014 | 705900 | 5600 | 4220.4 | 0 | 0 | 0
25-112 | 06-100 | Rough Carpentry | Labour | 294900 | 32200 | 327100 | 318677.73 | 0 | 100% | 327100 | 1.0264 | 318677.73 | 8422.27 | 0 | 4607 | 4488.3 | 4607
25-112 | 07-200 | Roofing & Insulation | Subcontract | 400400 | 0 | 400400 | 389056.75 | 400200 | 100% | 400400 | 1.0292 | 400200 | 200 | 11143.25 | 0 | 0 | 0
25-112 | 08-100 | Doors, Frames & Hardware | Material | 347500 | 0 | 347500 | 334701.95 | 355600 | 95.1% | 330472.5 | 0.98736 | 355600 | -8100 | 20898.05 | 0 | 0 | 0
25-112 | 09-200 | Drywall & Finishes | Subcontract | 799500 | 0 | 799500 | 730978.29 | 822900 | 90.4% | 722748 | 0.98874 | 822900 | -23400 | 91921.71 | 0 | 0 | 0
25-112 | 15-000 | Mechanical | Subcontract | 1250200 | 0 | 1250200 | 1194129.1 | 1267400 | 94.3% | 1178938.6 | 0.98728 | 1267400 | -17200 | 73270.9 | 0 | 0 | 0
25-112 | 16-000 | Electrical | Subcontract | 828900 | 0 | 828900 | 893002.49 | 980600 | 91.8% | 760930.2 | 0.8521 | 980600 | -151700 | 87597.51 | 0 | 0 | 0
25-115 | 01-100 | General Conditions - Supervision | Labour | 957900 | 0 | 957900 | 766276.35 | 0 | 76.3% | 730877.7 | 0.9538 | 1004294.0367 | -46394.0367 | 238017.6867 | 10412 | 8329 | 7944.356
25-115 | 01-200 | Site Facilities & Temp Services | Other | 313200 | 43300 | 356500 | 275153.11 | 0 | 74.3% | 264879.5 | 0.96266 | 370327.2005 | -13827.2005 | 95174.0905 | 0 | 0 | 0
25-115 | 01-500 | Equipment Rental | Equipment | 275800 | 0 | 275800 | 267801.12 | 0 | 90.4% | 249323.2 | 0.931 | 296240.177 | -20440.177 | 28439.057 | 0 | 0 | 0
25-115 | 02-200 | Earthwork & Excavation | Subcontract | 410500 | 0 | 410500 | 395353.03 | 396500 | 100% | 410500 | 1.0383 | 396500 | 14000 | 1146.97 | 0 | 0 | 0
25-115 | 03-100 | Concrete Formwork | Labour | 545200 | 549300 | 1094500 | 1229218.83 | 0 | 100% | 1094500 | 0.8904 | 1229218.83 | -134718.83 | 0 | 14791 | 16611.2 | 14791
25-115 | 03-200 | Reinforcing Steel | Material | 452600 | 0 | 452600 | 446285.28 | 456400 | 100% | 452600 | 1.0141 | 456400 | -3800 | 10114.72 | 0 | 0 | 0
25-115 | 03-300 | Cast-in-Place Concrete | Material | 763100 | 0 | 763100 | 756596.67 | 767600 | 100% | 763100 | 1.0086 | 767600 | -4500 | 11003.33 | 0 | 0 | 0
25-115 | 04-200 | Masonry | Subcontract | 789900 | 0 | 789900 | 808032.22 | 811100 | 100% | 789900 | 0.97756 | 811100 | -21200 | 3067.78 | 0 | 0 | 0
25-115 | 05-100 | Structural Steel | Subcontract | 730300 | 0 | 730300 | 731077.8 | 735800 | 100% | 730300 | 0.99894 | 735800 | -5500 | 4722.2 | 0 | 0 | 0
25-115 | 06-100 | Rough Carpentry | Labour | 385900 | 0 | 385900 | 360969.68 | 0 | 75.1% | 289810.9 | 0.80287 | 480652.0373 | -94752.0373 | 119682.3573 | 5435 | 5084.1 | 4081.685
25-115 | 07-200 | Roofing & Insulation | Subcontract | 647300 | 57600 | 704900 | 657408.01 | 705400 | 95.4% | 672474.6 | 1.0229 | 705400 | -500 | 47991.99 | 0 | 0 | 0
25-115 | 08-100 | Doors, Frames & Hardware | Material | 438400 | 0 | 438400 | 46792.64 | 430700 | 11% | 48224 | 1.0306 | 430700 | 7700 | 383907.36 | 0 | 0 | 0
25-115 | 09-200 | Drywall & Finishes | Subcontract | 874500 | 0 | 874500 | 81208.9 | 884500 | 9.4% | 82203 | 1.0122 | 884500 | -10000 | 803291.1 | 0 | 0 | 0
25-115 | 15-000 | Mechanical | Subcontract | 1463800 | 0 | 1463800 | 1151483.07 | 1898700 | 60.7% | 888526.6 | 0.77164 | 1898700 | -434900 | 747216.93 | 0 | 0 | 0
25-115 | 16-000 | Electrical | Subcontract | 1065000 | 0 | 1065000 | 608567.8 | 1052300 | 58.7% | 625155 | 1.0273 | 1052300 | 12700 | 443732.2 | 0 | 0 | 0
25-118 | 01-100 | General Conditions - Supervision | Labour | 1199900 | 0 | 1199900 | 953629.8 | 0 | 79.1% | 949120.9 | 0.99527 | 1205600.2528 | -5700.2528 | 251970.4528 | 13042 | 10365.8 | 10316.222
25-118 | 01-200 | Site Facilities & Temp Services | Other | 509000 | 0 | 509000 | 388824.89 | 0 | 77.4% | 393966 | 1.0132 | 502357.739 | 6642.261 | 113532.849 | 0 | 0 | 0
25-118 | 01-500 | Equipment Rental | Equipment | 658100 | 38300 | 696400 | 617946.11 | 0 | 89.6% | 623974.4 | 1.0098 | 689671.9978 | 6728.0022 | 71725.8878 | 0 | 0 | 0
25-118 | 02-200 | Earthwork & Excavation | Subcontract | 1227600 | 58200 | 1285800 | 1298186.18 | 1315300 | 100% | 1285800 | 0.99046 | 1315300 | -29500 | 17113.82 | 0 | 0 | 0
25-118 | 03-100 | Concrete Formwork | Labour | 873100 | 0 | 873100 | 857839.11 | 0 | 100% | 873100 | 1.0178 | 857839.11 | 15260.89 | 0 | 11799 | 11592.3 | 11799
25-118 | 03-200 | Reinforcing Steel | Material | 892600 | 0 | 892600 | 854863.53 | 881000 | 100% | 892600 | 1.0441 | 881000 | 11600 | 26136.47 | 0 | 0 | 0
25-118 | 03-300 | Cast-in-Place Concrete | Material | 1323200 | 0 | 1323200 | 1270216.59 | 1292800 | 100% | 1323200 | 1.0417 | 1292800 | 30400 | 22583.41 | 0 | 0 | 0
25-118 | 05-100 | Structural Steel | Subcontract | 2666800 | 0 | 2666800 | 2553992.93 | 2620700 | 100% | 2666800 | 1.0442 | 2620700 | 46100 | 66707.07 | 0 | 0 | 0
25-118 | 06-100 | Rough Carpentry | Labour | 337700 | 0 | 337700 | 255485.96 | 0 | 80.5% | 271848.5 | 1.064 | 317373.8634 | 20326.1366 | 61887.9034 | 4756 | 3598.4 | 3828.58
25-118 | 07-200 | Roofing & Insulation | Subcontract | 967600 | 0 | 967600 | 979805.56 | 990400 | 100% | 967600 | 0.98754 | 990400 | -22800 | 10594.44 | 0 | 0 | 0
25-118 | 08-100 | Doors, Frames & Hardware | Material | 289100 | 0 | 289100 | 47899.5 | 293600 | 16.8% | 48568.8 | 1.014 | 293600 | -4500 | 245700.5 | 0 | 0 | 0
25-118 | 09-200 | Drywall & Finishes | Subcontract | 637500 | 0 | 637500 | 91203.98 | 626700 | 14.7% | 93712.5 | 1.0275 | 626700 | 10800 | 535496.02 | 0 | 0 | 0
25-118 | 15-000 | Mechanical | Subcontract | 2513100 | 150000 | 2663100 | 1740749.17 | 2709200 | 64.8% | 1725688.8 | 0.99135 | 2709200 | -46100 | 968450.83 | 0 | 0 | 0
25-118 | 16-000 | Electrical | Subcontract | 1960400 | 0 | 1960400 | 1181480.68 | 1931200 | 61.9% | 1213487.6 | 1.0271 | 1931200 | 29200 | 749719.32 | 0 | 0 | 0
25-121 | 01-100 | General Conditions - Supervision | Labour | 1400200 | 0 | 1400200 | 555469.42 | 0 | 40.5% | 567081 | 1.0209 | 1371529.4321 | 28670.5679 | 816060.0121 | 15220 | 6037.6 | 6164.1
25-121 | 01-200 | Site Facilities & Temp Services | Other | 588300 | 177100 | 765400 | 284869.62 | 0 | 38.3% | 293148.2 | 1.0291 | 743784.9086 | 21615.0914 | 458915.2886 | 0 | 0 | 0
25-121 | 01-500 | Equipment Rental | Equipment | 546800 | 0 | 546800 | 291131.92 | 0 | 52.5% | 287070 | 0.98605 | 554536.9905 | -7736.9905 | 263405.0705 | 0 | 0 | 0
25-121 | 02-200 | Earthwork & Excavation | Subcontract | 705000 | 0 | 705000 | 708640.43 | 716500 | 100% | 705000 | 0.99486 | 716500 | -11500 | 7859.57 | 0 | 0 | 0
25-121 | 03-100 | Concrete Formwork | Labour | 809400 | 0 | 809400 | 796447.18 | 0 | 98.9% | 800496.6 | 1.0051 | 805305.541 | 4094.459 | 8858.361 | 10938 | 10762.8 | 10817.682
25-121 | 03-200 | Reinforcing Steel | Material | 546100 | 0 | 546100 | 530522.24 | 537500 | 100% | 546100 | 1.0294 | 537500 | 8600 | 6977.76 | 0 | 0 | 0
25-121 | 03-300 | Cast-in-Place Concrete | Material | 946000 | 0 | 946000 | 874565.45 | 933900 | 94.1% | 890186 | 1.0179 | 933900 | 12100 | 59334.55 | 0 | 0 | 0
25-121 | 04-200 | Masonry | Subcontract | 1108900 | 0 | 1108900 | 208485.85 | 1107700 | 19% | 210691 | 1.0106 | 1107700 | 1200 | 899214.15 | 0 | 0 | 0
25-121 | 05-100 | Structural Steel | Subcontract | 833800 | 0 | 833800 | 568252.76 | 809400 | 71.9% | 599502.2 | 1.055 | 809400 | 24400 | 241147.24 | 0 | 0 | 0
25-121 | 06-100 | Rough Carpentry | Labour | 1847600 | 71500 | 1919100 | 68200.63 | 0 | 3.6% | 69087.6 | 1.013 | 1894461.9444 | 24638.0556 | 1826261.3144 | 27030 | 960.5 | 973.08
25-121 | 07-200 | Roofing & Insulation | Subcontract | 957700 | 0 | 957700 | 0 | 967100 | 0% | 0 |  | 967100 | -9400 | 967100 | 0 | 0 | 0
25-121 | 08-100 | Doors, Frames & Hardware | Material | 991100 | 0 | 991100 | 0 | 973400 | 0% | 0 |  | 973400 | 17700 | 973400 | 0 | 0 | 0
25-121 | 09-200 | Drywall & Finishes | Subcontract | 2276000 | 0 | 2276000 | 0 | 2297400 | 0% | 0 |  | 2297400 | -21400 | 2297400 | 0 | 0 | 0
25-121 | 15-000 | Mechanical | Subcontract | 2300900 | 0 | 2300900 | 227233.87 | 2327200 | 9.9% | 227789.1 | 1.0024 | 2327200 | -26300 | 2099966.13 | 0 | 0 | 0
25-121 | 16-000 | Electrical | Subcontract | 2296800 | 138200 | 2435000 | 251060.15 | 2499100 | 10.1% | 245935 | 0.97959 | 2499100 | -64100 | 2248039.85 | 0 | 0 | 0
26-124 | 01-100 | General Conditions - Supervision | Labour | 938900 | 0 | 938900 | 355444.51 | 0 | 38.8% | 364293.2 | 1.0249 | 916094.0979 | 22805.9021 | 560649.5879 | 10205 | 3863.5 | 3959.54
26-124 | 01-200 | Site Facilities & Temp Services | Other | 328500 | 0 | 328500 | 128455.19 | 0 | 40.2% | 132057 | 1.028 | 319540.2736 | 8959.7264 | 191085.0836 | 0 | 0 | 0
26-124 | 01-500 | Equipment Rental | Equipment | 477600 | 0 | 477600 | 294796.88 | 0 | 51.2% | 244531.2 | 0.82949 | 575775.1562 | -98175.1562 | 280978.2762 | 0 | 0 | 0
26-124 | 02-200 | Earthwork & Excavation | Subcontract | 878600 | 0 | 878600 | 887650.02 | 903400 | 100% | 878600 | 0.9898 | 903400 | -24800 | 15749.98 | 0 | 0 | 0
26-124 | 03-100 | Concrete Formwork | Labour | 634200 | 0 | 634200 | 621384.37 | 0 | 95.5% | 605661 | 0.9747 | 650664.2618 | -16464.2618 | 29279.8918 | 8570 | 8397.2 | 8184.35
26-124 | 03-200 | Reinforcing Steel | Material | 687200 | 0 | 687200 | 702388.9 | 707200 | 100% | 687200 | 0.97838 | 707200 | -20000 | 4811.1 | 0 | 0 | 0
26-124 | 03-300 | Cast-in-Place Concrete | Material | 921200 | 0 | 921200 | 834902.39 | 892000 | 94.3% | 868691.6 | 1.0405 | 892000 | 29200 | 57097.61 | 0 | 0 | 0
26-124 | 05-100 | Structural Steel | Subcontract | 1650300 | 0 | 1650300 | 1170075.47 | 1648500 | 71.9% | 1186565.7 | 1.0141 | 1648500 | 1800 | 478424.53 | 0 | 0 | 0
26-124 | 06-100 | Rough Carpentry | Labour | 275000 | 0 | 275000 | 9729.02 | 0 | 3.5% | 9625 | 0.98931 | 277972 | -2972 | 268242.98 | 3873 | 137.1 | 135.555
26-124 | 07-200 | Roofing & Insulation | Subcontract | 772800 | 0 | 772800 | 0 | 783300 | 0% | 0 |  | 783300 | -10500 | 783300 | 0 | 0 | 0
26-124 | 08-100 | Doors, Frames & Hardware | Material | 216400 | 0 | 216400 | 0 | 222400 | 0% | 0 |  | 222400 | -6000 | 222400 | 0 | 0 | 0
26-124 | 09-200 | Drywall & Finishes | Subcontract | 477400 | 0 | 477400 | 0 | 475400 | 0% | 0 |  | 475400 | 2000 | 475400 | 0 | 0 | 0
26-124 | 15-000 | Mechanical | Subcontract | 1717600 | 0 | 1717600 | 182644.69 | 1765400 | 10.5% | 180348 | 0.98743 | 1765400 | -47800 | 1582755.31 | 0 | 0 | 0
26-124 | 16-000 | Electrical | Subcontract | 1883200 | 0 | 1883200 | 184739.4 | 1813600 | 10.5% | 197736 | 1.0704 | 1813600 | 69600 | 1628860.6 | 0 | 0 | 0
26-127 | 01-100 | General Conditions - Supervision | Labour | 609600 | 0 | 609600 | 205553.93 | 0 | 34% | 207264 | 1.0083 | 604570.3824 | 5029.6176 | 399016.4524 | 6626 | 2234.3 | 2252.84
26-127 | 01-200 | Site Facilities & Temp Services | Other | 183200 | 0 | 183200 | 63602.54 | 0 | 35.6% | 65219.2 | 1.0254 | 178658.8202 | 4541.1798 | 115056.2802 | 0 | 0 | 0
26-127 | 01-500 | Equipment Rental | Equipment | 226400 | 0 | 226400 | 103189.39 | 0 | 46.2% | 104596.8 | 1.0136 | 223353.658 | 3046.342 | 120164.268 | 0 | 0 | 0
26-127 | 02-200 | Earthwork & Excavation | Subcontract | 334700 | 0 | 334700 | 317917.75 | 327000 | 100% | 334700 | 1.0528 | 327000 | 7700 | 9082.25 | 0 | 0 | 0
26-127 | 03-100 | Concrete Formwork | Labour | 346800 | 0 | 346800 | 312995.42 | 0 | 95.2% | 330153.6 | 1.0548 | 328776.7017 | 18023.2983 | 15781.2817 | 4686 | 4229.5 | 4461.072
26-127 | 03-200 | Reinforcing Steel | Material | 234500 | 0 | 234500 | 230704.62 | 236000 | 100% | 234500 | 1.0165 | 236000 | -1500 | 5295.38 | 0 | 0 | 0
26-127 | 03-300 | Cast-in-Place Concrete | Material | 528400 | 0 | 528400 | 469679.48 | 530300 | 90.7% | 479258.8 | 1.0204 | 530300 | -1900 | 60620.52 | 0 | 0 | 0
26-127 | 04-200 | Masonry | Subcontract | 299100 | 0 | 299100 | 28087.4 | 287800 | 10% | 29910 | 1.0649 | 287800 | 11300 | 259712.6 | 0 | 0 | 0
26-127 | 05-100 | Structural Steel | Subcontract | 656400 | 0 | 656400 | 356006.11 | 642300 | 57.1% | 374804.4 | 1.0528 | 642300 | 14100 | 286293.89 | 0 | 0 | 0
26-127 | 06-100 | Rough Carpentry | Labour | 268600 | 0 | 268600 | 2440.5 | 0 | 0.9% | 2417.4 | 0.99053 | 271166.6667 | -2566.6667 | 268726.1667 | 3783 | 34.4 | 34.047
26-127 | 07-200 | Roofing & Insulation | Subcontract | 541300 | 0 | 541300 | 0 | 527900 | 0% | 0 |  | 527900 | 13400 | 527900 | 0 | 0 | 0
26-127 | 08-100 | Doors, Frames & Hardware | Material | 306300 | 0 | 306300 | 0 | 305400 | 0% | 0 |  | 305400 | 900 | 305400 | 0 | 0 | 0
26-127 | 09-200 | Drywall & Finishes | Subcontract | 530900 | 0 | 530900 | 0 | 527200 | 0% | 0 |  | 527200 | 3700 | 527200 | 0 | 0 | 0
26-127 | 15-000 | Mechanical | Subcontract | 907400 | 0 | 907400 | 63561.47 | 918500 | 7.1% | 64425.4 | 1.0136 | 918500 | -11100 | 854938.53 | 0 | 0 | 0
26-127 | 16-000 | Electrical | Subcontract | 720200 | 0 | 720200 | 47549.92 | 698500 | 7% | 50414 | 1.0602 | 698500 | 21700 | 650950.08 | 0 | 0 | 0
26-130 | 01-100 | General Conditions - Supervision | Labour | 547900 | 0 | 547900 | 62005.88 | 0 | 11.4% | 62460.6 | 1.0073 | 543911.2281 | 3988.7719 | 481905.3481 | 5955 | 673.8 | 678.87
26-130 | 01-200 | Site Facilities & Temp Services | Other | 177400 | 0 | 177400 | 19387.93 | 0 | 10.9% | 19336.6 | 0.99735 | 177870.9174 | -470.9174 | 158482.9874 | 0 | 0 | 0
26-130 | 01-500 | Equipment Rental | Equipment | 141200 | 0 | 141200 | 18335.99 | 0 | 13.1% | 18497.2 | 1.0088 | 139969.3893 | 1230.6107 | 121633.3993 | 0 | 0 | 0
26-130 | 02-200 | Earthwork & Excavation | Subcontract | 223200 | 0 | 223200 | 197258.66 | 215500 | 93.8% | 209361.6 | 1.0614 | 215500 | 7700 | 18241.34 | 0 | 0 | 0
26-130 | 03-100 | Concrete Formwork | Labour | 292200 | 0 | 292200 | 87859.26 | 0 | 30.4% | 88828.8 | 1.011 | 289010.7237 | 3189.2763 | 201151.4637 | 3949 | 1187.3 | 1200.496
26-130 | 03-200 | Reinforcing Steel | Material | 229900 | 0 | 229900 | 79312.22 | 231200 | 34.4% | 79085.6 | 0.99714 | 231200 | -1300 | 151887.78 | 0 | 0 | 0
26-130 | 03-300 | Cast-in-Place Concrete | Material | 346900 | 0 | 346900 | 76577.64 | 354700 | 21.9% | 75971.1 | 0.99208 | 354700 | -7800 | 278122.36 | 0 | 0 | 0
26-130 | 04-200 | Masonry | Subcontract | 428600 | 0 | 428600 | 0 | 423200 | 0% | 0 |  | 423200 | 5400 | 423200 | 0 | 0 | 0
26-130 | 05-100 | Structural Steel | Subcontract | 397200 | 0 | 397200 | 0 | 396800 | 0% | 0 |  | 396800 | 400 | 396800 | 0 | 0 | 0
26-130 | 06-100 | Rough Carpentry | Labour | 242600 | 0 | 242600 | 0 | 0 | 0% | 0 |  | 242600 | 0 | 242600 | 3417 | 0 | 0
26-130 | 07-200 | Roofing & Insulation | Subcontract | 309600 | 0 | 309600 | 0 | 320500 | 0% | 0 |  | 320500 | -10900 | 320500 | 0 | 0 | 0
26-130 | 08-100 | Doors, Frames & Hardware | Material | 206300 | 0 | 206300 | 0 | 0 | 0% | 0 |  | 206300 | 0 | 206300 | 0 | 0 | 0
26-130 | 09-200 | Drywall & Finishes | Subcontract | 512500 | 0 | 512500 | 0 | 0 | 0% | 0 |  | 512500 | 0 | 512500 | 0 | 0 | 0
26-130 | 15-000 | Mechanical | Subcontract | 839000 | 0 | 839000 | 0 | 829600 | 0% | 0 |  | 829600 | 9400 | 829600 | 0 | 0 | 0
26-130 | 16-000 | Electrical | Subcontract | 712600 | 0 | 712600 | 0 | 715300 | 0% | 0 |  | 715300 | -2700 | 715300 | 0 | 0 | 0
Total |  |  |  | 154155800 | 4097900 | 158253700 | 114578264.51 | 120824700 |  | 113719298 | 0.9925 | 160824398.0686 | -2570698.0686 | 46246133.5586 | 348577 | 268954 | 262803.417

## Data_Jobs
job_no | job_name | job_type | client_type | project_manager | original_contract | approved_change_orders | bid_margin_pct | start_date | scheduled_finish | revised_contract | status | company
23-098 | Transit Bus Garage Upgrade | Institutional | Municipal | R. Singh | 14850000 | 612000 | 10.5% | 2024-06-03 | 2026-08-28 | 15462000 | Substantially complete | Boreal Ridge Construction Ltd. (fictional)
24-101 | Leduc Distribution Warehouse | Industrial | Private developer | M. Okafor | 21400000 | 845000 | 9.5% | 2025-03-03 | 2026-12-18 | 22245000 | In progress | Boreal Ridge Construction Ltd. (fictional)
24-104 | School Modernization - Phase 2 | Institutional | School board | J. Tremblay | 16200000 | 338000 | 11% | 2025-05-05 | 2027-01-29 | 16538000 | In progress | Boreal Ridge Construction Ltd. (fictional)
24-107 | Fabrication Shop Expansion | Industrial | Private industrial | M. Okafor | 9750000 | 410000 | 12% | 2025-06-02 | 2026-10-30 | 10160000 | In progress | Boreal Ridge Construction Ltd. (fictional)
25-110 | Medical Office Building | Commercial | Private developer | S. Chen | 24600000 | 980000 | 10% | 2025-08-04 | 2027-05-28 | 25580000 | In progress | Boreal Ridge Construction Ltd. (fictional)
25-112 | Fire Hall No. 4 | Institutional | Municipal | R. Singh | 8900000 | 126000 | 11.5% | 2025-09-08 | 2026-11-27 | 9026000 | In progress | Boreal Ridge Construction Ltd. (fictional)
25-115 | Recreation Centre Retrofit | Institutional | Municipal | J. Tremblay | 11300000 | 765000 | 10.5% | 2025-10-06 | 2027-03-26 | 12065000 | In progress | Boreal Ridge Construction Ltd. (fictional)
25-118 | Cold Storage Facility | Industrial | Private industrial | S. Chen | 17800000 | 290000 | 9.8% | 2025-11-03 | 2027-02-26 | 18090000 | In progress | Boreal Ridge Construction Ltd. (fictional)
25-121 | Seniors Residence | Residential | Non-profit | A. Dubois | 19950000 | 455000 | 9% | 2026-01-12 | 2027-08-27 | 20405000 | In progress | Boreal Ridge Construction Ltd. (fictional)
26-124 | Process Building | Industrial | Private industrial | M. Okafor | 13400000 | 0 | 11.5% | 2026-03-02 | 2027-06-25 | 13400000 | In progress | Boreal Ridge Construction Ltd. (fictional)
26-127 | Retail Plaza | Commercial | Private developer | A. Dubois | 7650000 | 0 | 12.5% | 2026-05-04 | 2027-04-30 | 7650000 | In progress | Boreal Ridge Construction Ltd. (fictional)
26-130 | Public Works Yard Building | Institutional | Municipal | R. Singh | 6300000 | 0 | 11% | 2026-07-06 | 2027-07-30 | 6300000 | In progress | Boreal Ridge Construction Ltd. (fictional)

## Data_CostCodes
cost_code | description | division | cost_type
01-100 | General Conditions - Supervision | 01 | Labour
01-200 | Site Facilities & Temp Services | 01 | Other
01-500 | Equipment Rental | 01 | Equipment
02-200 | Earthwork & Excavation | 02 | Subcontract
03-100 | Concrete Formwork | 03 | Labour
03-200 | Reinforcing Steel | 03 | Material
03-300 | Cast-in-Place Concrete | 03 | Material
04-200 | Masonry | 04 | Subcontract
05-100 | Structural Steel | 05 | Subcontract
06-100 | Rough Carpentry | 06 | Labour
07-200 | Roofing & Insulation | 07 | Subcontract
08-100 | Doors, Frames & Hardware | 08 | Material
09-200 | Drywall & Finishes | 09 | Subcontract
15-000 | Mechanical | 15 | Subcontract
16-000 | Electrical | 16 | Subcontract

## Data_Budgets
job_no | cost_code | original_budget | approved_budget_changes | revised_budget | budget_hours
23-098 | 01-100 | 1055600 | 0 | 1055600 | 11474
23-098 | 01-200 | 405700 | 0 | 405700 | 0
23-098 | 01-500 | 385500 | 0 | 385500 | 0
23-098 | 02-200 | 499000 | 0 | 499000 | 0
23-098 | 03-100 | 620700 | 0 | 620700 | 8388
23-098 | 03-200 | 564400 | 0 | 564400 | 0
23-098 | 03-300 | 1018900 | 0 | 1018900 | 0
23-098 | 04-200 | 820600 | 0 | 820600 | 0
23-098 | 05-100 | 1085900 | 121300 | 1207200 | 0
23-098 | 06-100 | 487700 | 41900 | 529600 | 7459
23-098 | 07-200 | 887800 | 0 | 887800 | 0
23-098 | 08-100 | 584500 | 357000 | 941500 | 0
23-098 | 09-200 | 1215700 | 0 | 1215700 | 0
23-098 | 15-000 | 2094400 | 0 | 2094400 | 0
23-098 | 16-000 | 1564500 | 0 | 1564500 | 0
24-101 | 01-100 | 1406900 | 0 | 1406900 | 15292
24-101 | 01-200 | 580100 | 313000 | 893100 | 0
24-101 | 01-500 | 790300 | 0 | 790300 | 0
24-101 | 02-200 | 1483000 | 145300 | 1628300 | 0
24-101 | 03-100 | 1211100 | 0 | 1211100 | 16366
24-101 | 03-200 | 989400 | 260000 | 1249400 | 0
24-101 | 03-300 | 1614300 | 0 | 1614300 | 0
24-101 | 05-100 | 3037500 | 0 | 3037500 | 0
24-101 | 06-100 | 359000 | 0 | 359000 | 5056
24-101 | 07-200 | 1116300 | 0 | 1116300 | 0
24-101 | 08-100 | 389800 | 0 | 389800 | 0
24-101 | 09-200 | 737800 | 0 | 737800 | 0
24-101 | 15-000 | 2603000 | 0 | 2603000 | 0
24-101 | 16-000 | 3048400 | 0 | 3048400 | 0
24-104 | 01-100 | 1243700 | 25100 | 1268800 | 13791
24-104 | 01-200 | 445000 | 0 | 445000 | 0
24-104 | 01-500 | 362600 | 0 | 362600 | 0
24-104 | 02-200 | 542400 | 0 | 542400 | 0
24-104 | 03-100 | 625800 | 0 | 625800 | 8457
24-104 | 03-200 | 525100 | 0 | 525100 | 0
24-104 | 03-300 | 850700 | 0 | 850700 | 0
24-104 | 04-200 | 989600 | 0 | 989600 | 0
24-104 | 05-100 | 1228200 | 0 | 1228200 | 0
24-104 | 06-100 | 606300 | 0 | 606300 | 8539
24-104 | 07-200 | 973800 | 177600 | 1151400 | 0
24-104 | 08-100 | 635200 | 0 | 635200 | 0
24-104 | 09-200 | 1354700 | 84600 | 1439300 | 0
24-104 | 15-000 | 2291900 | 0 | 2291900 | 0
24-104 | 16-000 | 1742900 | 0 | 1742900 | 0
24-107 | 01-100 | 768500 | 203100 | 971600 | 10561
24-107 | 01-200 | 246700 | 0 | 246700 | 0
24-107 | 01-500 | 340900 | 35700 | 376600 | 0
24-107 | 02-200 | 642100 | 0 | 642100 | 0
24-107 | 03-100 | 523800 | 0 | 523800 | 7078
24-107 | 03-200 | 471200 | 109700 | 580900 | 0
24-107 | 03-300 | 665100 | 0 | 665100 | 0
24-107 | 05-100 | 1231200 | 0 | 1231200 | 0
24-107 | 06-100 | 176500 | 0 | 176500 | 2486
24-107 | 07-200 | 528300 | 0 | 528300 | 0
24-107 | 08-100 | 153800 | 0 | 153800 | 0
24-107 | 09-200 | 294700 | 0 | 294700 | 0
24-107 | 15-000 | 1203300 | 0 | 1203300 | 0
24-107 | 16-000 | 1333800 | 0 | 1333800 | 0
25-110 | 01-100 | 1916200 | 31300 | 1947500 | 21168
25-110 | 01-200 | 564300 | 309100 | 873400 | 0
25-110 | 01-500 | 584000 | 0 | 584000 | 0
25-110 | 02-200 | 1048800 | 0 | 1048800 | 0
25-110 | 03-100 | 1195800 | 0 | 1195800 | 16159
25-110 | 03-200 | 822400 | 0 | 822400 | 0
25-110 | 03-300 | 1676400 | 0 | 1676400 | 0
25-110 | 04-200 | 750400 | 0 | 750400 | 0
25-110 | 05-100 | 2435200 | 0 | 2435200 | 0
25-110 | 06-100 | 921800 | 0 | 921800 | 12983
25-110 | 07-200 | 1544900 | 0 | 1544900 | 0
25-110 | 08-100 | 893600 | 0 | 893600 | 0
25-110 | 09-200 | 1997100 | 492700 | 2489800 | 0
25-110 | 15-000 | 3272600 | 0 | 3272600 | 0
25-110 | 16-000 | 2516600 | 0 | 2516600 | 0
25-112 | 01-100 | 787900 | 0 | 787900 | 8564
25-112 | 01-200 | 232200 | 0 | 232200 | 0
25-112 | 01-500 | 205900 | 59600 | 265500 | 0
25-112 | 02-200 | 309200 | 0 | 309200 | 0
25-112 | 03-100 | 419000 | 0 | 419000 | 5662
25-112 | 03-200 | 280000 | 0 | 280000 | 0
25-112 | 03-300 | 512100 | 0 | 512100 | 0
25-112 | 04-200 | 512600 | 0 | 512600 | 0
25-112 | 05-100 | 696300 | 15200 | 711500 | 0
25-112 | 06-100 | 294900 | 32200 | 327100 | 4607
25-112 | 07-200 | 400400 | 0 | 400400 | 0
25-112 | 08-100 | 347500 | 0 | 347500 | 0
25-112 | 09-200 | 799500 | 0 | 799500 | 0
25-112 | 15-000 | 1250200 | 0 | 1250200 | 0
25-112 | 16-000 | 828900 | 0 | 828900 | 0
25-115 | 01-100 | 957900 | 0 | 957900 | 10412
25-115 | 01-200 | 313200 | 43300 | 356500 | 0
25-115 | 01-500 | 275800 | 0 | 275800 | 0
25-115 | 02-200 | 410500 | 0 | 410500 | 0
25-115 | 03-100 | 545200 | 549300 | 1094500 | 14791
25-115 | 03-200 | 452600 | 0 | 452600 | 0
25-115 | 03-300 | 763100 | 0 | 763100 | 0
25-115 | 04-200 | 789900 | 0 | 789900 | 0
25-115 | 05-100 | 730300 | 0 | 730300 | 0
25-115 | 06-100 | 385900 | 0 | 385900 | 5435
25-115 | 07-200 | 647300 | 57600 | 704900 | 0
25-115 | 08-100 | 438400 | 0 | 438400 | 0
25-115 | 09-200 | 874500 | 0 | 874500 | 0
25-115 | 15-000 | 1463800 | 0 | 1463800 | 0
25-115 | 16-000 | 1065000 | 0 | 1065000 | 0
25-118 | 01-100 | 1199900 | 0 | 1199900 | 13042
25-118 | 01-200 | 509000 | 0 | 509000 | 0
25-118 | 01-500 | 658100 | 38300 | 696400 | 0
25-118 | 02-200 | 1227600 | 58200 | 1285800 | 0
25-118 | 03-100 | 873100 | 0 | 873100 | 11799
25-118 | 03-200 | 892600 | 0 | 892600 | 0
25-118 | 03-300 | 1323200 | 0 | 1323200 | 0
25-118 | 05-100 | 2666800 | 0 | 2666800 | 0
25-118 | 06-100 | 337700 | 0 | 337700 | 4756
25-118 | 07-200 | 967600 | 0 | 967600 | 0
25-118 | 08-100 | 289100 | 0 | 289100 | 0
25-118 | 09-200 | 637500 | 0 | 637500 | 0
25-118 | 15-000 | 2513100 | 150000 | 2663100 | 0
25-118 | 16-000 | 1960400 | 0 | 1960400 | 0
25-121 | 01-100 | 1400200 | 0 | 1400200 | 15220
25-121 | 01-200 | 588300 | 177100 | 765400 | 0
25-121 | 01-500 | 546800 | 0 | 546800 | 0
25-121 | 02-200 | 705000 | 0 | 705000 | 0
25-121 | 03-100 | 809400 | 0 | 809400 | 10938
25-121 | 03-200 | 546100 | 0 | 546100 | 0
25-121 | 03-300 | 946000 | 0 | 946000 | 0
25-121 | 04-200 | 1108900 | 0 | 1108900 | 0
25-121 | 05-100 | 833800 | 0 | 833800 | 0
25-121 | 06-100 | 1847600 | 71500 | 1919100 | 27030
25-121 | 07-200 | 957700 | 0 | 957700 | 0
25-121 | 08-100 | 991100 | 0 | 991100 | 0
25-121 | 09-200 | 2276000 | 0 | 2276000 | 0
25-121 | 15-000 | 2300900 | 0 | 2300900 | 0
25-121 | 16-000 | 2296800 | 138200 | 2435000 | 0
26-124 | 01-100 | 938900 | 0 | 938900 | 10205
26-124 | 01-200 | 328500 | 0 | 328500 | 0
26-124 | 01-500 | 477600 | 0 | 477600 | 0
26-124 | 02-200 | 878600 | 0 | 878600 | 0
26-124 | 03-100 | 634200 | 0 | 634200 | 8570
26-124 | 03-200 | 687200 | 0 | 687200 | 0
26-124 | 03-300 | 921200 | 0 | 921200 | 0
26-124 | 05-100 | 1650300 | 0 | 1650300 | 0
26-124 | 06-100 | 275000 | 0 | 275000 | 3873
26-124 | 07-200 | 772800 | 0 | 772800 | 0
26-124 | 08-100 | 216400 | 0 | 216400 | 0
26-124 | 09-200 | 477400 | 0 | 477400 | 0
26-124 | 15-000 | 1717600 | 0 | 1717600 | 0
26-124 | 16-000 | 1883200 | 0 | 1883200 | 0
26-127 | 01-100 | 609600 | 0 | 609600 | 6626
26-127 | 01-200 | 183200 | 0 | 183200 | 0
26-127 | 01-500 | 226400 | 0 | 226400 | 0
26-127 | 02-200 | 334700 | 0 | 334700 | 0
26-127 | 03-100 | 346800 | 0 | 346800 | 4686
26-127 | 03-200 | 234500 | 0 | 234500 | 0
26-127 | 03-300 | 528400 | 0 | 528400 | 0
26-127 | 04-200 | 299100 | 0 | 299100 | 0
26-127 | 05-100 | 656400 | 0 | 656400 | 0
26-127 | 06-100 | 268600 | 0 | 268600 | 3783
26-127 | 07-200 | 541300 | 0 | 541300 | 0
26-127 | 08-100 | 306300 | 0 | 306300 | 0
26-127 | 09-200 | 530900 | 0 | 530900 | 0
26-127 | 15-000 | 907400 | 0 | 907400 | 0
26-127 | 16-000 | 720200 | 0 | 720200 | 0
26-130 | 01-100 | 547900 | 0 | 547900 | 5955
26-130 | 01-200 | 177400 | 0 | 177400 | 0
26-130 | 01-500 | 141200 | 0 | 141200 | 0
26-130 | 02-200 | 223200 | 0 | 223200 | 0
26-130 | 03-100 | 292200 | 0 | 292200 | 3949
26-130 | 03-200 | 229900 | 0 | 229900 | 0
26-130 | 03-300 | 346900 | 0 | 346900 | 0
26-130 | 04-200 | 428600 | 0 | 428600 | 0
26-130 | 05-100 | 397200 | 0 | 397200 | 0
26-130 | 06-100 | 242600 | 0 | 242600 | 3417
26-130 | 07-200 | 309600 | 0 | 309600 | 0
26-130 | 08-100 | 206300 | 0 | 206300 | 0
26-130 | 09-200 | 512500 | 0 | 512500 | 0
26-130 | 15-000 | 839000 | 0 | 839000 | 0
26-130 | 16-000 | 712600 | 0 | 712600 | 0

## Data_Progress
job_no | cost_code | pct_complete
23-098 | 01-100 | 98%
23-098 | 01-200 | 100%
23-098 | 01-500 | 100%
23-098 | 02-200 | 100%
23-098 | 03-100 | 100%
23-098 | 03-200 | 100%
23-098 | 03-300 | 100%
23-098 | 04-200 | 100%
23-098 | 05-100 | 100%
23-098 | 06-100 | 100%
23-098 | 07-200 | 100%
23-098 | 08-100 | 100%
23-098 | 09-200 | 100%
23-098 | 15-000 | 100%
23-098 | 16-000 | 100%
24-101 | 01-100 | 95.6%
24-101 | 01-200 | 93.3%
24-101 | 01-500 | 100%
24-101 | 02-200 | 100%
24-101 | 03-100 | 100%
24-101 | 03-200 | 100%
24-101 | 03-300 | 100%
24-101 | 05-100 | 100%
24-101 | 06-100 | 100%
24-101 | 07-200 | 100%
24-101 | 08-100 | 94.2%
24-101 | 09-200 | 93.1%
24-101 | 15-000 | 96.7%
24-101 | 16-000 | 91.5%
24-104 | 01-100 | 93.6%
24-104 | 01-200 | 91.7%
24-104 | 01-500 | 96.7%
24-104 | 02-200 | 100%
24-104 | 03-100 | 100%
24-104 | 03-200 | 100%
24-104 | 03-300 | 100%
24-104 | 04-200 | 100%
24-104 | 05-100 | 100%
24-104 | 06-100 | 100%
24-104 | 07-200 | 100%
24-104 | 08-100 | 75.1%
24-104 | 09-200 | 64.5%
24-104 | 15-000 | 87.3%
24-104 | 16-000 | 86.4%
24-107 | 01-100 | 99.4%
24-107 | 01-200 | 94.6%
24-107 | 01-500 | 100%
24-107 | 02-200 | 100%
24-107 | 03-100 | 100%
24-107 | 03-200 | 100%
24-107 | 03-300 | 100%
24-107 | 05-100 | 100%
24-107 | 06-100 | 100%
24-107 | 07-200 | 100%
24-107 | 08-100 | 100%
24-107 | 09-200 | 100%
24-107 | 15-000 | 99.2%
24-107 | 16-000 | 99.5%
25-110 | 01-100 | 70.5%
25-110 | 01-200 | 72.4%
25-110 | 01-500 | 82.5%
25-110 | 02-200 | 100%
25-110 | 03-100 | 100%
25-110 | 03-200 | 100%
25-110 | 03-300 | 100%
25-110 | 04-200 | 100%
25-110 | 05-100 | 100%
25-110 | 06-100 | 66.4%
25-110 | 07-200 | 85.5%
25-110 | 08-100 | 4.2%
25-110 | 09-200 | 3.7%
25-110 | 15-000 | 49.3%
25-110 | 16-000 | 50.9%
25-112 | 01-100 | 94.7%
25-112 | 01-200 | 91.9%
25-112 | 01-500 | 100%
25-112 | 02-200 | 100%
25-112 | 03-100 | 100%
25-112 | 03-200 | 100%
25-112 | 03-300 | 100%
25-112 | 04-200 | 100%
25-112 | 05-100 | 100%
25-112 | 06-100 | 100%
25-112 | 07-200 | 100%
25-112 | 08-100 | 95.1%
25-112 | 09-200 | 90.4%
25-112 | 15-000 | 94.3%
25-112 | 16-000 | 91.8%
25-115 | 01-100 | 76.3%
25-115 | 01-200 | 74.3%
25-115 | 01-500 | 90.4%
25-115 | 02-200 | 100%
25-115 | 03-100 | 100%
25-115 | 03-200 | 100%
25-115 | 03-300 | 100%
25-115 | 04-200 | 100%
25-115 | 05-100 | 100%
25-115 | 06-100 | 75.1%
25-115 | 07-200 | 95.4%
25-115 | 08-100 | 11%
25-115 | 09-200 | 9.4%
25-115 | 15-000 | 60.7%
25-115 | 16-000 | 58.7%
25-118 | 01-100 | 79.1%
25-118 | 01-200 | 77.4%
25-118 | 01-500 | 89.6%
25-118 | 02-200 | 100%
25-118 | 03-100 | 100%
25-118 | 03-200 | 100%
25-118 | 03-300 | 100%
25-118 | 05-100 | 100%
25-118 | 06-100 | 80.5%
25-118 | 07-200 | 100%
25-118 | 08-100 | 16.8%
25-118 | 09-200 | 14.7%
25-118 | 15-000 | 64.8%
25-118 | 16-000 | 61.9%
25-121 | 01-100 | 40.5%
25-121 | 01-200 | 38.3%
25-121 | 01-500 | 52.5%
25-121 | 02-200 | 100%
25-121 | 03-100 | 98.9%
25-121 | 03-200 | 100%
25-121 | 03-300 | 94.1%
25-121 | 04-200 | 19%
25-121 | 05-100 | 71.9%
25-121 | 06-100 | 3.6%
25-121 | 07-200 | 0%
25-121 | 08-100 | 0%
25-121 | 09-200 | 0%
25-121 | 15-000 | 9.9%
25-121 | 16-000 | 10.1%
26-124 | 01-100 | 38.8%
26-124 | 01-200 | 40.2%
26-124 | 01-500 | 51.2%
26-124 | 02-200 | 100%
26-124 | 03-100 | 95.5%
26-124 | 03-200 | 100%
26-124 | 03-300 | 94.3%
26-124 | 05-100 | 71.9%
26-124 | 06-100 | 3.5%
26-124 | 07-200 | 0%
26-124 | 08-100 | 0%
26-124 | 09-200 | 0%
26-124 | 15-000 | 10.5%
26-124 | 16-000 | 10.5%
26-127 | 01-100 | 34%
26-127 | 01-200 | 35.6%
26-127 | 01-500 | 46.2%
26-127 | 02-200 | 100%
26-127 | 03-100 | 95.2%
26-127 | 03-200 | 100%
26-127 | 03-300 | 90.7%
26-127 | 04-200 | 10%
26-127 | 05-100 | 57.1%
26-127 | 06-100 | 0.9%
26-127 | 07-200 | 0%
26-127 | 08-100 | 0%
26-127 | 09-200 | 0%
26-127 | 15-000 | 7.1%
26-127 | 16-000 | 7%
26-130 | 01-100 | 11.4%
26-130 | 01-200 | 10.9%
26-130 | 01-500 | 13.1%
26-130 | 02-200 | 93.8%
26-130 | 03-100 | 30.4%
26-130 | 03-200 | 34.4%
26-130 | 03-300 | 21.9%
26-130 | 04-200 | 0%
26-130 | 05-100 | 0%
26-130 | 06-100 | 0%
26-130 | 07-200 | 0%
26-130 | 08-100 | 0%
26-130 | 09-200 | 0%
26-130 | 15-000 | 0%
26-130 | 16-000 | 0%

## Data_Commitments
commitment_no | job_no | cost_code | commitment_type | committed_amount
SC-20001 | 23-098 | 02-200 | Subcontract | 504300
PO-20002 | 23-098 | 03-200 | Material | 557000
PO-20003 | 23-098 | 03-300 | Material | 1000500
SC-20004 | 23-098 | 04-200 | Subcontract | 796800
SC-20005 | 23-098 | 05-100 | Subcontract | 1239500
SC-20006 | 23-098 | 07-200 | Subcontract | 883100
PO-20007 | 23-098 | 08-100 | Material | 952900
SC-20008 | 23-098 | 09-200 | Subcontract | 1208700
SC-20009 | 23-098 | 15-000 | Subcontract | 2618700
SC-20010 | 23-098 | 16-000 | Subcontract | 1596700
SC-20011 | 24-101 | 02-200 | Subcontract | 1628400
PO-20012 | 24-101 | 03-200 | Material | 1249400
PO-20013 | 24-101 | 03-300 | Material | 1566400
SC-20014 | 24-101 | 05-100 | Subcontract | 3076400
SC-20015 | 24-101 | 07-200 | Subcontract | 1083200
PO-20016 | 24-101 | 08-100 | Material | 384200
SC-20017 | 24-101 | 09-200 | Subcontract | 727500
SC-20018 | 24-101 | 15-000 | Subcontract | 2532000
SC-20019 | 24-101 | 16-000 | Subcontract | 2938600
SC-20020 | 24-104 | 02-200 | Subcontract | 549400
PO-20021 | 24-104 | 03-200 | Material | 505200
PO-20022 | 24-104 | 03-300 | Material | 833200
SC-20023 | 24-104 | 04-200 | Subcontract | 978100
SC-20024 | 24-104 | 05-100 | Subcontract | 1257200
SC-20025 | 24-104 | 07-200 | Subcontract | 1108500
PO-20026 | 24-104 | 08-100 | Material | 643900
SC-20027 | 24-104 | 09-200 | Subcontract | 1857800
SC-20028 | 24-104 | 15-000 | Subcontract | 2206000
SC-20029 | 24-104 | 16-000 | Subcontract | 1754100
SC-20030 | 24-107 | 02-200 | Subcontract | 645600
PO-20031 | 24-107 | 03-200 | Material | 572900
PO-20032 | 24-107 | 03-300 | Material | 660000
SC-20033 | 24-107 | 05-100 | Subcontract | 1229000
SC-20034 | 24-107 | 07-200 | Subcontract | 522300
PO-20035 | 24-107 | 08-100 | Material | 151000
SC-20036 | 24-107 | 09-200 | Subcontract | 285800
SC-20037 | 24-107 | 15-000 | Subcontract | 1172500
SC-20038 | 24-107 | 16-000 | Subcontract | 1309500
SC-20039 | 25-110 | 02-200 | Subcontract | 1013400
PO-20040 | 25-110 | 03-200 | Material | 808000
PO-20041 | 25-110 | 03-300 | Material | 1711500
SC-20042 | 25-110 | 04-200 | Subcontract | 720700
SC-20043 | 25-110 | 05-100 | Subcontract | 3079300
SC-20044 | 25-110 | 07-200 | Subcontract | 1486700
PO-20045 | 25-110 | 08-100 | Material | 908100
SC-20046 | 25-110 | 09-200 | Subcontract | 2550500
SC-20047 | 25-110 | 15-000 | Subcontract | 3362800
SC-20048 | 25-110 | 16-000 | Subcontract | 2554100
SC-20049 | 25-112 | 02-200 | Subcontract | 315700
PO-20050 | 25-112 | 03-200 | Material | 287900
PO-20051 | 25-112 | 03-300 | Material | 518400
SC-20052 | 25-112 | 04-200 | Subcontract | 520700
SC-20053 | 25-112 | 05-100 | Subcontract | 705900
SC-20054 | 25-112 | 07-200 | Subcontract | 400200
PO-20055 | 25-112 | 08-100 | Material | 355600
SC-20056 | 25-112 | 09-200 | Subcontract | 822900
SC-20057 | 25-112 | 15-000 | Subcontract | 1267400
SC-20058 | 25-112 | 16-000 | Subcontract | 980600
SC-20059 | 25-115 | 02-200 | Subcontract | 396500
PO-20060 | 25-115 | 03-200 | Material | 456400
PO-20061 | 25-115 | 03-300 | Material | 767600
SC-20062 | 25-115 | 04-200 | Subcontract | 811100
SC-20063 | 25-115 | 05-100 | Subcontract | 735800
SC-20064 | 25-115 | 07-200 | Subcontract | 705400
PO-20065 | 25-115 | 08-100 | Material | 430700
SC-20066 | 25-115 | 09-200 | Subcontract | 884500
SC-20067 | 25-115 | 15-000 | Subcontract | 1898700
SC-20068 | 25-115 | 16-000 | Subcontract | 1052300
SC-20069 | 25-118 | 02-200 | Subcontract | 1315300
PO-20070 | 25-118 | 03-200 | Material | 881000
PO-20071 | 25-118 | 03-300 | Material | 1292800
SC-20072 | 25-118 | 05-100 | Subcontract | 2620700
SC-20073 | 25-118 | 07-200 | Subcontract | 990400
PO-20074 | 25-118 | 08-100 | Material | 293600
SC-20075 | 25-118 | 09-200 | Subcontract | 626700
SC-20076 | 25-118 | 15-000 | Subcontract | 2709200
SC-20077 | 25-118 | 16-000 | Subcontract | 1931200
SC-20078 | 25-121 | 02-200 | Subcontract | 716500
PO-20079 | 25-121 | 03-200 | Material | 537500
PO-20080 | 25-121 | 03-300 | Material | 933900
SC-20081 | 25-121 | 04-200 | Subcontract | 1107700
SC-20082 | 25-121 | 05-100 | Subcontract | 809400
SC-20083 | 25-121 | 07-200 | Subcontract | 967100
PO-20084 | 25-121 | 08-100 | Material | 973400
SC-20085 | 25-121 | 09-200 | Subcontract | 2297400
SC-20086 | 25-121 | 15-000 | Subcontract | 2327200
SC-20087 | 25-121 | 16-000 | Subcontract | 2499100
SC-20088 | 26-124 | 02-200 | Subcontract | 903400
PO-20089 | 26-124 | 03-200 | Material | 707200
PO-20090 | 26-124 | 03-300 | Material | 892000
SC-20091 | 26-124 | 05-100 | Subcontract | 1648500
SC-20092 | 26-124 | 07-200 | Subcontract | 783300
PO-20093 | 26-124 | 08-100 | Material | 222400
SC-20094 | 26-124 | 09-200 | Subcontract | 475400
SC-20095 | 26-124 | 15-000 | Subcontract | 1765400
SC-20096 | 26-124 | 16-000 | Subcontract | 1813600
SC-20097 | 26-127 | 02-200 | Subcontract | 327000
PO-20098 | 26-127 | 03-200 | Material | 236000
PO-20099 | 26-127 | 03-300 | Material | 530300
SC-20100 | 26-127 | 04-200 | Subcontract | 287800
SC-20101 | 26-127 | 05-100 | Subcontract | 642300
SC-20102 | 26-127 | 07-200 | Subcontract | 527900
PO-20103 | 26-127 | 08-100 | Material | 305400
SC-20104 | 26-127 | 09-200 | Subcontract | 527200
SC-20105 | 26-127 | 15-000 | Subcontract | 918500
SC-20106 | 26-127 | 16-000 | Subcontract | 698500
SC-20107 | 26-130 | 02-200 | Subcontract | 215500
PO-20108 | 26-130 | 03-200 | Material | 231200
PO-20109 | 26-130 | 03-300 | Material | 354700
SC-20110 | 26-130 | 04-200 | Subcontract | 423200
SC-20111 | 26-130 | 05-100 | Subcontract | 396800
SC-20112 | 26-130 | 07-200 | Subcontract | 320500
SC-20113 | 26-130 | 15-000 | Subcontract | 829600
SC-20114 | 26-130 | 16-000 | Subcontract | 715300

## Data_JobCost
transaction_id | posting_date | fiscal_period | job_no | cost_code | cost_type | source | vendor_id | vendor_name | description | hours | amount
500001 | 2024-06-07 | 202406 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jun 07 | 42.7 | 3925.47
500118 | 2024-06-13 | 202406 | 23-098 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 37896 | 0 | 1683.3
500002 | 2024-06-14 | 202406 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jun 14 | 17.2 | 1582.75
500003 | 2024-06-21 | 202406 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jun 21 | 18.6 | 1706.79
500119 | 2024-06-23 | 202406 | 23-098 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 89358 | 0 | 2175.1
500197 | 2024-06-25 | 202406 | 23-098 | 02-200 | Subcontract | AP | V1001 | Earthwork Subcontractor A | Progress claim Jun 2024 | 0 | 25341.95
500004 | 2024-06-28 | 202406 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jun 28 | 11.4 | 1045.28
500174 | 2024-06-30 | 202406 | 23-098 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 1740.38
500005 | 2024-07-05 | 202407 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jul 05 | 58.9 | 5415.03
500006 | 2024-07-12 | 202407 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jul 12 | 37.5 | 3453.36
500120 | 2024-07-12 | 202407 | 23-098 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 84491 | 0 | 5787.75
500007 | 2024-07-19 | 202407 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jul 19 | 28.6 | 2634.95
500198 | 2024-07-25 | 202407 | 23-098 | 02-200 | Subcontract | AP | V1001 | Earthwork Subcontractor A | Progress claim Jul 2024 | 0 | 66566.23
500008 | 2024-07-26 | 202407 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jul 26 | 21.6 | 1983.68
500175 | 2024-07-31 | 202407 | 23-098 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 5435.61
500009 | 2024-08-02 | 202408 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Aug 02 | 59.7 | 5493.3
500205 | 2024-08-02 | 202408 | 23-098 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Aug 02 | 61.3 | 4537.19
500254 | 2024-08-05 | 202408 | 23-098 | 03-200 | Material | AP | V1002 | Reinforcing Steel Supplier F | Invoice 35883 | 0 | 6320.46
500010 | 2024-08-09 | 202408 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Aug 09 | 37 | 3406.7
500206 | 2024-08-09 | 202408 | 23-098 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Aug 09 | 27.1 | 2007.33
500121 | 2024-08-12 | 202408 | 23-098 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 91022 | 0 | 5301.2
500277 | 2024-08-12 | 202408 | 23-098 | 03-300 | Material | AP | V1003 | Cast-in-Place Concrete Supplier G | Invoice 65475 | 0 | 2733.72
500122 | 2024-08-13 | 202408 | 23-098 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 91750 | 0 | 1967.56
500011 | 2024-08-16 | 202408 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Aug 16 | 35.4 | 3259.93
500207 | 2024-08-16 | 202408 | 23-098 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Aug 16 | 56.4 | 4174.06
500276 | 2024-08-17 | 202408 | 23-098 | 03-300 | Material | AP | V1003 | Cast-in-Place Concrete Supplier G | Invoice 49006 | 0 | 1101.65
500253 | 2024-08-20 | 202408 | 23-098 | 03-200 | Material | AP | V1002 | Reinforcing Steel Supplier F | Invoice 47508 | 0 | 8232.65
500012 | 2024-08-23 | 202408 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Aug 23 | 22 | 2024.46
500208 | 2024-08-23 | 202408 | 23-098 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Aug 23 | 48.8 | 3610.68
500278 | 2024-08-23 | 202408 | 23-098 | 03-300 | Material | AP | V1003 | Cast-in-Place Concrete Supplier G | Invoice 31941 | 0 | 1595.59
500199 | 2024-08-25 | 202408 | 23-098 | 02-200 | Subcontract | AP | V1001 | Earthwork Subcontractor A | Progress claim Aug 2024 | 0 | 115010.44
500013 | 2024-08-30 | 202408 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Aug 30 | 23.6 | 2167.05
500209 | 2024-08-30 | 202408 | 23-098 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Aug 30 | 54.5 | 4036.35
500176 | 2024-08-31 | 202408 | 23-098 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 7256.19
500014 | 2024-09-06 | 202409 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Sep 06 | 71.3 | 6557.49
500123 | 2024-09-06 | 202409 | 23-098 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 65822 | 0 | 1627.06
500125 | 2024-09-06 | 202409 | 23-098 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 81022 | 0 | 4358.07
500210 | 2024-09-06 | 202409 | 23-098 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Sep 06 | 90.2 | 6677.52
500279 | 2024-09-11 | 202409 | 23-098 | 03-300 | Material | AP | V1003 | Cast-in-Place Concrete Supplier G | Invoice 48703 | 0 | 33217
500015 | 2024-09-13 | 202409 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Sep 13 | 39.5 | 3634.33
500211 | 2024-09-13 | 202409 | 23-098 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Sep 13 | 210.1 | 15544.75
500257 | 2024-09-16 | 202409 | 23-098 | 03-200 | Material | AP | V1002 | Reinforcing Steel Supplier F | Invoice 32319 | 0 | 13186.76
500256 | 2024-09-18 | 202409 | 23-098 | 03-200 | Material | AP | V1002 | Reinforcing Steel Supplier F | Invoice 67370 | 0 | 9332.88
500255 | 2024-09-19 | 202409 | 23-098 | 03-200 | Material | AP | V1002 | Reinforcing Steel Supplier F | Invoice 62659 | 0 | 8801.32
500016 | 2024-09-20 | 202409 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Sep 20 | 51.6 | 4748.41
500212 | 2024-09-20 | 202409 | 23-098 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Sep 20 | 50.1 | 3710.36
500124 | 2024-09-22 | 202409 | 23-098 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 79066 | 0 | 1683.9
500200 | 2024-09-25 | 202409 | 23-098 | 02-200 | Subcontract | AP | V1001 | Earthwork Subcontractor A | Progress claim Sep 2024 | 0 | 109163.52
500017 | 2024-09-27 | 202409 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Sep 27 | 38 | 3492.82
500213 | 2024-09-27 | 202409 | 23-098 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Sep 27 | 126.3 | 9344.29
500177 | 2024-09-30 | 202409 | 23-098 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 10384.1
500018 | 2024-10-04 | 202410 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Oct 04 | 60.1 | 5529.25
500214 | 2024-10-04 | 202410 | 23-098 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Oct 04 | 304.3 | 22521.5
500127 | 2024-10-10 | 202410 | 23-098 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 56419 | 0 | 5020.31
500280 | 2024-10-10 | 202410 | 23-098 | 03-300 | Material | AP | V1003 | Cast-in-Place Concrete Supplier G | Invoice 24863 | 0 | 3777.74
500019 | 2024-10-11 | 202410 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Oct 11 | 107.6 | 9903.47
500126 | 2024-10-11 | 202410 | 23-098 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 35780 | 0 | 1419.16
500215 | 2024-10-11 | 202410 | 23-098 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Oct 11 | 120.2 | 8897.82
500128 | 2024-10-16 | 202410 | 23-098 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 69187 | 0 | 2228.98
500020 | 2024-10-18 | 202410 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Oct 18 | 41.3 | 3795.32
500216 | 2024-10-18 | 202410 | 23-098 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Oct 18 | 87.1 | 6446.52
500259 | 2024-10-18 | 202410 | 23-098 | 03-200 | Material | AP | V1002 | Reinforcing Steel Supplier F | Invoice 16632 | 0 | 31161.18
500281 | 2024-10-18 | 202410 | 23-098 | 03-300 | Material | AP | V1003 | Cast-in-Place Concrete Supplier G | Invoice 95263 | 0 | 23510.82
500282 | 2024-10-18 | 202410 | 23-098 | 03-300 | Material | AP | V1003 | Cast-in-Place Concrete Supplier G | Invoice 38340 | 0 | 43760.43
500021 | 2024-10-25 | 202410 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Oct 25 | 76.8 | 7063.92
500201 | 2024-10-25 | 202410 | 23-098 | 02-200 | Subcontract | AP | V1001 | Earthwork Subcontractor A | Progress claim Oct 2024 | 0 | 108653.75
500217 | 2024-10-25 | 202410 | 23-098 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Oct 25 | 293.8 | 21742.29
500260 | 2024-10-26 | 202410 | 23-098 | 03-200 | Material | AP | V1002 | Reinforcing Steel Supplier F | Invoice 17639 | 0 | 18623.46
500258 | 2024-10-27 | 202410 | 23-098 | 03-200 | Material | AP | V1002 | Reinforcing Steel Supplier F | Invoice 30788 | 0 | 8017.75
500178 | 2024-10-31 | 202410 | 23-098 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 10819.93
500022 | 2024-11-01 | 202411 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Nov 01 | 77 | 7083.41
500218 | 2024-11-01 | 202411 | 23-098 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Nov 01 | 276.9 | 20489.99
500129 | 2024-11-07 | 202411 | 23-098 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 45287 | 0 | 11984.09
500023 | 2024-11-08 | 202411 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Nov 08 | 15.8 | 1453.13
500219 | 2024-11-08 | 202411 | 23-098 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Nov 08 | 342.3 | 25330.01
500283 | 2024-11-12 | 202411 | 23-098 | 03-300 | Material | AP | V1003 | Cast-in-Place Concrete Supplier G | Invoice 21448 | 0 | 108997.25
500024 | 2024-11-15 | 202411 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Nov 15 | 25.8 | 2377.58
500220 | 2024-11-15 | 202411 | 23-098 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Nov 15 | 167.3 | 12377.48
500262 | 2024-11-18 | 202411 | 23-098 | 03-200 | Material | AP | V1002 | Reinforcing Steel Supplier F | Invoice 60154 | 0 | 16924.42
500025 | 2024-11-22 | 202411 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Nov 22 | 136.8 | 12583.85
500221 | 2024-11-22 | 202411 | 23-098 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Nov 22 | 64.4 | 4768.27
500261 | 2024-11-22 | 202411 | 23-098 | 03-200 | Material | AP | V1002 | Reinforcing Steel Supplier F | Invoice 71930 | 0 | 48060.77
500202 | 2024-11-25 | 202411 | 23-098 | 02-200 | Subcontract | AP | V1001 | Earthwork Subcontractor A | Progress claim Nov 2024 | 0 | 54392.1
500263 | 2024-11-26 | 202411 | 23-098 | 03-200 | Material | AP | V1002 | Reinforcing Steel Supplier F | Invoice 64238 | 0 | 22203.6
500026 | 2024-11-29 | 202411 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Nov 29 | 62.6 | 5763.26
500222 | 2024-11-29 | 202411 | 23-098 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Nov 29 | 203.1 | 15026.52
500179 | 2024-11-30 | 202411 | 23-098 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 14457.77
500027 | 2024-12-06 | 202412 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Dec 06 | 59.2 | 5448.18
500223 | 2024-12-06 | 202412 | 23-098 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Dec 06 | 273 | 20202.98
500130 | 2024-12-10 | 202412 | 23-098 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 18415 | 0 | 2543.84
500132 | 2024-12-12 | 202412 | 23-098 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 53733 | 0 | 5813.83
500028 | 2024-12-13 | 202412 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Dec 13 | 106.7 | 9815.54
500224 | 2024-12-13 | 202412 | 23-098 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Dec 13 | 205.3 | 15191.91
500265 | 2024-12-17 | 202412 | 23-098 | 03-200 | Material | AP | V1002 | Reinforcing Steel Supplier F | Invoice 53778 | 0 | 47404.8
500285 | 2024-12-18 | 202412 | 23-098 | 03-300 | Material | AP | V1003 | Cast-in-Place Concrete Supplier G | Invoice 50401 | 0 | 50665.31
500029 | 2024-12-20 | 202412 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Dec 20 | 89.3 | 8219.28
500225 | 2024-12-20 | 202412 | 23-098 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Dec 20 | 634.2 | 46930.49
500264 | 2024-12-21 | 202412 | 23-098 | 03-200 | Material | AP | V1002 | Reinforcing Steel Supplier F | Invoice 64492 | 0 | 59197.79
500284 | 2024-12-22 | 202412 | 23-098 | 03-300 | Material | AP | V1003 | Cast-in-Place Concrete Supplier G | Invoice 82883 | 0 | 82705.23
500203 | 2024-12-25 | 202412 | 23-098 | 02-200 | Subcontract | AP | V1001 | Earthwork Subcontractor A | Progress claim Dec 2024 | 0 | 19047.48
500309 | 2024-12-25 | 202412 | 23-098 | 05-100 | Subcontract | AP | V1005 | Structural Steel Subcontractor C | Progress claim Dec 2024 | 0 | 10518.51
500131 | 2024-12-26 | 202412 | 23-098 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 85161 | 0 | 4881.09
500030 | 2024-12-27 | 202412 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Dec 27 | 119.9 | 11027.51
500226 | 2024-12-27 | 202412 | 23-098 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Dec 27 | 241.2 | 17847.24
500180 | 2024-12-31 | 202412 | 23-098 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 20640.96
500031 | 2025-01-03 | 202501 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jan 03 | 90.9 | 8363.22
500227 | 2025-01-03 | 202501 | 23-098 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Jan 03 | 391.1 | 28943.09
500266 | 2025-01-09 | 202501 | 23-098 | 03-200 | Material | AP | V1002 | Reinforcing Steel Supplier F | Invoice 98532 | 0 | 96626.95
500032 | 2025-01-10 | 202501 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jan 10 | 121.2 | 11152.65
500228 | 2025-01-10 | 202501 | 23-098 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Jan 10 | 387.8 | 28697.66
500287 | 2025-01-16 | 202501 | 23-098 | 03-300 | Material | AP | V1003 | Cast-in-Place Concrete Supplier G | Invoice 29766 | 0 | 122313.38
500033 | 2025-01-17 | 202501 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jan 17 | 15.3 | 1406.65
500229 | 2025-01-17 | 202501 | 23-098 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Jan 17 | 256.7 | 18996
500286 | 2025-01-18 | 202501 | 23-098 | 03-300 | Material | AP | V1003 | Cast-in-Place Concrete Supplier G | Invoice 78935 | 0 | 69618.82
500034 | 2025-01-24 | 202501 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jan 24 | 50.1 | 4606.36
500230 | 2025-01-24 | 202501 | 23-098 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Jan 24 | 298.4 | 22083.36
500310 | 2025-01-25 | 202501 | 23-098 | 05-100 | Subcontract | AP | V1005 | Structural Steel Subcontractor C | Progress claim Jan 2025 | 0 | 78996.16
500133 | 2025-01-27 | 202501 | 23-098 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 29631 | 0 | 16228.87
500035 | 2025-01-31 | 202501 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jan 31 | 150.6 | 13852.47
500181 | 2025-01-31 | 202501 | 23-098 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 21469.94
500231 | 2025-01-31 | 202501 | 23-098 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Jan 31 | 207.4 | 15346.58
500135 | 2025-02-06 | 202502 | 23-098 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 14365 | 0 | 3257.35
500036 | 2025-02-07 | 202502 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Feb 07 | 152.8 | 14055.81
500232 | 2025-02-07 | 202502 | 23-098 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Feb 07 | 174.2 | 12891.92
500267 | 2025-02-12 | 202502 | 23-098 | 03-200 | Material | AP | V1002 | Reinforcing Steel Supplier F | Invoice 86434 | 0 | 30439.55
500037 | 2025-02-14 | 202502 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Feb 14 | 132.4 | 12176.69
500233 | 2025-02-14 | 202502 | 23-098 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Feb 14 | 389.8 | 28845.93
500288 | 2025-02-14 | 202502 | 23-098 | 03-300 | Material | AP | V1003 | Cast-in-Place Concrete Supplier G | Invoice 75723 | 0 | 137207.62
500038 | 2025-02-21 | 202502 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Feb 21 | 81.8 | 7527.87
500234 | 2025-02-21 | 202502 | 23-098 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Feb 21 | 196.8 | 14562.06
500311 | 2025-02-25 | 202502 | 23-098 | 05-100 | Subcontract | AP | V1005 | Structural Steel Subcontractor C | Progress claim Feb 2025 | 0 | 107240.9
500410 | 2025-02-25 | 202502 | 23-098 | 15-000 | Subcontract | AP | V1009 | Mechanical Subcontractor B | Progress claim Feb 2025 | 0 | 30630.72
500429 | 2025-02-25 | 202502 | 23-098 | 16-000 | Subcontract | AP | V1010 | Electrical Subcontractor C | Progress claim Feb 2025 | 0 | 19650.13
500134 | 2025-02-26 | 202502 | 23-098 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 52623 | 0 | 14850.73
500268 | 2025-02-26 | 202502 | 23-098 | 03-200 | Material | AP | V1002 | Reinforcing Steel Supplier F | Invoice 59784 | 0 | 29649.99
500039 | 2025-02-28 | 202502 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Feb 28 | 172.9 | 15907.83
500182 | 2025-02-28 | 202502 | 23-098 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 22951.28
500235 | 2025-02-28 | 202502 | 23-098 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Feb 28 | 258.3 | 19117.8
500531 | 2025-03-03 | 202503 | 24-101 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 49303 | 0 | 1619.13
500040 | 2025-03-07 | 202503 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Mar 07 | 247.2 | 22746.42
500236 | 2025-03-07 | 202503 | 23-098 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Mar 07 | 128.5 | 9509.47
500448 | 2025-03-07 | 202503 | 24-101 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Mar 07 | 62.9 | 5783.33
500269 | 2025-03-10 | 202503 | 23-098 | 03-200 | Material | AP | V1002 | Reinforcing Steel Supplier F | Invoice 69683 | 0 | 9574.2
500291 | 2025-03-10 | 202503 | 23-098 | 03-300 | Material | AP | V1003 | Cast-in-Place Concrete Supplier G | Invoice 64395 | 0 | 66959.08
500532 | 2025-03-11 | 202503 | 24-101 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 78442 | 0 | 2666.44
500136 | 2025-03-13 | 202503 | 23-098 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 32941 | 0 | 21369.7
500041 | 2025-03-14 | 202503 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Mar 14 | 272.3 | 25050.31
500237 | 2025-03-14 | 202503 | 23-098 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Mar 14 | 318.7 | 23586.9
500271 | 2025-03-14 | 202503 | 23-098 | 03-200 | Material | AP | V1002 | Reinforcing Steel Supplier F | Invoice 60662 | 0 | 13911.05
500449 | 2025-03-14 | 202503 | 24-101 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Mar 14 | 30 | 2762.2
500270 | 2025-03-15 | 202503 | 23-098 | 03-200 | Material | AP | V1002 | Reinforcing Steel Supplier F | Invoice 41057 | 0 | 32582.46
500290 | 2025-03-15 | 202503 | 23-098 | 03-300 | Material | AP | V1003 | Cast-in-Place Concrete Supplier G | Invoice 50538 | 0 | 44596.93
500289 | 2025-03-17 | 202503 | 23-098 | 03-300 | Material | AP | V1003 | Cast-in-Place Concrete Supplier G | Invoice 59304 | 0 | 31702.41
500042 | 2025-03-21 | 202503 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Mar 21 | 70 | 6436.62
500238 | 2025-03-21 | 202503 | 23-098 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Mar 21 | 178.5 | 13207.27
500450 | 2025-03-21 | 202503 | 24-101 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Mar 21 | 51.6 | 4748.59
500530 | 2025-03-21 | 202503 | 24-101 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 31027 | 0 | 6334.24
500299 | 2025-03-25 | 202503 | 23-098 | 04-200 | Subcontract | AP | V1004 | Masonry Subcontractor A | Progress claim Mar 2025 | 0 | 14616.46
500312 | 2025-03-25 | 202503 | 23-098 | 05-100 | Subcontract | AP | V1005 | Structural Steel Subcontractor C | Progress claim Mar 2025 | 0 | 190578.21
500411 | 2025-03-25 | 202503 | 23-098 | 15-000 | Subcontract | AP | V1009 | Mechanical Subcontractor B | Progress claim Mar 2025 | 0 | 52615.59
500430 | 2025-03-25 | 202503 | 23-098 | 16-000 | Subcontract | AP | V1010 | Electrical Subcontractor C | Progress claim Mar 2025 | 0 | 38467.33
500589 | 2025-03-25 | 202503 | 24-101 | 02-200 | Subcontract | AP | V1011 | Earthwork Subcontractor A | Progress claim Mar 2025 | 0 | 106455.88
500043 | 2025-03-28 | 202503 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Mar 28 | 68.1 | 6268.78
500239 | 2025-03-28 | 202503 | 23-098 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Mar 28 | 218.3 | 16155.15
500451 | 2025-03-28 | 202503 | 24-101 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Mar 28 | 56.2 | 5171.46
500183 | 2025-03-31 | 202503 | 23-098 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 27931.94
500570 | 2025-03-31 | 202503 | 24-101 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 5541.7
500044 | 2025-04-04 | 202504 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Apr 04 | 50.8 | 4673.74
500137 | 2025-04-04 | 202504 | 23-098 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 67468 | 0 | 4208.1
500240 | 2025-04-04 | 202504 | 23-098 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Apr 04 | 196.6 | 14545.53
500318 | 2025-04-04 | 202504 | 23-098 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Apr 04 | 7.5 | 531.11
500452 | 2025-04-04 | 202504 | 24-101 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Apr 04 | 107.9 | 9926.22
500596 | 2025-04-04 | 202504 | 24-101 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Apr 04 | 23.1 | 1710.79
500139 | 2025-04-06 | 202504 | 23-098 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 35517 | 0 | 12302.02
500637 | 2025-04-09 | 202504 | 24-101 | 03-200 | Material | AP | V1012 | Reinforcing Steel Supplier E | Invoice 64485 | 0 | 5136.58
500138 | 2025-04-10 | 202504 | 23-098 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 71373 | 0 | 6763.79
500272 | 2025-04-10 | 202504 | 23-098 | 03-200 | Material | AP | V1002 | Reinforcing Steel Supplier F | Invoice 32213 | 0 | 22861.66
500045 | 2025-04-11 | 202504 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Apr 11 | 313.7 | 28856.5
500241 | 2025-04-11 | 202504 | 23-098 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Apr 11 | 112.7 | 8339.24
500319 | 2025-04-11 | 202504 | 23-098 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Apr 11 | 5.1 | 362.36
500453 | 2025-04-11 | 202504 | 24-101 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Apr 11 | 71.8 | 6601.25
500597 | 2025-04-11 | 202504 | 24-101 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Apr 11 | 22.3 | 1650.24
500292 | 2025-04-12 | 202504 | 23-098 | 03-300 | Material | AP | V1003 | Cast-in-Place Concrete Supplier G | Invoice 26093 | 0 | 81408.87
500636 | 2025-04-12 | 202504 | 24-101 | 03-200 | Material | AP | V1012 | Reinforcing Steel Supplier E | Invoice 10707 | 0 | 2875.71
500046 | 2025-04-18 | 202504 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Apr 18 | 277.3 | 25514.6
500242 | 2025-04-18 | 202504 | 23-098 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Apr 18 | 94.7 | 7011.06
500320 | 2025-04-18 | 202504 | 23-098 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Apr 18 | 11 | 779.18
500454 | 2025-04-18 | 202504 | 24-101 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Apr 18 | 62.1 | 5713.63
500598 | 2025-04-18 | 202504 | 24-101 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Apr 18 | 9.9 | 731.06
500635 | 2025-04-18 | 202504 | 24-101 | 03-200 | Material | AP | V1012 | Reinforcing Steel Supplier E | Invoice 49700 | 0 | 899.26
500047 | 2025-04-25 | 202504 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Apr 25 | 23 | 2112.94
500243 | 2025-04-25 | 202504 | 23-098 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Apr 25 | 201 | 14873.93
500300 | 2025-04-25 | 202504 | 23-098 | 04-200 | Subcontract | AP | V1004 | Masonry Subcontractor A | Progress claim Apr 2025 | 0 | 52210.62
500313 | 2025-04-25 | 202504 | 23-098 | 05-100 | Subcontract | AP | V1005 | Structural Steel Subcontractor C | Progress claim Apr 2025 | 0 | 279254.25
500321 | 2025-04-25 | 202504 | 23-098 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Apr 25 | 5.8 | 411
500412 | 2025-04-25 | 202504 | 23-098 | 15-000 | Subcontract | AP | V1009 | Mechanical Subcontractor B | Progress claim Apr 2025 | 0 | 68343.11
500431 | 2025-04-25 | 202504 | 23-098 | 16-000 | Subcontract | AP | V1010 | Electrical Subcontractor C | Progress claim Apr 2025 | 0 | 40936.79
500455 | 2025-04-25 | 202504 | 24-101 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Apr 25 | 19.5 | 1789.85
500590 | 2025-04-25 | 202504 | 24-101 | 02-200 | Subcontract | AP | V1011 | Earthwork Subcontractor A | Progress claim Apr 2025 | 0 | 304283.39
500599 | 2025-04-25 | 202504 | 24-101 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Apr 25 | 55.6 | 4110.82
500533 | 2025-04-26 | 202504 | 24-101 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 71485 | 0 | 14473.14
500184 | 2025-04-30 | 202504 | 23-098 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 25393.58
500571 | 2025-04-30 | 202504 | 24-101 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 15755.29
500048 | 2025-05-02 | 202505 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e May 02 | 48.5 | 4458.76
500244 | 2025-05-02 | 202505 | 23-098 | 03-100 | Labour | PR |  | Payroll | Payroll w/e May 02 | 44.2 | 3273.06
500322 | 2025-05-02 | 202505 | 23-098 | 06-100 | Labour | PR |  | Payroll | Payroll w/e May 02 | 75.3 | 5349.17
500456 | 2025-05-02 | 202505 | 24-101 | 01-100 | Labour | PR |  | Payroll | Payroll w/e May 02 | 138.6 | 12752.99
500600 | 2025-05-02 | 202505 | 24-101 | 03-100 | Labour | PR |  | Payroll | Payroll w/e May 02 | 160 | 11842.01
500785 | 2025-05-02 | 202505 | 24-104 | 01-100 | Labour | PR |  | Payroll | Payroll w/e May 02 | 30.4 | 2794.15
500860 | 2025-05-03 | 202505 | 24-104 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 43635 | 0 | 4116.98
500295 | 2025-05-04 | 202505 | 23-098 | 03-300 | Material | AP | V1003 | Cast-in-Place Concrete Supplier G | Invoice 17716 | 0 | 27802.63
500049 | 2025-05-09 | 202505 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e May 09 | 126.7 | 11656.48
500245 | 2025-05-09 | 202505 | 23-098 | 03-100 | Labour | PR |  | Payroll | Payroll w/e May 09 | 79.2 | 5863.51
500323 | 2025-05-09 | 202505 | 23-098 | 06-100 | Labour | PR |  | Payroll | Payroll w/e May 09 | 55.8 | 3961.05
500457 | 2025-05-09 | 202505 | 24-101 | 01-100 | Labour | PR |  | Payroll | Payroll w/e May 09 | 115.4 | 10619.5
500601 | 2025-05-09 | 202505 | 24-101 | 03-100 | Labour | PR |  | Payroll | Payroll w/e May 09 | 280.7 | 20770.68
500786 | 2025-05-09 | 202505 | 24-104 | 01-100 | Labour | PR |  | Payroll | Payroll w/e May 09 | 16 | 1471.39
500273 | 2025-05-10 | 202505 | 23-098 | 03-200 | Material | AP | V1002 | Reinforcing Steel Supplier F | Invoice 82294 | 0 | 1407.93
500638 | 2025-05-10 | 202505 | 24-101 | 03-200 | Material | AP | V1012 | Reinforcing Steel Supplier E | Invoice 71716 | 0 | 78141.19
500657 | 2025-05-10 | 202505 | 24-101 | 03-300 | Material | AP | V1013 | Cast-in-Place Concrete Supplier C | Invoice 21409 | 0 | 28404.92
500141 | 2025-05-12 | 202505 | 23-098 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 92594 | 0 | 1575.14
500536 | 2025-05-14 | 202505 | 24-101 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 69653 | 0 | 9121.22
500050 | 2025-05-16 | 202505 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e May 16 | 232.4 | 21376.4
500246 | 2025-05-16 | 202505 | 23-098 | 03-100 | Labour | PR |  | Payroll | Payroll w/e May 16 | 49.8 | 3685.5
500294 | 2025-05-16 | 202505 | 23-098 | 03-300 | Material | AP | V1003 | Cast-in-Place Concrete Supplier G | Invoice 43234 | 0 | 28578.28
500324 | 2025-05-16 | 202505 | 23-098 | 06-100 | Labour | PR |  | Payroll | Payroll w/e May 16 | 50 | 3551.18
500458 | 2025-05-16 | 202505 | 24-101 | 01-100 | Labour | PR |  | Payroll | Payroll w/e May 16 | 8.4 | 776.53
500535 | 2025-05-16 | 202505 | 24-101 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 52135 | 0 | 4445.32
500602 | 2025-05-16 | 202505 | 24-101 | 03-100 | Labour | PR |  | Payroll | Payroll w/e May 16 | 130.4 | 9647.26
500787 | 2025-05-16 | 202505 | 24-104 | 01-100 | Labour | PR |  | Payroll | Payroll w/e May 16 | 17.2 | 1583.15
500859 | 2025-05-16 | 202505 | 24-104 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 81737 | 0 | 1683.18
500274 | 2025-05-21 | 202505 | 23-098 | 03-200 | Material | AP | V1002 | Reinforcing Steel Supplier F | Invoice 99756 | 0 | 2304.37
500051 | 2025-05-23 | 202505 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e May 23 | 149.2 | 13729.74
500140 | 2025-05-23 | 202505 | 23-098 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 60141 | 0 | 21055.13
500247 | 2025-05-23 | 202505 | 23-098 | 03-100 | Labour | PR |  | Payroll | Payroll w/e May 23 | 94.4 | 6986.45
500325 | 2025-05-23 | 202505 | 23-098 | 06-100 | Labour | PR |  | Payroll | Payroll w/e May 23 | 19.2 | 1366.33
500459 | 2025-05-23 | 202505 | 24-101 | 01-100 | Labour | PR |  | Payroll | Payroll w/e May 23 | 56.5 | 5195.84
500603 | 2025-05-23 | 202505 | 24-101 | 03-100 | Labour | PR |  | Payroll | Payroll w/e May 23 | 21.2 | 1569.63
500788 | 2025-05-23 | 202505 | 24-104 | 01-100 | Labour | PR |  | Payroll | Payroll w/e May 23 | 63.1 | 5805.55
500275 | 2025-05-24 | 202505 | 23-098 | 03-200 | Material | AP | V1002 | Reinforcing Steel Supplier F | Invoice 92467 | 0 | 3819.37
500534 | 2025-05-24 | 202505 | 24-101 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 31760 | 0 | 8529.73
500301 | 2025-05-25 | 202505 | 23-098 | 04-200 | Subcontract | AP | V1004 | Masonry Subcontractor A | Progress claim May 2025 | 0 | 95630.42
500314 | 2025-05-25 | 202505 | 23-098 | 05-100 | Subcontract | AP | V1005 | Structural Steel Subcontractor C | Progress claim May 2025 | 0 | 251419.57
500413 | 2025-05-25 | 202505 | 23-098 | 15-000 | Subcontract | AP | V1009 | Mechanical Subcontractor B | Progress claim May 2025 | 0 | 99099.99
500432 | 2025-05-25 | 202505 | 23-098 | 16-000 | Subcontract | AP | V1010 | Electrical Subcontractor C | Progress claim May 2025 | 0 | 66736.56
500591 | 2025-05-25 | 202505 | 24-101 | 02-200 | Subcontract | AP | V1011 | Earthwork Subcontractor A | Progress claim May 2025 | 0 | 550394.13
500659 | 2025-05-25 | 202505 | 24-101 | 03-300 | Material | AP | V1013 | Cast-in-Place Concrete Supplier C | Invoice 44845 | 0 | 4953.62
500911 | 2025-05-25 | 202505 | 24-104 | 02-200 | Subcontract | AP | V1020 | Earthwork Subcontractor E | Progress claim May 2025 | 0 | 43431.51
500658 | 2025-05-26 | 202505 | 24-101 | 03-300 | Material | AP | V1013 | Cast-in-Place Concrete Supplier C | Invoice 97809 | 0 | 10255.39
500293 | 2025-05-27 | 202505 | 23-098 | 03-300 | Material | AP | V1003 | Cast-in-Place Concrete Supplier G | Invoice 46595 | 0 | 5719.41
500052 | 2025-05-30 | 202505 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e May 30 | 125.1 | 11506.63
500248 | 2025-05-30 | 202505 | 23-098 | 03-100 | Labour | PR |  | Payroll | Payroll w/e May 30 | 90.6 | 6703.1
500326 | 2025-05-30 | 202505 | 23-098 | 06-100 | Labour | PR |  | Payroll | Payroll w/e May 30 | 48.6 | 3447.71
500460 | 2025-05-30 | 202505 | 24-101 | 01-100 | Labour | PR |  | Payroll | Payroll w/e May 30 | 64 | 5890.19
500604 | 2025-05-30 | 202505 | 24-101 | 03-100 | Labour | PR |  | Payroll | Payroll w/e May 30 | 157.5 | 11658.08
500789 | 2025-05-30 | 202505 | 24-104 | 01-100 | Labour | PR |  | Payroll | Payroll w/e May 30 | 22.5 | 2071.84
500185 | 2025-05-31 | 202505 | 23-098 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 32641.07
500572 | 2025-05-31 | 202505 | 24-101 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 20118.38
500894 | 2025-05-31 | 202505 | 24-104 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 3063.5
500537 | 2025-06-04 | 202506 | 24-101 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 70016 | 0 | 25660.43
500862 | 2025-06-04 | 202506 | 24-104 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 36196 | 0 | 2258.32
500053 | 2025-06-06 | 202506 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jun 06 | 336.2 | 30932.32
500249 | 2025-06-06 | 202506 | 23-098 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Jun 06 | 5.1 | 376.22
500327 | 2025-06-06 | 202506 | 23-098 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Jun 06 | 54.2 | 3851.04
500461 | 2025-06-06 | 202506 | 24-101 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jun 06 | 63.3 | 5828.05
500605 | 2025-06-06 | 202506 | 24-101 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Jun 06 | 47.6 | 3522.38
500790 | 2025-06-06 | 202506 | 24-104 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jun 06 | 102.7 | 9447.72
500918 | 2025-06-06 | 202506 | 24-104 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Jun 06 | 22.3 | 1647.59
501097 | 2025-06-06 | 202506 | 24-107 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jun 06 | 57.2 | 5260.9
500640 | 2025-06-07 | 202506 | 24-101 | 03-200 | Material | AP | V1012 | Reinforcing Steel Supplier E | Invoice 80422 | 0 | 119860.95
500142 | 2025-06-08 | 202506 | 23-098 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 38482 | 0 | 23940.13
500662 | 2025-06-08 | 202506 | 24-101 | 03-300 | Material | AP | V1013 | Cast-in-Place Concrete Supplier C | Invoice 15516 | 0 | 50677.2
500660 | 2025-06-10 | 202506 | 24-101 | 03-300 | Material | AP | V1013 | Cast-in-Place Concrete Supplier C | Invoice 24600 | 0 | 68754.91
500661 | 2025-06-12 | 202506 | 24-101 | 03-300 | Material | AP | V1013 | Cast-in-Place Concrete Supplier C | Invoice 31136 | 0 | 8033.35
500054 | 2025-06-13 | 202506 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jun 13 | 235.9 | 21705.49
500250 | 2025-06-13 | 202506 | 23-098 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Jun 13 | 15.5 | 1149.4
500328 | 2025-06-13 | 202506 | 23-098 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Jun 13 | 74.8 | 5312.09
500462 | 2025-06-13 | 202506 | 24-101 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jun 13 | 28.7 | 2641.76
500606 | 2025-06-13 | 202506 | 24-101 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Jun 13 | 652.7 | 48297.72
500791 | 2025-06-13 | 202506 | 24-104 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jun 13 | 49.6 | 4567.79
500919 | 2025-06-13 | 202506 | 24-104 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Jun 13 | 8.9 | 656.31
500958 | 2025-06-13 | 202506 | 24-104 | 03-200 | Material | AP | V1021 | Reinforcing Steel Supplier D | Invoice 38376 | 0 | 2217.62
501098 | 2025-06-13 | 202506 | 24-107 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jun 13 | 65 | 5981.28
500957 | 2025-06-15 | 202506 | 24-104 | 03-200 | Material | AP | V1021 | Reinforcing Steel Supplier D | Invoice 28951 | 0 | 548.92
501166 | 2025-06-19 | 202506 | 24-107 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 95649 | 0 | 3983.78
500055 | 2025-06-20 | 202506 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jun 20 | 162.2 | 14924.33
500251 | 2025-06-20 | 202506 | 23-098 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Jun 20 | 5.4 | 400.59
500329 | 2025-06-20 | 202506 | 23-098 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Jun 20 | 199.8 | 14182.81
500463 | 2025-06-20 | 202506 | 24-101 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jun 20 | 192.3 | 17693.92
500607 | 2025-06-20 | 202506 | 24-101 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Jun 20 | 402 | 29751.45
500792 | 2025-06-20 | 202506 | 24-104 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jun 20 | 79.1 | 7274.68
500920 | 2025-06-20 | 202506 | 24-104 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Jun 20 | 18.2 | 1344.68
501099 | 2025-06-20 | 202506 | 24-107 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jun 20 | 39.5 | 3632.89
500863 | 2025-06-21 | 202506 | 24-104 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 53702 | 0 | 4989.41
500959 | 2025-06-21 | 202506 | 24-104 | 03-200 | Material | AP | V1021 | Reinforcing Steel Supplier D | Invoice 99359 | 0 | 849.26
500302 | 2025-06-25 | 202506 | 23-098 | 04-200 | Subcontract | AP | V1004 | Masonry Subcontractor A | Progress claim Jun 2025 | 0 | 135970.33
500315 | 2025-06-25 | 202506 | 23-098 | 05-100 | Subcontract | AP | V1005 | Structural Steel Subcontractor C | Progress claim Jun 2025 | 0 | 151514.49
500370 | 2025-06-25 | 202506 | 23-098 | 07-200 | Subcontract | AP | V1006 | Roofing Subcontractor B | Progress claim Jun 2025 | 0 | 36756.1
500414 | 2025-06-25 | 202506 | 23-098 | 15-000 | Subcontract | AP | V1009 | Mechanical Subcontractor B | Progress claim Jun 2025 | 0 | 116320.29
500433 | 2025-06-25 | 202506 | 23-098 | 16-000 | Subcontract | AP | V1010 | Electrical Subcontractor C | Progress claim Jun 2025 | 0 | 88883.81
500592 | 2025-06-25 | 202506 | 24-101 | 02-200 | Subcontract | AP | V1011 | Earthwork Subcontractor A | Progress claim Jun 2025 | 0 | 392375.18
500861 | 2025-06-25 | 202506 | 24-104 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 36941 | 0 | 1514.08
500912 | 2025-06-25 | 202506 | 24-104 | 02-200 | Subcontract | AP | V1020 | Earthwork Subcontractor E | Progress claim Jun 2025 | 0 | 115200.31
501210 | 2025-06-25 | 202506 | 24-107 | 02-200 | Subcontract | AP | V1030 | Earthwork Subcontractor G | Progress claim Jun 2025 | 0 | 75333.02
500296 | 2025-06-26 | 202506 | 23-098 | 03-300 | Material | AP | V1003 | Cast-in-Place Concrete Supplier G | Invoice 77210 | 0 | 27666.89
500056 | 2025-06-27 | 202506 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jun 27 | 85.8 | 7890.92
500252 | 2025-06-27 | 202506 | 23-098 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Jun 27 | 8 | 590.22
500330 | 2025-06-27 | 202506 | 23-098 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Jun 27 | 154 | 10931.89
500464 | 2025-06-27 | 202506 | 24-101 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jun 27 | 95.8 | 8816.02
500608 | 2025-06-27 | 202506 | 24-101 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Jun 27 | 303.5 | 22458.51
500639 | 2025-06-27 | 202506 | 24-101 | 03-200 | Material | AP | V1012 | Reinforcing Steel Supplier E | Invoice 21509 | 0 | 44920.43
500793 | 2025-06-27 | 202506 | 24-104 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jun 27 | 35.5 | 3268.32
500921 | 2025-06-27 | 202506 | 24-104 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Jun 27 | 18.5 | 1372.56
501100 | 2025-06-27 | 202506 | 24-107 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jun 27 | 19.4 | 1784.91
500186 | 2025-06-30 | 202506 | 23-098 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 33021.59
500573 | 2025-06-30 | 202506 | 24-101 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 29090.86
500895 | 2025-06-30 | 202506 | 24-104 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 7420.41
501195 | 2025-06-30 | 202506 | 24-107 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 3920.06
500145 | 2025-07-03 | 202507 | 23-098 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 91940 | 0 | 11532.82
500057 | 2025-07-04 | 202507 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jul 04 | 184.1 | 16941.46
500331 | 2025-07-04 | 202507 | 23-098 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Jul 04 | 201 | 14272.08
500465 | 2025-07-04 | 202507 | 24-101 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jul 04 | 225.7 | 20768.57
500609 | 2025-07-04 | 202507 | 24-101 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Jul 04 | 1012.9 | 74956.04
500794 | 2025-07-04 | 202507 | 24-104 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jul 04 | 123 | 11313.33
500922 | 2025-07-04 | 202507 | 24-104 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Jul 04 | 233.7 | 17291.69
501101 | 2025-07-04 | 202507 | 24-107 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jul 04 | 83.9 | 7714.35
501215 | 2025-07-04 | 202507 | 24-107 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Jul 04 | 46.9 | 3472.45
500864 | 2025-07-05 | 202507 | 24-104 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 15421 | 0 | 10928.32
500540 | 2025-07-06 | 202507 | 24-101 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 83789 | 0 | 12791.73
501167 | 2025-07-09 | 202507 | 24-107 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 20413 | 0 | 5424.67
500058 | 2025-07-11 | 202507 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jul 11 | 438.5 | 40340.16
500332 | 2025-07-11 | 202507 | 23-098 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Jul 11 | 183.5 | 13026.69
500466 | 2025-07-11 | 202507 | 24-101 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jul 11 | 152.1 | 13991.05
500610 | 2025-07-11 | 202507 | 24-101 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Jul 11 | 1014.4 | 75064.53
500795 | 2025-07-11 | 202507 | 24-104 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jul 11 | 49.8 | 4581.53
500923 | 2025-07-11 | 202507 | 24-104 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Jul 11 | 103.6 | 7663.79
501102 | 2025-07-11 | 202507 | 24-107 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jul 11 | 42.4 | 3898.06
501216 | 2025-07-11 | 202507 | 24-107 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Jul 11 | 62.1 | 4595.09
500144 | 2025-07-12 | 202507 | 23-098 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 43819 | 0 | 2370.97
500641 | 2025-07-12 | 202507 | 24-101 | 03-200 | Material | AP | V1012 | Reinforcing Steel Supplier E | Invoice 93528 | 0 | 100535.31
501260 | 2025-07-13 | 202507 | 24-107 | 03-300 | Material | AP | V1032 | Cast-in-Place Concrete Supplier G | Invoice 92639 | 0 | 3751.55
501246 | 2025-07-14 | 202507 | 24-107 | 03-200 | Material | AP | V1031 | Reinforcing Steel Supplier C | Invoice 78066 | 0 | 5883.47
501247 | 2025-07-15 | 202507 | 24-107 | 03-200 | Material | AP | V1031 | Reinforcing Steel Supplier C | Invoice 19832 | 0 | 4300.98
501262 | 2025-07-15 | 202507 | 24-107 | 03-300 | Material | AP | V1032 | Cast-in-Place Concrete Supplier G | Invoice 68244 | 0 | 2651.37
500960 | 2025-07-17 | 202507 | 24-104 | 03-200 | Material | AP | V1021 | Reinforcing Steel Supplier D | Invoice 97279 | 0 | 36698.26
500059 | 2025-07-18 | 202507 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jul 18 | 74.7 | 6873.96
500333 | 2025-07-18 | 202507 | 23-098 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Jul 18 | 184.5 | 13099.53
500467 | 2025-07-18 | 202507 | 24-101 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jul 18 | 46.2 | 4253.63
500611 | 2025-07-18 | 202507 | 24-101 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Jul 18 | 619.6 | 45850.42
500796 | 2025-07-18 | 202507 | 24-104 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jul 18 | 56.8 | 5226.31
500924 | 2025-07-18 | 202507 | 24-104 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Jul 18 | 194.3 | 14375.74
501103 | 2025-07-18 | 202507 | 24-107 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jul 18 | 46.2 | 4252.99
501217 | 2025-07-18 | 202507 | 24-107 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Jul 18 | 67.4 | 4984.34
500642 | 2025-07-19 | 202507 | 24-101 | 03-200 | Material | AP | V1012 | Reinforcing Steel Supplier E | Invoice 85939 | 0 | 55327.53
500643 | 2025-07-19 | 202507 | 24-101 | 03-200 | Material | AP | V1012 | Reinforcing Steel Supplier E | Invoice 19160 | 0 | 86693.43
500975 | 2025-07-19 | 202507 | 24-104 | 03-300 | Material | AP | V1022 | Cast-in-Place Concrete Supplier F | Invoice 69284 | 0 | 11512.42
500663 | 2025-07-20 | 202507 | 24-101 | 03-300 | Material | AP | V1013 | Cast-in-Place Concrete Supplier C | Invoice 80782 | 0 | 228357.89
501248 | 2025-07-20 | 202507 | 24-107 | 03-200 | Material | AP | V1031 | Reinforcing Steel Supplier C | Invoice 35648 | 0 | 10043.01
500143 | 2025-07-21 | 202507 | 23-098 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 49598 | 0 | 16695.66
500538 | 2025-07-21 | 202507 | 24-101 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 99804 | 0 | 14543.3
500974 | 2025-07-23 | 202507 | 24-104 | 03-300 | Material | AP | V1022 | Cast-in-Place Concrete Supplier F | Invoice 77459 | 0 | 5327.01
500060 | 2025-07-25 | 202507 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jul 25 | 75.7 | 6967.45
500303 | 2025-07-25 | 202507 | 23-098 | 04-200 | Subcontract | AP | V1004 | Masonry Subcontractor A | Progress claim Jul 2025 | 0 | 185265.75
500316 | 2025-07-25 | 202507 | 23-098 | 05-100 | Subcontract | AP | V1005 | Structural Steel Subcontractor C | Progress claim Jul 2025 | 0 | 90221.81
500334 | 2025-07-25 | 202507 | 23-098 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Jul 25 | 186.1 | 13216.39
500371 | 2025-07-25 | 202507 | 23-098 | 07-200 | Subcontract | AP | V1006 | Roofing Subcontractor B | Progress claim Jul 2025 | 0 | 108131.48
500415 | 2025-07-25 | 202507 | 23-098 | 15-000 | Subcontract | AP | V1009 | Mechanical Subcontractor B | Progress claim Jul 2025 | 0 | 170314.44
500434 | 2025-07-25 | 202507 | 23-098 | 16-000 | Subcontract | AP | V1010 | Electrical Subcontractor C | Progress claim Jul 2025 | 0 | 103815.67
500468 | 2025-07-25 | 202507 | 24-101 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jul 25 | 61.9 | 5691.45
500593 | 2025-07-25 | 202507 | 24-101 | 02-200 | Subcontract | AP | V1011 | Earthwork Subcontractor A | Progress claim Jul 2025 | 0 | 208564.48
500612 | 2025-07-25 | 202507 | 24-101 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Jul 25 | 405.6 | 30012.47
500797 | 2025-07-25 | 202507 | 24-104 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jul 25 | 100.2 | 9220.73
500913 | 2025-07-25 | 202507 | 24-104 | 02-200 | Subcontract | AP | V1020 | Earthwork Subcontractor E | Progress claim Jul 2025 | 0 | 175922.38
500925 | 2025-07-25 | 202507 | 24-104 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Jul 25 | 72.4 | 5359.19
501104 | 2025-07-25 | 202507 | 24-107 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jul 25 | 58.9 | 5418.7
501211 | 2025-07-25 | 202507 | 24-107 | 02-200 | Subcontract | AP | V1030 | Earthwork Subcontractor G | Progress claim Jul 2025 | 0 | 210119.41
501218 | 2025-07-25 | 202507 | 24-107 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Jul 25 | 31.6 | 2335.09
500539 | 2025-07-26 | 202507 | 24-101 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 61086 | 0 | 1904.91
500976 | 2025-07-27 | 202507 | 24-104 | 03-300 | Material | AP | V1022 | Cast-in-Place Concrete Supplier F | Invoice 18228 | 0 | 8445.1
501261 | 2025-07-27 | 202507 | 24-107 | 03-300 | Material | AP | V1032 | Cast-in-Place Concrete Supplier G | Invoice 28311 | 0 | 1270.89
500187 | 2025-07-31 | 202507 | 23-098 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 32532.55
500574 | 2025-07-31 | 202507 | 24-101 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 42645.26
500896 | 2025-07-31 | 202507 | 24-104 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 10348.47
501196 | 2025-07-31 | 202507 | 24-107 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 10165.59
500061 | 2025-08-01 | 202508 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Aug 01 | 144 | 13245.93
500335 | 2025-08-01 | 202508 | 23-098 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Aug 01 | 110 | 7810.46
500469 | 2025-08-01 | 202508 | 24-101 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Aug 01 | 142.8 | 13140.82
500613 | 2025-08-01 | 202508 | 24-101 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Aug 01 | 344.3 | 25481.5
500798 | 2025-08-01 | 202508 | 24-104 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Aug 01 | 98.5 | 9060.32
500926 | 2025-08-01 | 202508 | 24-104 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Aug 01 | 330.2 | 24434.36
501105 | 2025-08-01 | 202508 | 24-107 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Aug 01 | 78.3 | 7205.28
501219 | 2025-08-01 | 202508 | 24-107 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Aug 01 | 225.2 | 16663.32
501366 | 2025-08-01 | 202508 | 25-110 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Aug 01 | 43.7 | 4018.45
501250 | 2025-08-03 | 202508 | 24-107 | 03-200 | Material | AP | V1031 | Reinforcing Steel Supplier C | Invoice 39136 | 0 | 44747.98
500865 | 2025-08-04 | 202508 | 24-104 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 69859 | 0 | 7259.13
500062 | 2025-08-08 | 202508 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Aug 08 | 191.9 | 17655.93
500336 | 2025-08-08 | 202508 | 23-098 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Aug 08 | 205.8 | 14614.79
500470 | 2025-08-08 | 202508 | 24-101 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Aug 08 | 168.1 | 15463.21
500614 | 2025-08-08 | 202508 | 24-101 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Aug 08 | 690.7 | 51109.44
500799 | 2025-08-08 | 202508 | 24-104 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Aug 08 | 74.8 | 6879.25
500927 | 2025-08-08 | 202508 | 24-104 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Aug 08 | 259.6 | 19209.23
500978 | 2025-08-08 | 202508 | 24-104 | 03-300 | Material | AP | V1022 | Cast-in-Place Concrete Supplier F | Invoice 89751 | 0 | 4236.58
501106 | 2025-08-08 | 202508 | 24-107 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Aug 08 | 35.1 | 3232.37
501220 | 2025-08-08 | 202508 | 24-107 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Aug 08 | 107 | 7920.43
501367 | 2025-08-08 | 202508 | 25-110 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Aug 08 | 29.5 | 2710.07
500646 | 2025-08-09 | 202508 | 24-101 | 03-200 | Material | AP | V1012 | Reinforcing Steel Supplier E | Invoice 10158 | 0 | 173353.87
500867 | 2025-08-09 | 202508 | 24-104 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 64164 | 0 | 6118.49
500962 | 2025-08-09 | 202508 | 24-104 | 03-200 | Material | AP | V1021 | Reinforcing Steel Supplier D | Invoice 60363 | 0 | 52080.68
500146 | 2025-08-10 | 202508 | 23-098 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 82238 | 0 | 5953.47
501427 | 2025-08-12 | 202508 | 25-110 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 12327 | 0 | 9557.42
500645 | 2025-08-13 | 202508 | 24-101 | 03-200 | Material | AP | V1012 | Reinforcing Steel Supplier E | Invoice 44583 | 0 | 40049.14
500665 | 2025-08-13 | 202508 | 24-101 | 03-300 | Material | AP | V1013 | Cast-in-Place Concrete Supplier C | Invoice 85065 | 0 | 230559.45
501249 | 2025-08-14 | 202508 | 24-107 | 03-200 | Material | AP | V1031 | Reinforcing Steel Supplier C | Invoice 54359 | 0 | 30636.91
500063 | 2025-08-15 | 202508 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Aug 15 | 132.8 | 12219.09
500337 | 2025-08-15 | 202508 | 23-098 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Aug 15 | 402.1 | 28551.58
500471 | 2025-08-15 | 202508 | 24-101 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Aug 15 | 197.4 | 18160.36
500615 | 2025-08-15 | 202508 | 24-101 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Aug 15 | 479.6 | 35493.29
500800 | 2025-08-15 | 202508 | 24-104 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Aug 15 | 74.6 | 6863.47
500928 | 2025-08-15 | 202508 | 24-104 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Aug 15 | 112 | 8290.42
501107 | 2025-08-15 | 202508 | 24-107 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Aug 15 | 58.4 | 5368.63
501221 | 2025-08-15 | 202508 | 24-107 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Aug 15 | 54.5 | 4030.38
501368 | 2025-08-15 | 202508 | 25-110 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Aug 15 | 78.4 | 7212.01
500644 | 2025-08-16 | 202508 | 24-101 | 03-200 | Material | AP | V1012 | Reinforcing Steel Supplier E | Invoice 16296 | 0 | 78712.44
500866 | 2025-08-17 | 202508 | 24-104 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 21061 | 0 | 3145.18
500977 | 2025-08-17 | 202508 | 24-104 | 03-300 | Material | AP | V1022 | Cast-in-Place Concrete Supplier F | Invoice 79323 | 0 | 27905.41
500664 | 2025-08-18 | 202508 | 24-101 | 03-300 | Material | AP | V1013 | Cast-in-Place Concrete Supplier C | Invoice 29207 | 0 | 73956.98
501263 | 2025-08-19 | 202508 | 24-107 | 03-300 | Material | AP | V1032 | Cast-in-Place Concrete Supplier G | Invoice 95538 | 0 | 25962.55
500541 | 2025-08-20 | 202508 | 24-101 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 42745 | 0 | 11475.3
500979 | 2025-08-20 | 202508 | 24-104 | 03-300 | Material | AP | V1022 | Cast-in-Place Concrete Supplier F | Invoice 50818 | 0 | 34237.09
500542 | 2025-08-21 | 202508 | 24-101 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 97037 | 0 | 6180.51
500064 | 2025-08-22 | 202508 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Aug 22 | 184.5 | 16977.01
500338 | 2025-08-22 | 202508 | 23-098 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Aug 22 | 150.6 | 10693.26
500472 | 2025-08-22 | 202508 | 24-101 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Aug 22 | 145.9 | 13425.38
500616 | 2025-08-22 | 202508 | 24-101 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Aug 22 | 604.3 | 44717.52
500801 | 2025-08-22 | 202508 | 24-104 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Aug 22 | 124.5 | 11455.17
500929 | 2025-08-22 | 202508 | 24-104 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Aug 22 | 362.5 | 26822.98
501108 | 2025-08-22 | 202508 | 24-107 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Aug 22 | 80.4 | 7396.66
501222 | 2025-08-22 | 202508 | 24-107 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Aug 22 | 312.1 | 23094.14
501369 | 2025-08-22 | 202508 | 25-110 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Aug 22 | 91 | 8372.59
500543 | 2025-08-23 | 202508 | 24-101 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 82227 | 0 | 20558.14
500961 | 2025-08-23 | 202508 | 24-104 | 03-200 | Material | AP | V1021 | Reinforcing Steel Supplier D | Invoice 48872 | 0 | 22924.1
501168 | 2025-08-24 | 202508 | 24-107 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 16880 | 0 | 8967.82
500147 | 2025-08-25 | 202508 | 23-098 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 36154 | 0 | 5215.8
500148 | 2025-08-25 | 202508 | 23-098 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 30883 | 0 | 16277.17
500304 | 2025-08-25 | 202508 | 23-098 | 04-200 | Subcontract | AP | V1004 | Masonry Subcontractor A | Progress claim Aug 2025 | 0 | 137906.7
500317 | 2025-08-25 | 202508 | 23-098 | 05-100 | Subcontract | AP | V1005 | Structural Steel Subcontractor C | Progress claim Aug 2025 | 0 | 52454.1
500372 | 2025-08-25 | 202508 | 23-098 | 07-200 | Subcontract | AP | V1006 | Roofing Subcontractor B | Progress claim Aug 2025 | 0 | 181430.2
500416 | 2025-08-25 | 202508 | 23-098 | 15-000 | Subcontract | AP | V1009 | Mechanical Subcontractor B | Progress claim Aug 2025 | 0 | 207857.18
500435 | 2025-08-25 | 202508 | 23-098 | 16-000 | Subcontract | AP | V1010 | Electrical Subcontractor C | Progress claim Aug 2025 | 0 | 110337.11
500594 | 2025-08-25 | 202508 | 24-101 | 02-200 | Subcontract | AP | V1011 | Earthwork Subcontractor A | Progress claim Aug 2025 | 0 | 42203.22
500678 | 2025-08-25 | 202508 | 24-101 | 05-100 | Subcontract | AP | V1014 | Structural Steel Subcontractor B | Progress claim Aug 2025 | 0 | 87093.85
500914 | 2025-08-25 | 202508 | 24-104 | 02-200 | Subcontract | AP | V1020 | Earthwork Subcontractor E | Progress claim Aug 2025 | 0 | 137640.33
501212 | 2025-08-25 | 202508 | 24-107 | 02-200 | Subcontract | AP | V1030 | Earthwork Subcontractor G | Progress claim Aug 2025 | 0 | 228677.17
501469 | 2025-08-25 | 202508 | 25-110 | 02-200 | Subcontract | AP | V1039 | Earthwork Subcontractor E | Progress claim Aug 2025 | 0 | 61177.75
501264 | 2025-08-27 | 202508 | 24-107 | 03-300 | Material | AP | V1032 | Cast-in-Place Concrete Supplier G | Invoice 51447 | 0 | 27772.17
500065 | 2025-08-29 | 202508 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Aug 29 | 79.3 | 7294.84
500339 | 2025-08-29 | 202508 | 23-098 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Aug 29 | 186.1 | 13212.49
500473 | 2025-08-29 | 202508 | 24-101 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Aug 29 | 109.8 | 10099.53
500617 | 2025-08-29 | 202508 | 24-101 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Aug 29 | 1239.8 | 91747.22
500802 | 2025-08-29 | 202508 | 24-104 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Aug 29 | 84.6 | 7783.22
500930 | 2025-08-29 | 202508 | 24-104 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Aug 29 | 233.4 | 17271.71
501109 | 2025-08-29 | 202508 | 24-107 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Aug 29 | 68.3 | 6284.66
501223 | 2025-08-29 | 202508 | 24-107 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Aug 29 | 132.5 | 9804.8
501370 | 2025-08-29 | 202508 | 25-110 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Aug 29 | 15.8 | 1457.86
500188 | 2025-08-31 | 202508 | 23-098 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 26957.97
500575 | 2025-08-31 | 202508 | 24-101 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 44588.91
500897 | 2025-08-31 | 202508 | 24-104 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 14265.66
501197 | 2025-08-31 | 202508 | 24-107 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 16131.81
501455 | 2025-08-31 | 202508 | 25-110 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 4156.31
500150 | 2025-09-04 | 202509 | 23-098 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 14554 | 0 | 18214.03
500066 | 2025-09-05 | 202509 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Sep 05 | 301.9 | 27775.03
500340 | 2025-09-05 | 202509 | 23-098 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Sep 05 | 163.8 | 11630.9
500474 | 2025-09-05 | 202509 | 24-101 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Sep 05 | 291.8 | 26843.78
500618 | 2025-09-05 | 202509 | 24-101 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Sep 05 | 651.7 | 48227.18
500803 | 2025-09-05 | 202509 | 24-104 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Sep 05 | 48 | 4413.33
500931 | 2025-09-05 | 202509 | 24-104 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Sep 05 | 557.4 | 41244.12
501110 | 2025-09-05 | 202509 | 24-107 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Sep 05 | 123.2 | 11337.42
501224 | 2025-09-05 | 202509 | 24-107 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Sep 05 | 143.9 | 10650.13
501371 | 2025-09-05 | 202509 | 25-110 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Sep 05 | 128.8 | 11852.39
501475 | 2025-09-05 | 202509 | 25-110 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Sep 05 | 14.1 | 1045.79
501617 | 2025-09-05 | 202509 | 25-112 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Sep 05 | 59.2 | 5444.71
501675 | 2025-09-06 | 202509 | 25-112 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 81551 | 0 | 262.32
501514 | 2025-09-07 | 202509 | 25-110 | 03-200 | Material | AP | V1040 | Reinforcing Steel Supplier B | Invoice 13085 | 0 | 1537.54
501673 | 2025-09-09 | 202509 | 25-112 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 76775 | 0 | 2842.96
500963 | 2025-09-10 | 202509 | 24-104 | 03-200 | Material | AP | V1021 | Reinforcing Steel Supplier D | Invoice 18692 | 0 | 90680.85
500149 | 2025-09-11 | 202509 | 23-098 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 75358 | 0 | 10053.56
500067 | 2025-09-12 | 202509 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Sep 12 | 173.7 | 15981.91
500341 | 2025-09-12 | 202509 | 23-098 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Sep 12 | 80.1 | 5687.35
500475 | 2025-09-12 | 202509 | 24-101 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Sep 12 | 124.2 | 11424.25
500545 | 2025-09-12 | 202509 | 24-101 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 92457 | 0 | 27158.1
500619 | 2025-09-12 | 202509 | 24-101 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Sep 12 | 661.1 | 48921.16
500804 | 2025-09-12 | 202509 | 24-104 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Sep 12 | 169 | 15551.68
500932 | 2025-09-12 | 202509 | 24-104 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Sep 12 | 420.7 | 31134.57
500981 | 2025-09-12 | 202509 | 24-104 | 03-300 | Material | AP | V1022 | Cast-in-Place Concrete Supplier F | Invoice 27652 | 0 | 36085.58
501111 | 2025-09-12 | 202509 | 24-107 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Sep 12 | 186.2 | 17129.09
501225 | 2025-09-12 | 202509 | 24-107 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Sep 12 | 395.4 | 29259.54
501372 | 2025-09-12 | 202509 | 25-110 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Sep 12 | 101.3 | 9321.4
501476 | 2025-09-12 | 202509 | 25-110 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Sep 12 | 18.6 | 1374.14
501618 | 2025-09-12 | 202509 | 25-112 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Sep 12 | 35.4 | 3252.59
500870 | 2025-09-13 | 202509 | 24-104 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 65059 | 0 | 10455.25
501674 | 2025-09-13 | 202509 | 25-112 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 50765 | 0 | 700.71
500648 | 2025-09-14 | 202509 | 24-101 | 03-200 | Material | AP | V1012 | Reinforcing Steel Supplier E | Invoice 67209 | 0 | 63740.71
501265 | 2025-09-15 | 202509 | 24-107 | 03-300 | Material | AP | V1032 | Cast-in-Place Concrete Supplier G | Invoice 82259 | 0 | 114878.45
501251 | 2025-09-16 | 202509 | 24-107 | 03-200 | Material | AP | V1031 | Reinforcing Steel Supplier C | Invoice 12880 | 0 | 50491.13
501252 | 2025-09-16 | 202509 | 24-107 | 03-200 | Material | AP | V1031 | Reinforcing Steel Supplier C | Invoice 21566 | 0 | 59196.51
500068 | 2025-09-19 | 202509 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Sep 19 | 84.6 | 7781.62
500342 | 2025-09-19 | 202509 | 23-098 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Sep 19 | 571.2 | 40556.68
500476 | 2025-09-19 | 202509 | 24-101 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Sep 19 | 215.9 | 19861.96
500544 | 2025-09-19 | 202509 | 24-101 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 37093 | 0 | 18142.27
500620 | 2025-09-19 | 202509 | 24-101 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Sep 19 | 524 | 38776.48
500666 | 2025-09-19 | 202509 | 24-101 | 03-300 | Material | AP | V1013 | Cast-in-Place Concrete Supplier C | Invoice 24914 | 0 | 247140.2
500805 | 2025-09-19 | 202509 | 24-104 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Sep 19 | 221.9 | 20415.5
500933 | 2025-09-19 | 202509 | 24-104 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Sep 19 | 304.6 | 22538.15
501112 | 2025-09-19 | 202509 | 24-107 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Sep 19 | 126 | 11591.44
501169 | 2025-09-19 | 202509 | 24-107 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 82618 | 0 | 11416.81
501226 | 2025-09-19 | 202509 | 24-107 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Sep 19 | 339.6 | 25133.31
501373 | 2025-09-19 | 202509 | 25-110 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Sep 19 | 57 | 5248.08
501477 | 2025-09-19 | 202509 | 25-110 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Sep 19 | 18.9 | 1402.07
501619 | 2025-09-19 | 202509 | 25-112 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Sep 19 | 19.7 | 1815.95
500647 | 2025-09-20 | 202509 | 24-101 | 03-200 | Material | AP | V1012 | Reinforcing Steel Supplier E | Invoice 16037 | 0 | 68627.67
500868 | 2025-09-21 | 202509 | 24-104 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 34838 | 0 | 4533.36
500982 | 2025-09-22 | 202509 | 24-104 | 03-300 | Material | AP | V1022 | Cast-in-Place Concrete Supplier F | Invoice 86868 | 0 | 14866.02
500649 | 2025-09-23 | 202509 | 24-101 | 03-200 | Material | AP | V1012 | Reinforcing Steel Supplier E | Invoice 23075 | 0 | 87770.6
500305 | 2025-09-25 | 202509 | 23-098 | 04-200 | Subcontract | AP | V1004 | Masonry Subcontractor A | Progress claim Sep 2025 | 0 | 106667.82
500373 | 2025-09-25 | 202509 | 23-098 | 07-200 | Subcontract | AP | V1006 | Roofing Subcontractor B | Progress claim Sep 2025 | 0 | 207931.16
500417 | 2025-09-25 | 202509 | 23-098 | 15-000 | Subcontract | AP | V1009 | Mechanical Subcontractor B | Progress claim Sep 2025 | 0 | 201822.29
500436 | 2025-09-25 | 202509 | 23-098 | 16-000 | Subcontract | AP | V1010 | Electrical Subcontractor C | Progress claim Sep 2025 | 0 | 154846.34
500667 | 2025-09-25 | 202509 | 24-101 | 03-300 | Material | AP | V1013 | Cast-in-Place Concrete Supplier C | Invoice 63995 | 0 | 58267.69
500679 | 2025-09-25 | 202509 | 24-101 | 05-100 | Subcontract | AP | V1014 | Structural Steel Subcontractor B | Progress claim Sep 2025 | 0 | 326528.1
500759 | 2025-09-25 | 202509 | 24-101 | 15-000 | Subcontract | AP | V1018 | Mechanical Subcontractor F | Progress claim Sep 2025 | 0 | 21449.52
500772 | 2025-09-25 | 202509 | 24-101 | 16-000 | Subcontract | AP | V1019 | Electrical Subcontractor G | Progress claim Sep 2025 | 0 | 27546.09
500915 | 2025-09-25 | 202509 | 24-104 | 02-200 | Subcontract | AP | V1020 | Earthwork Subcontractor E | Progress claim Sep 2025 | 0 | 66875.98
501213 | 2025-09-25 | 202509 | 24-107 | 02-200 | Subcontract | AP | V1030 | Earthwork Subcontractor G | Progress claim Sep 2025 | 0 | 109685.75
501470 | 2025-09-25 | 202509 | 25-110 | 02-200 | Subcontract | AP | V1039 | Earthwork Subcontractor E | Progress claim Sep 2025 | 0 | 172180.24
501720 | 2025-09-25 | 202509 | 25-112 | 02-200 | Subcontract | AP | V1049 | Earthwork Subcontractor D | Progress claim Sep 2025 | 0 | 24886.79
500069 | 2025-09-26 | 202509 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Sep 26 | 215.7 | 19845.01
500343 | 2025-09-26 | 202509 | 23-098 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Sep 26 | 226.6 | 16090.02
500477 | 2025-09-26 | 202509 | 24-101 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Sep 26 | 119.8 | 11020.01
500621 | 2025-09-26 | 202509 | 24-101 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Sep 26 | 1680.7 | 124371.52
500806 | 2025-09-26 | 202509 | 24-104 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Sep 26 | 97.3 | 8953.3
500869 | 2025-09-26 | 202509 | 24-104 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 21241 | 0 | 3507.08
500934 | 2025-09-26 | 202509 | 24-104 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Sep 26 | 560.4 | 41473.23
501113 | 2025-09-26 | 202509 | 24-107 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Sep 26 | 46.1 | 4244.98
501227 | 2025-09-26 | 202509 | 24-107 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Sep 26 | 489.8 | 36246.66
501374 | 2025-09-26 | 202509 | 25-110 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Sep 26 | 66.1 | 6084.62
501478 | 2025-09-26 | 202509 | 25-110 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Sep 26 | 17.9 | 1326.32
501620 | 2025-09-26 | 202509 | 25-112 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Sep 26 | 20.2 | 1862.91
500980 | 2025-09-27 | 202509 | 24-104 | 03-300 | Material | AP | V1022 | Cast-in-Place Concrete Supplier F | Invoice 80931 | 0 | 55468.42
501253 | 2025-09-27 | 202509 | 24-107 | 03-200 | Material | AP | V1031 | Reinforcing Steel Supplier C | Invoice 59571 | 0 | 38374.88
501428 | 2025-09-27 | 202509 | 25-110 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 36381 | 0 | 13260.86
501515 | 2025-09-27 | 202509 | 25-110 | 03-200 | Material | AP | V1040 | Reinforcing Steel Supplier B | Invoice 58608 | 0 | 2250.58
500189 | 2025-09-30 | 202509 | 23-098 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 21372.98
500576 | 2025-09-30 | 202509 | 24-101 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 56925.8
500898 | 2025-09-30 | 202509 | 24-104 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 20424.5
501198 | 2025-09-30 | 202509 | 24-107 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 22277.11
501456 | 2025-09-30 | 202509 | 25-110 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 11240.28
501707 | 2025-09-30 | 202509 | 25-112 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 2984.73
500070 | 2025-10-03 | 202510 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Oct 03 | 111 | 10213.13
500344 | 2025-10-03 | 202510 | 23-098 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Oct 03 | 288.5 | 20486.88
500478 | 2025-10-03 | 202510 | 24-101 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Oct 03 | 189.8 | 17458.69
500547 | 2025-10-03 | 202510 | 24-101 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 93636 | 0 | 21260.11
500622 | 2025-10-03 | 202510 | 24-101 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Oct 03 | 422.9 | 31298.24
500807 | 2025-10-03 | 202510 | 24-104 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Oct 03 | 142.7 | 13129.81
500935 | 2025-10-03 | 202510 | 24-104 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Oct 03 | 266.2 | 19701.22
501114 | 2025-10-03 | 202510 | 24-107 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Oct 03 | 198.7 | 18284.75
501228 | 2025-10-03 | 202510 | 24-107 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Oct 03 | 242 | 17911.37
501266 | 2025-10-03 | 202510 | 24-107 | 03-300 | Material | AP | V1032 | Cast-in-Place Concrete Supplier G | Invoice 54740 | 0 | 142022.49
501375 | 2025-10-03 | 202510 | 25-110 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Oct 03 | 105.6 | 9718.03
501479 | 2025-10-03 | 202510 | 25-110 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Oct 03 | 332.9 | 24631.42
501621 | 2025-10-03 | 202510 | 25-112 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Oct 03 | 85.5 | 7861.59
501725 | 2025-10-03 | 202510 | 25-112 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Oct 03 | 27 | 1994.98
501855 | 2025-10-03 | 202510 | 25-115 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Oct 03 | 49.8 | 4582.25
501431 | 2025-10-05 | 202510 | 25-110 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 93227 | 0 | 13968.44
500668 | 2025-10-06 | 202510 | 24-101 | 03-300 | Material | AP | V1013 | Cast-in-Place Concrete Supplier C | Invoice 78546 | 0 | 178206.44
501254 | 2025-10-06 | 202510 | 24-107 | 03-200 | Material | AP | V1031 | Reinforcing Steel Supplier C | Invoice 83769 | 0 | 96345.19
500548 | 2025-10-07 | 202510 | 24-101 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 37812 | 0 | 33038.61
500964 | 2025-10-08 | 202510 | 24-104 | 03-200 | Material | AP | V1021 | Reinforcing Steel Supplier D | Invoice 24593 | 0 | 37887.9
500546 | 2025-10-09 | 202510 | 24-101 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 99841 | 0 | 9728.21
500071 | 2025-10-10 | 202510 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Oct 10 | 153.1 | 14089.13
500151 | 2025-10-10 | 202510 | 23-098 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 23110 | 0 | 26995.29
500345 | 2025-10-10 | 202510 | 23-098 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Oct 10 | 361.2 | 25641.93
500479 | 2025-10-10 | 202510 | 24-101 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Oct 10 | 213.1 | 19601.5
500623 | 2025-10-10 | 202510 | 24-101 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Oct 10 | 403.3 | 29845.9
500808 | 2025-10-10 | 202510 | 24-104 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Oct 10 | 117.1 | 10772.93
500936 | 2025-10-10 | 202510 | 24-104 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Oct 10 | 740.1 | 54768.68
501115 | 2025-10-10 | 202510 | 24-107 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Oct 10 | 111.5 | 10262.48
501229 | 2025-10-10 | 202510 | 24-107 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Oct 10 | 342.7 | 25357.15
501376 | 2025-10-10 | 202510 | 25-110 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Oct 10 | 131.5 | 12100.56
501480 | 2025-10-10 | 202510 | 25-110 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Oct 10 | 80.6 | 5967.78
501622 | 2025-10-10 | 202510 | 25-112 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Oct 10 | 53 | 4876.37
501726 | 2025-10-10 | 202510 | 25-112 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Oct 10 | 31.6 | 2340.46
501856 | 2025-10-10 | 202510 | 25-115 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Oct 10 | 35.2 | 3239.14
500983 | 2025-10-11 | 202510 | 24-104 | 03-300 | Material | AP | V1022 | Cast-in-Place Concrete Supplier F | Invoice 61087 | 0 | 122887.65
501255 | 2025-10-11 | 202510 | 24-107 | 03-200 | Material | AP | V1031 | Reinforcing Steel Supplier C | Invoice 65811 | 0 | 72054.61
500380 | 2025-10-13 | 202510 | 23-098 | 08-100 | Material | AP | V1007 | Doors Supplier G | Invoice 22959 | 0 | 4602.8
501908 | 2025-10-13 | 202510 | 25-115 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 62235 | 0 | 3608.86
501677 | 2025-10-14 | 202510 | 25-112 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 33726 | 0 | 1928.91
501751 | 2025-10-14 | 202510 | 25-112 | 03-200 | Material | AP | V1050 | Reinforcing Steel Supplier A | Invoice 64206 | 0 | 11380.83
501170 | 2025-10-15 | 202510 | 24-107 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 87932 | 0 | 15600.7
501517 | 2025-10-15 | 202510 | 25-110 | 03-200 | Material | AP | V1040 | Reinforcing Steel Supplier B | Invoice 87801 | 0 | 3880.26
501534 | 2025-10-15 | 202510 | 25-110 | 03-300 | Material | AP | V1041 | Cast-in-Place Concrete Supplier A | Invoice 15943 | 0 | 49238.69
501676 | 2025-10-16 | 202510 | 25-112 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 64474 | 0 | 5295.35
500072 | 2025-10-17 | 202510 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Oct 17 | 101.5 | 9337.92
500346 | 2025-10-17 | 202510 | 23-098 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Oct 17 | 215.1 | 15268.89
500480 | 2025-10-17 | 202510 | 24-101 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Oct 17 | 116.9 | 10755.92
500624 | 2025-10-17 | 202510 | 24-101 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Oct 17 | 560.6 | 41486.88
500809 | 2025-10-17 | 202510 | 24-104 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Oct 17 | 162.9 | 14987.9
500937 | 2025-10-17 | 202510 | 24-104 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Oct 17 | 333.6 | 24689.48
500965 | 2025-10-17 | 202510 | 24-104 | 03-200 | Material | AP | V1021 | Reinforcing Steel Supplier D | Invoice 64417 | 0 | 62140.27
501116 | 2025-10-17 | 202510 | 24-107 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Oct 17 | 89.5 | 8237.5
501230 | 2025-10-17 | 202510 | 24-107 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Oct 17 | 448.5 | 33186.54
501377 | 2025-10-17 | 202510 | 25-110 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Oct 17 | 120 | 11036.6
501430 | 2025-10-17 | 202510 | 25-110 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 54373 | 0 | 4105.35
501481 | 2025-10-17 | 202510 | 25-110 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Oct 17 | 51.4 | 3800.45
501623 | 2025-10-17 | 202510 | 25-112 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Oct 17 | 21.9 | 2011.14
501727 | 2025-10-17 | 202510 | 25-112 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Oct 17 | 32.7 | 2420.23
501857 | 2025-10-17 | 202510 | 25-115 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Oct 17 | 16.2 | 1487.14
500650 | 2025-10-18 | 202510 | 24-101 | 03-200 | Material | AP | V1012 | Reinforcing Steel Supplier E | Invoice 64640 | 0 | 21373.54
500871 | 2025-10-18 | 202510 | 24-104 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 84557 | 0 | 26270.11
500984 | 2025-10-18 | 202510 | 24-104 | 03-300 | Material | AP | V1022 | Cast-in-Place Concrete Supplier F | Invoice 73782 | 0 | 24156.9
501429 | 2025-10-18 | 202510 | 25-110 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 74360 | 0 | 2252.05
501516 | 2025-10-18 | 202510 | 25-110 | 03-200 | Material | AP | V1040 | Reinforcing Steel Supplier B | Invoice 98320 | 0 | 19236.09
500378 | 2025-10-19 | 202510 | 23-098 | 08-100 | Material | AP | V1007 | Doors Supplier G | Invoice 63779 | 0 | 12493.91
500669 | 2025-10-19 | 202510 | 24-101 | 03-300 | Material | AP | V1013 | Cast-in-Place Concrete Supplier C | Invoice 24533 | 0 | 66676.4
501907 | 2025-10-20 | 202510 | 25-115 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 12494 | 0 | 1311.7
500379 | 2025-10-21 | 202510 | 23-098 | 08-100 | Material | AP | V1007 | Doors Supplier G | Invoice 21713 | 0 | 9975.11
500985 | 2025-10-23 | 202510 | 24-104 | 03-300 | Material | AP | V1022 | Cast-in-Place Concrete Supplier F | Invoice 96712 | 0 | 35857.49
501766 | 2025-10-23 | 202510 | 25-112 | 03-300 | Material | AP | V1051 | Cast-in-Place Concrete Supplier F | Invoice 40685 | 0 | 7602.09
500073 | 2025-10-24 | 202510 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Oct 24 | 163.4 | 15029.21
500347 | 2025-10-24 | 202510 | 23-098 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Oct 24 | 91.3 | 6481.04
500481 | 2025-10-24 | 202510 | 24-101 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Oct 24 | 282.4 | 25985.32
500625 | 2025-10-24 | 202510 | 24-101 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Oct 24 | 568 | 42032.98
500810 | 2025-10-24 | 202510 | 24-104 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Oct 24 | 51.7 | 4760.8
500938 | 2025-10-24 | 202510 | 24-104 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Oct 24 | 750.4 | 55529.25
501117 | 2025-10-24 | 202510 | 24-107 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Oct 24 | 167.3 | 15387.49
501231 | 2025-10-24 | 202510 | 24-107 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Oct 24 | 429.9 | 31813.57
501378 | 2025-10-24 | 202510 | 25-110 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Oct 24 | 40.2 | 3701.04
501482 | 2025-10-24 | 202510 | 25-110 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Oct 24 | 198.7 | 14701.6
501518 | 2025-10-24 | 202510 | 25-110 | 03-200 | Material | AP | V1040 | Reinforcing Steel Supplier B | Invoice 88882 | 0 | 17067.65
501624 | 2025-10-24 | 202510 | 25-112 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Oct 24 | 52.9 | 4863.83
501728 | 2025-10-24 | 202510 | 25-112 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Oct 24 | 58.1 | 4300.81
501858 | 2025-10-24 | 202510 | 25-115 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Oct 24 | 23.9 | 2195.81
500306 | 2025-10-25 | 202510 | 23-098 | 04-200 | Subcontract | AP | V1004 | Masonry Subcontractor A | Progress claim Oct 2025 | 0 | 48816.9
500374 | 2025-10-25 | 202510 | 23-098 | 07-200 | Subcontract | AP | V1006 | Roofing Subcontractor B | Progress claim Oct 2025 | 0 | 192686.8
500400 | 2025-10-25 | 202510 | 23-098 | 09-200 | Subcontract | AP | V1008 | Drywall Subcontractor B | Progress claim Oct 2025 | 0 | 30955.46
500418 | 2025-10-25 | 202510 | 23-098 | 15-000 | Subcontract | AP | V1009 | Mechanical Subcontractor B | Progress claim Oct 2025 | 0 | 263740.63
500437 | 2025-10-25 | 202510 | 23-098 | 16-000 | Subcontract | AP | V1010 | Electrical Subcontractor C | Progress claim Oct 2025 | 0 | 154874.73
500651 | 2025-10-25 | 202510 | 24-101 | 03-200 | Material | AP | V1012 | Reinforcing Steel Supplier E | Invoice 22885 | 0 | 124955.32
500680 | 2025-10-25 | 202510 | 24-101 | 05-100 | Subcontract | AP | V1014 | Structural Steel Subcontractor B | Progress claim Oct 2025 | 0 | 650736.98
500760 | 2025-10-25 | 202510 | 24-101 | 15-000 | Subcontract | AP | V1018 | Mechanical Subcontractor F | Progress claim Oct 2025 | 0 | 65028.05
500773 | 2025-10-25 | 202510 | 24-101 | 16-000 | Subcontract | AP | V1019 | Electrical Subcontractor G | Progress claim Oct 2025 | 0 | 84663.15
500916 | 2025-10-25 | 202510 | 24-104 | 02-200 | Subcontract | AP | V1020 | Earthwork Subcontractor E | Progress claim Oct 2025 | 0 | 10203.49
501006 | 2025-10-25 | 202510 | 24-104 | 05-100 | Subcontract | AP | V1024 | Structural Steel Subcontractor A | Progress claim Oct 2025 | 0 | 42859.23
501214 | 2025-10-25 | 202510 | 24-107 | 02-200 | Subcontract | AP | V1030 | Earthwork Subcontractor G | Progress claim Oct 2025 | 0 | 11127.24
501277 | 2025-10-25 | 202510 | 24-107 | 05-100 | Subcontract | AP | V1033 | Structural Steel Subcontractor D | Progress claim Oct 2025 | 0 | 61625.33
501471 | 2025-10-25 | 202510 | 25-110 | 02-200 | Subcontract | AP | V1039 | Earthwork Subcontractor E | Progress claim Oct 2025 | 0 | 327842.99
501721 | 2025-10-25 | 202510 | 25-112 | 02-200 | Subcontract | AP | V1049 | Earthwork Subcontractor D | Progress claim Oct 2025 | 0 | 112224.85
501945 | 2025-10-25 | 202510 | 25-115 | 02-200 | Subcontract | AP | V1059 | Earthwork Subcontractor B | Progress claim Oct 2025 | 0 | 31884.29
500966 | 2025-10-26 | 202510 | 24-104 | 03-200 | Material | AP | V1021 | Reinforcing Steel Supplier D | Invoice 39202 | 0 | 36974.5
501267 | 2025-10-27 | 202510 | 24-107 | 03-300 | Material | AP | V1032 | Cast-in-Place Concrete Supplier G | Invoice 35199 | 0 | 39448.4
500074 | 2025-10-31 | 202510 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Oct 31 | 101.4 | 9325.37
500190 | 2025-10-31 | 202510 | 23-098 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 20715.19
500348 | 2025-10-31 | 202510 | 23-098 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Oct 31 | 329.2 | 23373.26
500482 | 2025-10-31 | 202510 | 24-101 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Oct 31 | 292.1 | 26871.49
500577 | 2025-10-31 | 202510 | 24-101 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 70503.69
500626 | 2025-10-31 | 202510 | 24-101 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Oct 31 | 253.2 | 18738.08
500811 | 2025-10-31 | 202510 | 24-104 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Oct 31 | 172.2 | 15840.43
500899 | 2025-10-31 | 202510 | 24-104 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 26001.88
500939 | 2025-10-31 | 202510 | 24-104 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Oct 31 | 392.9 | 29075.5
501118 | 2025-10-31 | 202510 | 24-107 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Oct 31 | 131.9 | 12134.81
501199 | 2025-10-31 | 202510 | 24-107 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 28996.65
501232 | 2025-10-31 | 202510 | 24-107 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Oct 31 | 490.5 | 36295.04
501379 | 2025-10-31 | 202510 | 25-110 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Oct 31 | 94.6 | 8706.44
501457 | 2025-10-31 | 202510 | 25-110 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 14603.86
501483 | 2025-10-31 | 202510 | 25-110 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Oct 31 | 196.3 | 14522.57
501625 | 2025-10-31 | 202510 | 25-112 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Oct 31 | 31.8 | 2921.41
501708 | 2025-10-31 | 202510 | 25-112 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 9075.1
501729 | 2025-10-31 | 202510 | 25-112 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Oct 31 | 26.3 | 1949.32
501859 | 2025-10-31 | 202510 | 25-115 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Oct 31 | 38.4 | 3530.8
501933 | 2025-10-31 | 202510 | 25-115 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 2993.64
501767 | 2025-11-03 | 202511 | 25-112 | 03-300 | Material | AP | V1051 | Cast-in-Place Concrete Supplier F | Invoice 56743 | 0 | 5384.38
501909 | 2025-11-04 | 202511 | 25-115 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 22960 | 0 | 2806.74
501984 | 2025-11-05 | 202511 | 25-115 | 03-200 | Material | AP | V1060 | Reinforcing Steel Supplier B | Invoice 16860 | 0 | 9525.06
500873 | 2025-11-06 | 202511 | 24-104 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 36065 | 0 | 12175.15
501268 | 2025-11-06 | 202511 | 24-107 | 03-300 | Material | AP | V1032 | Cast-in-Place Concrete Supplier G | Invoice 74331 | 0 | 140110.42
501434 | 2025-11-06 | 202511 | 25-110 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 80432 | 0 | 11864.61
500075 | 2025-11-07 | 202511 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Nov 07 | 185.1 | 17032.93
500349 | 2025-11-07 | 202511 | 23-098 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Nov 07 | 410.5 | 29143.34
500483 | 2025-11-07 | 202511 | 24-101 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Nov 07 | 136 | 12513.77
500627 | 2025-11-07 | 202511 | 24-101 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Nov 07 | 125.3 | 9269.89
500685 | 2025-11-07 | 202511 | 24-101 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Nov 07 | 8.2 | 584.71
500812 | 2025-11-07 | 202511 | 24-104 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Nov 07 | 176.2 | 16207.14
500872 | 2025-11-07 | 202511 | 24-104 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 94032 | 0 | 17869.73
500940 | 2025-11-07 | 202511 | 24-104 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Nov 07 | 865.8 | 64068.27
500967 | 2025-11-07 | 202511 | 24-104 | 03-200 | Material | AP | V1021 | Reinforcing Steel Supplier D | Invoice 45967 | 0 | 81696.82
501119 | 2025-11-07 | 202511 | 24-107 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Nov 07 | 211.8 | 19486.71
501171 | 2025-11-07 | 202511 | 24-107 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 44339 | 0 | 9926.44
501233 | 2025-11-07 | 202511 | 24-107 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Nov 07 | 138.9 | 10277.92
501380 | 2025-11-07 | 202511 | 25-110 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Nov 07 | 102 | 9379.78
501484 | 2025-11-07 | 202511 | 25-110 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Nov 07 | 640.5 | 47393.86
501626 | 2025-11-07 | 202511 | 25-112 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Nov 07 | 72.8 | 6700.19
501730 | 2025-11-07 | 202511 | 25-112 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Nov 07 | 206.1 | 15251.43
501860 | 2025-11-07 | 202511 | 25-115 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Nov 07 | 63.7 | 5856.94
501950 | 2025-11-07 | 202511 | 25-115 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Nov 07 | 78.5 | 5810.36
502076 | 2025-11-07 | 202511 | 25-118 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Nov 07 | 75.4 | 6936.59
500549 | 2025-11-09 | 202511 | 24-101 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 97316 | 0 | 38637.06
500672 | 2025-11-09 | 202511 | 24-101 | 03-300 | Material | AP | V1013 | Cast-in-Place Concrete Supplier C | Invoice 78926 | 0 | 58789.18
500154 | 2025-11-10 | 202511 | 23-098 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 88056 | 0 | 8169.81
500670 | 2025-11-10 | 202511 | 24-101 | 03-300 | Material | AP | V1013 | Cast-in-Place Concrete Supplier C | Invoice 10209 | 0 | 59026.31
501678 | 2025-11-11 | 202511 | 25-112 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 29208 | 0 | 1850.13
500381 | 2025-11-12 | 202511 | 23-098 | 08-100 | Material | AP | V1007 | Doors Supplier G | Invoice 68364 | 0 | 11966.19
500382 | 2025-11-12 | 202511 | 23-098 | 08-100 | Material | AP | V1007 | Doors Supplier G | Invoice 23684 | 0 | 45188.92
501999 | 2025-11-12 | 202511 | 25-115 | 03-300 | Material | AP | V1061 | Cast-in-Place Concrete Supplier A | Invoice 64811 | 0 | 1169.97
501679 | 2025-11-13 | 202511 | 25-112 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 61507 | 0 | 2780.51
501911 | 2025-11-13 | 202511 | 25-115 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 82738 | 0 | 1663
500076 | 2025-11-14 | 202511 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Nov 14 | 66 | 6069.24
500350 | 2025-11-14 | 202511 | 23-098 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Nov 14 | 168.5 | 11962.34
500484 | 2025-11-14 | 202511 | 24-101 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Nov 14 | 404.4 | 37203.39
500628 | 2025-11-14 | 202511 | 24-101 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Nov 14 | 407.5 | 30152.72
500686 | 2025-11-14 | 202511 | 24-101 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Nov 14 | 11.7 | 833.26
500813 | 2025-11-14 | 202511 | 24-104 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Nov 14 | 167.1 | 15370.78
500941 | 2025-11-14 | 202511 | 24-104 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Nov 14 | 1080.8 | 79980.61
501120 | 2025-11-14 | 202511 | 24-107 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Nov 14 | 312.7 | 28765.8
501234 | 2025-11-14 | 202511 | 24-107 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Nov 14 | 613.4 | 45391.85
501381 | 2025-11-14 | 202511 | 25-110 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Nov 14 | 218.9 | 20138.49
501485 | 2025-11-14 | 202511 | 25-110 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Nov 14 | 159.6 | 11810.41
501627 | 2025-11-14 | 202511 | 25-112 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Nov 14 | 93.4 | 8595.15
501731 | 2025-11-14 | 202511 | 25-112 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Nov 14 | 252 | 18651.57
501861 | 2025-11-14 | 202511 | 25-115 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Nov 14 | 46.2 | 4247.58
501951 | 2025-11-14 | 202511 | 25-115 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Nov 14 | 105.6 | 7817.65
502077 | 2025-11-14 | 202511 | 25-118 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Nov 14 | 69.4 | 6389.27
500153 | 2025-11-15 | 202511 | 23-098 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 78088 | 0 | 5741.04
501433 | 2025-11-15 | 202511 | 25-110 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 61821 | 0 | 11778.01
501432 | 2025-11-16 | 202511 | 25-110 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 78134 | 0 | 2379.29
501753 | 2025-11-16 | 202511 | 25-112 | 03-200 | Material | AP | V1050 | Reinforcing Steel Supplier A | Invoice 48710 | 0 | 11048.52
500652 | 2025-11-17 | 202511 | 24-101 | 03-200 | Material | AP | V1012 | Reinforcing Steel Supplier E | Invoice 54334 | 0 | 69401.97
500986 | 2025-11-17 | 202511 | 24-104 | 03-300 | Material | AP | V1022 | Cast-in-Place Concrete Supplier F | Invoice 41317 | 0 | 91803.31
501998 | 2025-11-17 | 202511 | 25-115 | 03-300 | Material | AP | V1061 | Cast-in-Place Concrete Supplier A | Invoice 83120 | 0 | 355.22
501535 | 2025-11-18 | 202511 | 25-110 | 03-300 | Material | AP | V1041 | Cast-in-Place Concrete Supplier A | Invoice 57776 | 0 | 50501.94
501768 | 2025-11-18 | 202511 | 25-112 | 03-300 | Material | AP | V1051 | Cast-in-Place Concrete Supplier F | Invoice 51427 | 0 | 43462.12
501519 | 2025-11-19 | 202511 | 25-110 | 03-200 | Material | AP | V1040 | Reinforcing Steel Supplier B | Invoice 81496 | 0 | 72289.57
502123 | 2025-11-20 | 202511 | 25-118 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 41561 | 0 | 8363.11
500077 | 2025-11-21 | 202511 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Nov 21 | 195 | 17939.85
500351 | 2025-11-21 | 202511 | 23-098 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Nov 21 | 422.3 | 29982.89
500485 | 2025-11-21 | 202511 | 24-101 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Nov 21 | 397.1 | 36536.18
500629 | 2025-11-21 | 202511 | 24-101 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Nov 21 | 93.6 | 6923.1
500687 | 2025-11-21 | 202511 | 24-101 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Nov 21 | 5.8 | 409.93
500814 | 2025-11-21 | 202511 | 24-104 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Nov 21 | 324 | 29811.25
500942 | 2025-11-21 | 202511 | 24-104 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Nov 21 | 324.6 | 24018.03
500987 | 2025-11-21 | 202511 | 24-104 | 03-300 | Material | AP | V1022 | Cast-in-Place Concrete Supplier F | Invoice 71913 | 0 | 100878.21
501121 | 2025-11-21 | 202511 | 24-107 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Nov 21 | 251.1 | 23102.07
501235 | 2025-11-21 | 202511 | 24-107 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Nov 21 | 467.6 | 34600.32
501256 | 2025-11-21 | 202511 | 24-107 | 03-200 | Material | AP | V1031 | Reinforcing Steel Supplier C | Invoice 88893 | 0 | 108374.58
501382 | 2025-11-21 | 202511 | 25-110 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Nov 21 | 136.3 | 12537.02
501486 | 2025-11-21 | 202511 | 25-110 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Nov 21 | 471.3 | 34878.78
501536 | 2025-11-21 | 202511 | 25-110 | 03-300 | Material | AP | V1041 | Cast-in-Place Concrete Supplier A | Invoice 34200 | 0 | 36374.09
501628 | 2025-11-21 | 202511 | 25-112 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Nov 21 | 59.1 | 5436.59
501732 | 2025-11-21 | 202511 | 25-112 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Nov 21 | 177.9 | 13161.87
501862 | 2025-11-21 | 202511 | 25-115 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Nov 21 | 85 | 7823.24
501952 | 2025-11-21 | 202511 | 25-115 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Nov 21 | 24.7 | 1825.12
502078 | 2025-11-21 | 202511 | 25-118 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Nov 21 | 49.3 | 4538.46
500152 | 2025-11-22 | 202511 | 23-098 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 18306 | 0 | 5531.1
500550 | 2025-11-22 | 202511 | 24-101 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 71254 | 0 | 18850.31
501910 | 2025-11-22 | 202511 | 25-115 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 57710 | 0 | 3633.07
501752 | 2025-11-23 | 202511 | 25-112 | 03-200 | Material | AP | V1050 | Reinforcing Steel Supplier A | Invoice 95144 | 0 | 5117.23
501520 | 2025-11-24 | 202511 | 25-110 | 03-200 | Material | AP | V1040 | Reinforcing Steel Supplier B | Invoice 77144 | 0 | 25309.86
501537 | 2025-11-24 | 202511 | 25-110 | 03-300 | Material | AP | V1041 | Cast-in-Place Concrete Supplier A | Invoice 84933 | 0 | 44608.47
500307 | 2025-11-25 | 202511 | 23-098 | 04-200 | Subcontract | AP | V1004 | Masonry Subcontractor A | Progress claim Nov 2025 | 0 | 16336.3
500375 | 2025-11-25 | 202511 | 23-098 | 07-200 | Subcontract | AP | V1006 | Roofing Subcontractor B | Progress claim Nov 2025 | 0 | 107490.51
500401 | 2025-11-25 | 202511 | 23-098 | 09-200 | Subcontract | AP | V1008 | Drywall Subcontractor B | Progress claim Nov 2025 | 0 | 68306.08
500419 | 2025-11-25 | 202511 | 23-098 | 15-000 | Subcontract | AP | V1009 | Mechanical Subcontractor B | Progress claim Nov 2025 | 0 | 249464.14
500438 | 2025-11-25 | 202511 | 23-098 | 16-000 | Subcontract | AP | V1010 | Electrical Subcontractor C | Progress claim Nov 2025 | 0 | 137230.78
500671 | 2025-11-25 | 202511 | 24-101 | 03-300 | Material | AP | V1013 | Cast-in-Place Concrete Supplier C | Invoice 24102 | 0 | 38503.9
500681 | 2025-11-25 | 202511 | 24-101 | 05-100 | Subcontract | AP | V1014 | Structural Steel Subcontractor B | Progress claim Nov 2025 | 0 | 684283.53
500761 | 2025-11-25 | 202511 | 24-101 | 15-000 | Subcontract | AP | V1018 | Mechanical Subcontractor F | Progress claim Nov 2025 | 0 | 102408.14
500774 | 2025-11-25 | 202511 | 24-101 | 16-000 | Subcontract | AP | V1019 | Electrical Subcontractor G | Progress claim Nov 2025 | 0 | 122435.24
501007 | 2025-11-25 | 202511 | 24-104 | 05-100 | Subcontract | AP | V1024 | Structural Steel Subcontractor A | Progress claim Nov 2025 | 0 | 144628.11
501075 | 2025-11-25 | 202511 | 24-104 | 15-000 | Subcontract | AP | V1028 | Mechanical Subcontractor B | Progress claim Nov 2025 | 0 | 25689.81
501086 | 2025-11-25 | 202511 | 24-104 | 16-000 | Subcontract | AP | V1029 | Electrical Subcontractor F | Progress claim Nov 2025 | 0 | 21891.26
501172 | 2025-11-25 | 202511 | 24-107 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 76789 | 0 | 5686.83
501278 | 2025-11-25 | 202511 | 24-107 | 05-100 | Subcontract | AP | V1033 | Structural Steel Subcontractor D | Progress claim Nov 2025 | 0 | 213046.24
501344 | 2025-11-25 | 202511 | 24-107 | 15-000 | Subcontract | AP | V1037 | Mechanical Subcontractor A | Progress claim Nov 2025 | 0 | 25057.61
501355 | 2025-11-25 | 202511 | 24-107 | 16-000 | Subcontract | AP | V1038 | Electrical Subcontractor A | Progress claim Nov 2025 | 0 | 30725.07
501472 | 2025-11-25 | 202511 | 25-110 | 02-200 | Subcontract | AP | V1039 | Earthwork Subcontractor E | Progress claim Nov 2025 | 0 | 259490.08
501722 | 2025-11-25 | 202511 | 25-112 | 02-200 | Subcontract | AP | V1049 | Earthwork Subcontractor D | Progress claim Nov 2025 | 0 | 125222.29
501754 | 2025-11-25 | 202511 | 25-112 | 03-200 | Material | AP | V1050 | Reinforcing Steel Supplier A | Invoice 34287 | 0 | 24159.92
501946 | 2025-11-25 | 202511 | 25-115 | 02-200 | Subcontract | AP | V1059 | Earthwork Subcontractor B | Progress claim Nov 2025 | 0 | 97994.07
502154 | 2025-11-25 | 202511 | 25-118 | 02-200 | Subcontract | AP | V1069 | Earthwork Subcontractor E | Progress claim Nov 2025 | 0 | 160023.78
501680 | 2025-11-27 | 202511 | 25-112 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 49930 | 0 | 3993.03
500078 | 2025-11-28 | 202511 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Nov 28 | 173.7 | 15976.14
500352 | 2025-11-28 | 202511 | 23-098 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Nov 28 | 139.9 | 9933.76
500486 | 2025-11-28 | 202511 | 24-101 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Nov 28 | 193.3 | 17785.77
500630 | 2025-11-28 | 202511 | 24-101 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Nov 28 | 559.1 | 41373.21
500688 | 2025-11-28 | 202511 | 24-101 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Nov 28 | 24 | 1700.58
500815 | 2025-11-28 | 202511 | 24-104 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Nov 28 | 259 | 23831.69
500943 | 2025-11-28 | 202511 | 24-104 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Nov 28 | 277.3 | 20518.63
501122 | 2025-11-28 | 202511 | 24-107 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Nov 28 | 94.2 | 8664.19
501236 | 2025-11-28 | 202511 | 24-107 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Nov 28 | 353.3 | 26141.48
501383 | 2025-11-28 | 202511 | 25-110 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Nov 28 | 160.1 | 14725.51
501487 | 2025-11-28 | 202511 | 25-110 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Nov 28 | 212.3 | 15713.75
501629 | 2025-11-28 | 202511 | 25-112 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Nov 28 | 122.8 | 11299.78
501733 | 2025-11-28 | 202511 | 25-112 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Nov 28 | 94.9 | 7024.91
501863 | 2025-11-28 | 202511 | 25-115 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Nov 28 | 63.4 | 5834.03
501953 | 2025-11-28 | 202511 | 25-115 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Nov 28 | 118 | 8733.28
502079 | 2025-11-28 | 202511 | 25-118 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Nov 28 | 49.1 | 4518.09
500191 | 2025-11-30 | 202511 | 23-098 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 17884.13
500578 | 2025-11-30 | 202511 | 24-101 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 65373.02
500900 | 2025-11-30 | 202511 | 24-104 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 31278.59
501200 | 2025-11-30 | 202511 | 24-107 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 39695.57
501458 | 2025-11-30 | 202511 | 25-110 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 18283.49
501709 | 2025-11-30 | 202511 | 25-112 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 13663.37
501934 | 2025-11-30 | 202511 | 25-115 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 7465.64
502143 | 2025-11-30 | 202511 | 25-118 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 8390.14
501681 | 2025-12-03 | 202512 | 25-112 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 91280 | 0 | 3973.98
501769 | 2025-12-03 | 202512 | 25-112 | 03-300 | Material | AP | V1051 | Cast-in-Place Concrete Supplier F | Invoice 91392 | 0 | 125489.11
500653 | 2025-12-04 | 202512 | 24-101 | 03-200 | Material | AP | V1012 | Reinforcing Steel Supplier E | Invoice 39513 | 0 | 1195.24
500673 | 2025-12-04 | 202512 | 24-101 | 03-300 | Material | AP | V1013 | Cast-in-Place Concrete Supplier C | Invoice 36901 | 0 | 28504.69
500079 | 2025-12-05 | 202512 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Dec 05 | 146.4 | 13471.02
500353 | 2025-12-05 | 202512 | 23-098 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Dec 05 | 170.9 | 12132.3
500385 | 2025-12-05 | 202512 | 23-098 | 08-100 | Material | AP | V1007 | Doors Supplier G | Invoice 83915 | 0 | 17256.53
500487 | 2025-12-05 | 202512 | 24-101 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Dec 05 | 302.7 | 27847.67
500631 | 2025-12-05 | 202512 | 24-101 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Dec 05 | 183.5 | 13578.88
500689 | 2025-12-05 | 202512 | 24-101 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Dec 05 | 64.9 | 4607.42
500816 | 2025-12-05 | 202512 | 24-104 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Dec 05 | 354.7 | 32631.19
500944 | 2025-12-05 | 202512 | 24-104 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Dec 05 | 445.4 | 32962.51
501123 | 2025-12-05 | 202512 | 24-107 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Dec 05 | 129.6 | 11925.76
501237 | 2025-12-05 | 202512 | 24-107 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Dec 05 | 211.2 | 15629.76
501283 | 2025-12-05 | 202512 | 24-107 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Dec 05 | 2.7 | 190.92
501384 | 2025-12-05 | 202512 | 25-110 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Dec 05 | 54 | 4968.19
501488 | 2025-12-05 | 202512 | 25-110 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Dec 05 | 392.4 | 29038.15
501521 | 2025-12-05 | 202512 | 25-110 | 03-200 | Material | AP | V1040 | Reinforcing Steel Supplier B | Invoice 38865 | 0 | 104124.18
501523 | 2025-12-05 | 202512 | 25-110 | 03-200 | Material | AP | V1040 | Reinforcing Steel Supplier B | Invoice 83254 | 0 | 25835.07
501630 | 2025-12-05 | 202512 | 25-112 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Dec 05 | 204.9 | 18848.77
501734 | 2025-12-05 | 202512 | 25-112 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Dec 05 | 343.8 | 25442.81
501864 | 2025-12-05 | 202512 | 25-115 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Dec 05 | 41 | 3772.66
501954 | 2025-12-05 | 202512 | 25-115 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Dec 05 | 163.9 | 12131.47
502080 | 2025-12-05 | 202512 | 25-118 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Dec 05 | 78.8 | 7253.95
502159 | 2025-12-05 | 202512 | 25-118 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Dec 05 | 41.6 | 3080.81
500990 | 2025-12-06 | 202512 | 24-104 | 03-300 | Material | AP | V1022 | Cast-in-Place Concrete Supplier F | Invoice 65696 | 0 | 42197.65
501269 | 2025-12-06 | 202512 | 24-107 | 03-300 | Material | AP | V1032 | Cast-in-Place Concrete Supplier G | Invoice 81651 | 0 | 18697.76
502193 | 2025-12-06 | 202512 | 25-118 | 03-200 | Material | AP | V1070 | Reinforcing Steel Supplier C | Invoice 93532 | 0 | 35701.25
500968 | 2025-12-07 | 202512 | 24-104 | 03-200 | Material | AP | V1021 | Reinforcing Steel Supplier D | Invoice 73523 | 0 | 11649.27
501436 | 2025-12-07 | 202512 | 25-110 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 47202 | 0 | 3271.87
500654 | 2025-12-08 | 202512 | 24-101 | 03-200 | Material | AP | V1012 | Reinforcing Steel Supplier E | Invoice 52402 | 0 | 2797.33
500969 | 2025-12-08 | 202512 | 24-104 | 03-200 | Material | AP | V1021 | Reinforcing Steel Supplier D | Invoice 12231 | 0 | 4895.97
500384 | 2025-12-10 | 202512 | 23-098 | 08-100 | Material | AP | V1007 | Doors Supplier G | Invoice 52012 | 0 | 55685.32
501522 | 2025-12-10 | 202512 | 25-110 | 03-200 | Material | AP | V1040 | Reinforcing Steel Supplier B | Invoice 29591 | 0 | 30395.05
502000 | 2025-12-10 | 202512 | 25-115 | 03-300 | Material | AP | V1061 | Cast-in-Place Concrete Supplier A | Invoice 91039 | 0 | 22536.7
502203 | 2025-12-10 | 202512 | 25-118 | 03-300 | Material | AP | V1071 | Cast-in-Place Concrete Supplier A | Invoice 59200 | 0 | 20723.47
501257 | 2025-12-11 | 202512 | 24-107 | 03-200 | Material | AP | V1031 | Reinforcing Steel Supplier C | Invoice 81585 | 0 | 45721.75
501437 | 2025-12-11 | 202512 | 25-110 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 69634 | 0 | 23384.01
501538 | 2025-12-11 | 202512 | 25-110 | 03-300 | Material | AP | V1041 | Cast-in-Place Concrete Supplier A | Invoice 95139 | 0 | 241316.3
500080 | 2025-12-12 | 202512 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Dec 12 | 134.4 | 12363.66
500354 | 2025-12-12 | 202512 | 23-098 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Dec 12 | 150.2 | 10662.82
500383 | 2025-12-12 | 202512 | 23-098 | 08-100 | Material | AP | V1007 | Doors Supplier G | Invoice 75598 | 0 | 34245.38
500488 | 2025-12-12 | 202512 | 24-101 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Dec 12 | 212.9 | 19585.3
500632 | 2025-12-12 | 202512 | 24-101 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Dec 12 | 85 | 6290.44
500690 | 2025-12-12 | 202512 | 24-101 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Dec 12 | 79.2 | 5624.29
500817 | 2025-12-12 | 202512 | 24-104 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Dec 12 | 247.6 | 22777.05
500874 | 2025-12-12 | 202512 | 24-104 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 53674 | 0 | 35399.34
500945 | 2025-12-12 | 202512 | 24-104 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Dec 12 | 328.6 | 24315.54
501124 | 2025-12-12 | 202512 | 24-107 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Dec 12 | 334.8 | 30804.75
501238 | 2025-12-12 | 202512 | 24-107 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Dec 12 | 178.6 | 13217.55
501284 | 2025-12-12 | 202512 | 24-107 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Dec 12 | 1.7 | 118.78
501385 | 2025-12-12 | 202512 | 25-110 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Dec 12 | 217.6 | 20018.84
501489 | 2025-12-12 | 202512 | 25-110 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Dec 12 | 995.9 | 73696.49
501631 | 2025-12-12 | 202512 | 25-112 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Dec 12 | 166.5 | 15314.7
501735 | 2025-12-12 | 202512 | 25-112 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Dec 12 | 409.8 | 30328.05
501865 | 2025-12-12 | 202512 | 25-115 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Dec 12 | 133.3 | 12259.27
501955 | 2025-12-12 | 202512 | 25-115 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Dec 12 | 314.6 | 23280.35
502081 | 2025-12-12 | 202512 | 25-118 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Dec 12 | 67.5 | 6208.94
502160 | 2025-12-12 | 202512 | 25-118 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Dec 12 | 116 | 8587.03
501756 | 2025-12-13 | 202512 | 25-112 | 03-200 | Material | AP | V1050 | Reinforcing Steel Supplier A | Invoice 94265 | 0 | 36244.49
500552 | 2025-12-14 | 202512 | 24-101 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 14813 | 0 | 40905.41
501986 | 2025-12-14 | 202512 | 25-115 | 03-200 | Material | AP | V1060 | Reinforcing Steel Supplier B | Invoice 55058 | 0 | 6046.29
500989 | 2025-12-15 | 202512 | 24-104 | 03-300 | Material | AP | V1022 | Cast-in-Place Concrete Supplier F | Invoice 52039 | 0 | 51298.66
501435 | 2025-12-15 | 202512 | 25-110 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 11358 | 0 | 3327.34
501985 | 2025-12-17 | 202512 | 25-115 | 03-200 | Material | AP | V1060 | Reinforcing Steel Supplier B | Invoice 34018 | 0 | 13847.77
502124 | 2025-12-17 | 202512 | 25-118 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 92195 | 0 | 12023.75
500551 | 2025-12-18 | 202512 | 24-101 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 66440 | 0 | 22671.63
501755 | 2025-12-18 | 202512 | 25-112 | 03-200 | Material | AP | V1050 | Reinforcing Steel Supplier A | Invoice 24764 | 0 | 38053.65
502002 | 2025-12-18 | 202512 | 25-115 | 03-300 | Material | AP | V1061 | Cast-in-Place Concrete Supplier A | Invoice 73645 | 0 | 23818.61
500081 | 2025-12-19 | 202512 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Dec 19 | 135.6 | 12476.74
500355 | 2025-12-19 | 202512 | 23-098 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Dec 19 | 290.5 | 20622.55
500489 | 2025-12-19 | 202512 | 24-101 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Dec 19 | 465.2 | 42801.27
500633 | 2025-12-19 | 202512 | 24-101 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Dec 19 | 124.9 | 9243.16
500691 | 2025-12-19 | 202512 | 24-101 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Dec 19 | 53.1 | 3769.19
500818 | 2025-12-19 | 202512 | 24-104 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Dec 19 | 319.9 | 29426.31
500946 | 2025-12-19 | 202512 | 24-104 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Dec 19 | 227.9 | 16863
501125 | 2025-12-19 | 202512 | 24-107 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Dec 19 | 97.2 | 8941.04
501173 | 2025-12-19 | 202512 | 24-107 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 86331 | 0 | 13244.7
501174 | 2025-12-19 | 202512 | 24-107 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 98350 | 0 | 9187.9
501239 | 2025-12-19 | 202512 | 24-107 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Dec 19 | 230.4 | 17051.24
501285 | 2025-12-19 | 202512 | 24-107 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Dec 19 | 6.3 | 449.62
501386 | 2025-12-19 | 202512 | 25-110 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Dec 19 | 149.4 | 13741.08
501490 | 2025-12-19 | 202512 | 25-110 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Dec 19 | 470.9 | 34844.79
501632 | 2025-12-19 | 202512 | 25-112 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Dec 19 | 67.9 | 6249.23
501682 | 2025-12-19 | 202512 | 25-112 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 41031 | 0 | 5756.09
501736 | 2025-12-19 | 202512 | 25-112 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Dec 19 | 265.2 | 19626.46
501866 | 2025-12-19 | 202512 | 25-115 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Dec 19 | 58.4 | 5376.84
501956 | 2025-12-19 | 202512 | 25-115 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Dec 19 | 310.6 | 22981.8
502082 | 2025-12-19 | 202512 | 25-118 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Dec 19 | 93.8 | 8633.6
502161 | 2025-12-19 | 202512 | 25-118 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Dec 19 | 173.2 | 12816.73
501683 | 2025-12-20 | 202512 | 25-112 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 40939 | 0 | 4592.59
501987 | 2025-12-20 | 202512 | 25-115 | 03-200 | Material | AP | V1060 | Reinforcing Steel Supplier B | Invoice 80710 | 0 | 19038.87
500674 | 2025-12-21 | 202512 | 24-101 | 03-300 | Material | AP | V1013 | Cast-in-Place Concrete Supplier C | Invoice 77398 | 0 | 23980.41
500970 | 2025-12-23 | 202512 | 24-104 | 03-200 | Material | AP | V1021 | Reinforcing Steel Supplier D | Invoice 12193 | 0 | 30920.46
501757 | 2025-12-23 | 202512 | 25-112 | 03-200 | Material | AP | V1050 | Reinforcing Steel Supplier A | Invoice 13902 | 0 | 29733.09
502001 | 2025-12-23 | 202512 | 25-115 | 03-300 | Material | AP | V1061 | Cast-in-Place Concrete Supplier A | Invoice 50548 | 0 | 7360.76
501270 | 2025-12-24 | 202512 | 24-107 | 03-300 | Material | AP | V1032 | Cast-in-Place Concrete Supplier G | Invoice 64569 | 0 | 30834.53
500376 | 2025-12-25 | 202512 | 23-098 | 07-200 | Subcontract | AP | V1006 | Roofing Subcontractor B | Progress claim Dec 2025 | 0 | 40458.49
500402 | 2025-12-25 | 202512 | 23-098 | 09-200 | Subcontract | AP | V1008 | Drywall Subcontractor B | Progress claim Dec 2025 | 0 | 135265.51
500420 | 2025-12-25 | 202512 | 23-098 | 15-000 | Subcontract | AP | V1009 | Mechanical Subcontractor B | Progress claim Dec 2025 | 0 | 263857.26
500439 | 2025-12-25 | 202512 | 23-098 | 16-000 | Subcontract | AP | V1010 | Electrical Subcontractor C | Progress claim Dec 2025 | 0 | 161637.43
500675 | 2025-12-25 | 202512 | 24-101 | 03-300 | Material | AP | V1013 | Cast-in-Place Concrete Supplier C | Invoice 38163 | 0 | 44473.93
500682 | 2025-12-25 | 202512 | 24-101 | 05-100 | Subcontract | AP | V1014 | Structural Steel Subcontractor B | Progress claim Dec 2025 | 0 | 700925.61
500732 | 2025-12-25 | 202512 | 24-101 | 07-200 | Subcontract | AP | V1015 | Roofing Subcontractor A | Progress claim Dec 2025 | 0 | 14746.17
500762 | 2025-12-25 | 202512 | 24-101 | 15-000 | Subcontract | AP | V1018 | Mechanical Subcontractor F | Progress claim Dec 2025 | 0 | 141759.57
500775 | 2025-12-25 | 202512 | 24-101 | 16-000 | Subcontract | AP | V1019 | Electrical Subcontractor G | Progress claim Dec 2025 | 0 | 183833.28
500999 | 2025-12-25 | 202512 | 24-104 | 04-200 | Subcontract | AP | V1023 | Masonry Subcontractor D | Progress claim Dec 2025 | 0 | 33592.57
501008 | 2025-12-25 | 202512 | 24-104 | 05-100 | Subcontract | AP | V1024 | Structural Steel Subcontractor A | Progress claim Dec 2025 | 0 | 259215.71
501076 | 2025-12-25 | 202512 | 24-104 | 15-000 | Subcontract | AP | V1028 | Mechanical Subcontractor B | Progress claim Dec 2025 | 0 | 74921.6
501087 | 2025-12-25 | 202512 | 24-104 | 16-000 | Subcontract | AP | V1029 | Electrical Subcontractor F | Progress claim Dec 2025 | 0 | 52540.21
501271 | 2025-12-25 | 202512 | 24-107 | 03-300 | Material | AP | V1032 | Cast-in-Place Concrete Supplier G | Invoice 66743 | 0 | 51641.56
501279 | 2025-12-25 | 202512 | 24-107 | 05-100 | Subcontract | AP | V1033 | Structural Steel Subcontractor D | Progress claim Dec 2025 | 0 | 402187.63
501345 | 2025-12-25 | 202512 | 24-107 | 15-000 | Subcontract | AP | V1037 | Mechanical Subcontractor A | Progress claim Dec 2025 | 0 | 54644.32
501356 | 2025-12-25 | 202512 | 24-107 | 16-000 | Subcontract | AP | V1038 | Electrical Subcontractor A | Progress claim Dec 2025 | 0 | 58119.46
501473 | 2025-12-25 | 202512 | 25-110 | 02-200 | Subcontract | AP | V1039 | Earthwork Subcontractor E | Progress claim Dec 2025 | 0 | 151857.5
501723 | 2025-12-25 | 202512 | 25-112 | 02-200 | Subcontract | AP | V1049 | Earthwork Subcontractor D | Progress claim Dec 2025 | 0 | 45672.4
501787 | 2025-12-25 | 202512 | 25-112 | 05-100 | Subcontract | AP | V1053 | Structural Steel Subcontractor F | Progress claim Dec 2025 | 0 | 3995.38
501947 | 2025-12-25 | 202512 | 25-115 | 02-200 | Subcontract | AP | V1059 | Earthwork Subcontractor B | Progress claim Dec 2025 | 0 | 159312.84
502155 | 2025-12-25 | 202512 | 25-118 | 02-200 | Subcontract | AP | V1069 | Earthwork Subcontractor E | Progress claim Dec 2025 | 0 | 512003.35
500082 | 2025-12-26 | 202512 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Dec 26 | 89.8 | 8259.89
500356 | 2025-12-26 | 202512 | 23-098 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Dec 26 | 122.6 | 8703.09
500490 | 2025-12-26 | 202512 | 24-101 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Dec 26 | 98 | 9017.81
500634 | 2025-12-26 | 202512 | 24-101 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Dec 26 | 151.4 | 11203.24
500692 | 2025-12-26 | 202512 | 24-101 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Dec 26 | 34.8 | 2473.26
500819 | 2025-12-26 | 202512 | 24-104 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Dec 26 | 180.2 | 16582.98
500947 | 2025-12-26 | 202512 | 24-104 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Dec 26 | 396.6 | 29346.17
501126 | 2025-12-26 | 202512 | 24-107 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Dec 26 | 376.2 | 34608.91
501240 | 2025-12-26 | 202512 | 24-107 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Dec 26 | 196 | 14504.33
501286 | 2025-12-26 | 202512 | 24-107 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Dec 26 | 8.7 | 615.8
501387 | 2025-12-26 | 202512 | 25-110 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Dec 26 | 205.9 | 18939.38
501491 | 2025-12-26 | 202512 | 25-110 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Dec 26 | 1048.4 | 77580.45
501633 | 2025-12-26 | 202512 | 25-112 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Dec 26 | 70.9 | 6521.62
501737 | 2025-12-26 | 202512 | 25-112 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Dec 26 | 457.7 | 33867.74
501867 | 2025-12-26 | 202512 | 25-115 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Dec 26 | 103.4 | 9516.98
501912 | 2025-12-26 | 202512 | 25-115 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 16838 | 0 | 10546.43
501957 | 2025-12-26 | 202512 | 25-115 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Dec 26 | 577.1 | 42706.36
502083 | 2025-12-26 | 202512 | 25-118 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Dec 26 | 91.4 | 8408.2
502162 | 2025-12-26 | 202512 | 25-118 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Dec 26 | 83.8 | 6198.94
500155 | 2025-12-27 | 202512 | 23-098 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 64801 | 0 | 19022.79
500988 | 2025-12-27 | 202512 | 24-104 | 03-300 | Material | AP | V1022 | Cast-in-Place Concrete Supplier F | Invoice 15261 | 0 | 39436.74
500192 | 2025-12-31 | 202512 | 23-098 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 15101.56
500579 | 2025-12-31 | 202512 | 24-101 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 81030.93
500901 | 2025-12-31 | 202512 | 24-104 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 34605.03
501201 | 2025-12-31 | 202512 | 24-107 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 43842.38
501459 | 2025-12-31 | 202512 | 25-110 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 26668.21
501710 | 2025-12-31 | 202512 | 25-112 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 19741.76
501935 | 2025-12-31 | 202512 | 25-115 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 11110.52
502144 | 2025-12-31 | 202512 | 25-118 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 23191.14
500083 | 2026-01-02 | 202601 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jan 02 | 109.6 | 10084.03
500357 | 2026-01-02 | 202601 | 23-098 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Jan 02 | 159.9 | 11353.4
500491 | 2026-01-02 | 202601 | 24-101 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jan 02 | 281.9 | 25934.55
500693 | 2026-01-02 | 202601 | 24-101 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Jan 02 | 123.5 | 8769.9
500820 | 2026-01-02 | 202601 | 24-104 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jan 02 | 227.6 | 20939.62
500948 | 2026-01-02 | 202601 | 24-104 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Jan 02 | 122.7 | 9081.63
501013 | 2026-01-02 | 202601 | 24-104 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Jan 02 | 19 | 1345.7
501127 | 2026-01-02 | 202601 | 24-107 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jan 02 | 276.6 | 25442.66
501241 | 2026-01-02 | 202601 | 24-107 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Jan 02 | 45.7 | 3379.39
501287 | 2026-01-02 | 202601 | 24-107 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Jan 02 | 34.3 | 2436.24
501388 | 2026-01-02 | 202601 | 25-110 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jan 02 | 160.1 | 14725.41
501492 | 2026-01-02 | 202601 | 25-110 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Jan 02 | 1178.5 | 87205.69
501634 | 2026-01-02 | 202601 | 25-112 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jan 02 | 266.6 | 24526.49
501738 | 2026-01-02 | 202601 | 25-112 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Jan 02 | 664.4 | 49169.24
501868 | 2026-01-02 | 202601 | 25-115 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jan 02 | 113.9 | 10482.26
501958 | 2026-01-02 | 202601 | 25-115 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Jan 02 | 346.6 | 25645.19
502084 | 2026-01-02 | 202601 | 25-118 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jan 02 | 151.1 | 13897.53
502163 | 2026-01-02 | 202601 | 25-118 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Jan 02 | 126.4 | 9351.06
502267 | 2026-01-02 | 202601 | 25-121 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jan 02 | 34.5 | 3172.45
500553 | 2026-01-03 | 202601 | 24-101 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 69229 | 0 | 78143.2
501175 | 2026-01-03 | 202601 | 24-107 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 94540 | 0 | 27016.73
501758 | 2026-01-03 | 202601 | 25-112 | 03-200 | Material | AP | V1050 | Reinforcing Steel Supplier A | Invoice 54386 | 0 | 13843.31
501272 | 2026-01-05 | 202601 | 24-107 | 03-300 | Material | AP | V1032 | Cast-in-Place Concrete Supplier G | Invoice 86571 | 0 | 26909.96
501439 | 2026-01-05 | 202601 | 25-110 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 38097 | 0 | 10011.53
500877 | 2026-01-07 | 202601 | 24-104 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 23080 | 0 | 20818.91
502306 | 2026-01-07 | 202601 | 25-121 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 10121 | 0 | 3312.03
502205 | 2026-01-08 | 202601 | 25-118 | 03-300 | Material | AP | V1071 | Cast-in-Place Concrete Supplier A | Invoice 29644 | 0 | 45927.14
500084 | 2026-01-09 | 202601 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jan 09 | 61.7 | 5679.04
500358 | 2026-01-09 | 202601 | 23-098 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Jan 09 | 80.4 | 5711.94
500492 | 2026-01-09 | 202601 | 24-101 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jan 09 | 178.8 | 16446.09
500694 | 2026-01-09 | 202601 | 24-101 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Jan 09 | 42 | 2981.13
500821 | 2026-01-09 | 202601 | 24-104 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jan 09 | 161.5 | 14858.76
500949 | 2026-01-09 | 202601 | 24-104 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Jan 09 | 91.5 | 6770.99
501014 | 2026-01-09 | 202601 | 24-104 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Jan 09 | 24.8 | 1759
501128 | 2026-01-09 | 202601 | 24-107 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jan 09 | 329.4 | 30300.41
501242 | 2026-01-09 | 202601 | 24-107 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Jan 09 | 78.2 | 5783.95
501259 | 2026-01-09 | 202601 | 24-107 | 03-200 | Material | AP | V1031 | Reinforcing Steel Supplier C | Invoice 85219 | 0 | 1251.74
501273 | 2026-01-09 | 202601 | 24-107 | 03-300 | Material | AP | V1032 | Cast-in-Place Concrete Supplier G | Invoice 57972 | 0 | 16496.92
501288 | 2026-01-09 | 202601 | 24-107 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Jan 09 | 42.9 | 3046.06
501389 | 2026-01-09 | 202601 | 25-110 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jan 09 | 376.2 | 34605.89
501493 | 2026-01-09 | 202601 | 25-110 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Jan 09 | 398.9 | 29517.37
501635 | 2026-01-09 | 202601 | 25-112 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jan 09 | 104.5 | 9613.11
501739 | 2026-01-09 | 202601 | 25-112 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Jan 09 | 564.7 | 41791.44
501869 | 2026-01-09 | 202601 | 25-115 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jan 09 | 72.9 | 6707.31
501959 | 2026-01-09 | 202601 | 25-115 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Jan 09 | 535.5 | 39623.81
502085 | 2026-01-09 | 202601 | 25-118 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jan 09 | 169.5 | 15593.12
502164 | 2026-01-09 | 202601 | 25-118 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Jan 09 | 181.4 | 13424.24
502268 | 2026-01-09 | 202601 | 25-121 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jan 09 | 32.7 | 3007.41
500876 | 2026-01-10 | 202601 | 24-104 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 31690 | 0 | 12336.11
500971 | 2026-01-11 | 202601 | 24-104 | 03-200 | Material | AP | V1021 | Reinforcing Steel Supplier D | Invoice 88967 | 0 | 21241.35
501684 | 2026-01-11 | 202601 | 25-112 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 32142 | 0 | 5063.75
502003 | 2026-01-11 | 202601 | 25-115 | 03-300 | Material | AP | V1061 | Cast-in-Place Concrete Supplier A | Invoice 58583 | 0 | 17163.61
502204 | 2026-01-11 | 202601 | 25-118 | 03-300 | Material | AP | V1071 | Cast-in-Place Concrete Supplier A | Invoice 58773 | 0 | 55843.05
501258 | 2026-01-12 | 202601 | 24-107 | 03-200 | Material | AP | V1031 | Reinforcing Steel Supplier C | Invoice 16183 | 0 | 2352.92
501770 | 2026-01-12 | 202601 | 25-112 | 03-300 | Material | AP | V1051 | Cast-in-Place Concrete Supplier F | Invoice 56624 | 0 | 69258.33
501438 | 2026-01-13 | 202601 | 25-110 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 30864 | 0 | 17354.65
500992 | 2026-01-14 | 202601 | 24-104 | 03-300 | Material | AP | V1022 | Cast-in-Place Concrete Supplier F | Invoice 75277 | 0 | 65353.18
501759 | 2026-01-14 | 202601 | 25-112 | 03-200 | Material | AP | V1050 | Reinforcing Steel Supplier A | Invoice 49066 | 0 | 48701.54
501914 | 2026-01-14 | 202601 | 25-115 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 17347 | 0 | 10562.19
502004 | 2026-01-14 | 202601 | 25-115 | 03-300 | Material | AP | V1061 | Cast-in-Place Concrete Supplier A | Invoice 61826 | 0 | 24844.65
502127 | 2026-01-14 | 202601 | 25-118 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 10016 | 0 | 5997.52
502307 | 2026-01-15 | 202601 | 25-121 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 51530 | 0 | 3594.02
500085 | 2026-01-16 | 202601 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jan 16 | 121.8 | 11201.97
500359 | 2026-01-16 | 202601 | 23-098 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Jan 16 | 102.4 | 7273.14
500493 | 2026-01-16 | 202601 | 24-101 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jan 16 | 172.6 | 15874.96
500676 | 2026-01-16 | 202601 | 24-101 | 03-300 | Material | AP | V1013 | Cast-in-Place Concrete Supplier C | Invoice 92378 | 0 | 7283.84
500695 | 2026-01-16 | 202601 | 24-101 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Jan 16 | 87.7 | 6226.24
500822 | 2026-01-16 | 202601 | 24-104 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jan 16 | 85.4 | 7860.49
500950 | 2026-01-16 | 202601 | 24-104 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Jan 16 | 50.5 | 3740.26
501015 | 2026-01-16 | 202601 | 24-104 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Jan 16 | 62.7 | 4449.81
501129 | 2026-01-16 | 202601 | 24-107 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jan 16 | 175.9 | 16181.07
501243 | 2026-01-16 | 202601 | 24-107 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Jan 16 | 80.1 | 5929.31
501289 | 2026-01-16 | 202601 | 24-107 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Jan 16 | 27 | 1914.66
501390 | 2026-01-16 | 202601 | 25-110 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jan 16 | 89.3 | 8219.69
501494 | 2026-01-16 | 202601 | 25-110 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Jan 16 | 875.8 | 64807.54
501636 | 2026-01-16 | 202601 | 25-112 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jan 16 | 65.1 | 5987.89
501740 | 2026-01-16 | 202601 | 25-112 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Jan 16 | 220.5 | 16316.51
501772 | 2026-01-16 | 202601 | 25-112 | 03-300 | Material | AP | V1051 | Cast-in-Place Concrete Supplier F | Invoice 33878 | 0 | 72873.18
501870 | 2026-01-16 | 202601 | 25-115 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jan 16 | 33.5 | 3082.87
501960 | 2026-01-16 | 202601 | 25-115 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Jan 16 | 254.5 | 18834.77
501989 | 2026-01-16 | 202601 | 25-115 | 03-200 | Material | AP | V1060 | Reinforcing Steel Supplier B | Invoice 69991 | 0 | 31521.73
502086 | 2026-01-16 | 202601 | 25-118 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jan 16 | 47.3 | 4351.59
502165 | 2026-01-16 | 202601 | 25-118 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Jan 16 | 524.9 | 38842.38
502269 | 2026-01-16 | 202601 | 25-121 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jan 16 | 8.3 | 766.55
501539 | 2026-01-17 | 202601 | 25-110 | 03-300 | Material | AP | V1041 | Cast-in-Place Concrete Supplier A | Invoice 27775 | 0 | 67232.89
501760 | 2026-01-17 | 202601 | 25-112 | 03-200 | Material | AP | V1050 | Reinforcing Steel Supplier A | Invoice 53325 | 0 | 17310.4
502126 | 2026-01-17 | 202601 | 25-118 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 25695 | 0 | 3944.26
500156 | 2026-01-18 | 202601 | 23-098 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 88865 | 0 | 17117.44
500386 | 2026-01-18 | 202601 | 23-098 | 08-100 | Material | AP | V1007 | Doors Supplier G | Invoice 97291 | 0 | 195316.39
500677 | 2026-01-19 | 202601 | 24-101 | 03-300 | Material | AP | V1013 | Cast-in-Place Concrete Supplier C | Invoice 50963 | 0 | 11246.41
501988 | 2026-01-19 | 202601 | 25-115 | 03-200 | Material | AP | V1060 | Reinforcing Steel Supplier B | Invoice 16794 | 0 | 69994.85
502206 | 2026-01-20 | 202601 | 25-118 | 03-300 | Material | AP | V1071 | Cast-in-Place Concrete Supplier A | Invoice 54311 | 0 | 16329.64
501440 | 2026-01-22 | 202601 | 25-110 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 62902 | 0 | 13595.22
501771 | 2026-01-22 | 202601 | 25-112 | 03-300 | Material | AP | V1051 | Cast-in-Place Concrete Supplier F | Invoice 63634 | 0 | 16723.14
500086 | 2026-01-23 | 202601 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jan 23 | 82.6 | 7599.22
500360 | 2026-01-23 | 202601 | 23-098 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Jan 23 | 32.6 | 2313.41
500494 | 2026-01-23 | 202601 | 24-101 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jan 23 | 365.9 | 33664.76
500696 | 2026-01-23 | 202601 | 24-101 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Jan 23 | 77.5 | 5502.73
500823 | 2026-01-23 | 202601 | 24-104 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jan 23 | 255.3 | 23483.53
500951 | 2026-01-23 | 202601 | 24-104 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Jan 23 | 296.9 | 21972.55
501016 | 2026-01-23 | 202601 | 24-104 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Jan 23 | 47.8 | 3396.2
501130 | 2026-01-23 | 202601 | 24-107 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jan 23 | 148.7 | 13681.83
501244 | 2026-01-23 | 202601 | 24-107 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Jan 23 | 34.4 | 2542.86
501290 | 2026-01-23 | 202601 | 24-107 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Jan 23 | 27.2 | 1930.96
501391 | 2026-01-23 | 202601 | 25-110 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jan 23 | 149.1 | 13721.2
501495 | 2026-01-23 | 202601 | 25-110 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Jan 23 | 575 | 42549.29
501541 | 2026-01-23 | 202601 | 25-110 | 03-300 | Material | AP | V1041 | Cast-in-Place Concrete Supplier A | Invoice 15152 | 0 | 114218.9
501637 | 2026-01-23 | 202601 | 25-112 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jan 23 | 65.2 | 6002.16
501741 | 2026-01-23 | 202601 | 25-112 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Jan 23 | 270.3 | 20002.9
501871 | 2026-01-23 | 202601 | 25-115 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jan 23 | 108.6 | 9990.72
501961 | 2026-01-23 | 202601 | 25-115 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Jan 23 | 405.7 | 30021.07
502087 | 2026-01-23 | 202601 | 25-118 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jan 23 | 111.8 | 10284.4
502166 | 2026-01-23 | 202601 | 25-118 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Jan 23 | 248.9 | 18420.62
502270 | 2026-01-23 | 202601 | 25-121 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jan 23 | 32.6 | 2998.44
500875 | 2026-01-24 | 202601 | 24-104 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 24684 | 0 | 4487.48
501540 | 2026-01-24 | 202601 | 25-110 | 03-300 | Material | AP | V1041 | Cast-in-Place Concrete Supplier A | Invoice 86309 | 0 | 107234.25
501685 | 2026-01-24 | 202601 | 25-112 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 85635 | 0 | 3236.25
500403 | 2026-01-25 | 202601 | 23-098 | 09-200 | Subcontract | AP | V1008 | Drywall Subcontractor B | Progress claim Jan 2026 | 0 | 177389.1
500421 | 2026-01-25 | 202601 | 23-098 | 15-000 | Subcontract | AP | V1009 | Mechanical Subcontractor B | Progress claim Jan 2026 | 0 | 228134.51
500440 | 2026-01-25 | 202601 | 23-098 | 16-000 | Subcontract | AP | V1010 | Electrical Subcontractor C | Progress claim Jan 2026 | 0 | 139698.91
500683 | 2026-01-25 | 202601 | 24-101 | 05-100 | Subcontract | AP | V1014 | Structural Steel Subcontractor B | Progress claim Jan 2026 | 0 | 406265.73
500733 | 2026-01-25 | 202601 | 24-101 | 07-200 | Subcontract | AP | V1015 | Roofing Subcontractor A | Progress claim Jan 2026 | 0 | 127248.59
500763 | 2026-01-25 | 202601 | 24-101 | 15-000 | Subcontract | AP | V1018 | Mechanical Subcontractor F | Progress claim Jan 2026 | 0 | 194818.01
500776 | 2026-01-25 | 202601 | 24-101 | 16-000 | Subcontract | AP | V1019 | Electrical Subcontractor G | Progress claim Jan 2026 | 0 | 226241.04
500991 | 2026-01-25 | 202601 | 24-104 | 03-300 | Material | AP | V1022 | Cast-in-Place Concrete Supplier F | Invoice 65017 | 0 | 19098.66
501000 | 2026-01-25 | 202601 | 24-104 | 04-200 | Subcontract | AP | V1023 | Masonry Subcontractor D | Progress claim Jan 2026 | 0 | 107970.58
501009 | 2026-01-25 | 202601 | 24-104 | 05-100 | Subcontract | AP | V1024 | Structural Steel Subcontractor A | Progress claim Jan 2026 | 0 | 332948.65
501077 | 2026-01-25 | 202601 | 24-104 | 15-000 | Subcontract | AP | V1028 | Mechanical Subcontractor B | Progress claim Jan 2026 | 0 | 110687.52
501088 | 2026-01-25 | 202601 | 24-104 | 16-000 | Subcontract | AP | V1029 | Electrical Subcontractor F | Progress claim Jan 2026 | 0 | 75948.14
501280 | 2026-01-25 | 202601 | 24-107 | 05-100 | Subcontract | AP | V1033 | Structural Steel Subcontractor D | Progress claim Jan 2026 | 0 | 340443.18
501318 | 2026-01-25 | 202601 | 24-107 | 07-200 | Subcontract | AP | V1034 | Roofing Subcontractor A | Progress claim Jan 2026 | 0 | 14648.74
501346 | 2026-01-25 | 202601 | 24-107 | 15-000 | Subcontract | AP | V1037 | Mechanical Subcontractor A | Progress claim Jan 2026 | 0 | 78804.99
501357 | 2026-01-25 | 202601 | 24-107 | 16-000 | Subcontract | AP | V1038 | Electrical Subcontractor A | Progress claim Jan 2026 | 0 | 95023.52
501474 | 2026-01-25 | 202601 | 25-110 | 02-200 | Subcontract | AP | V1039 | Earthwork Subcontractor E | Progress claim Jan 2026 | 0 | 35193.32
501524 | 2026-01-25 | 202601 | 25-110 | 03-200 | Material | AP | V1040 | Reinforcing Steel Supplier B | Invoice 87659 | 0 | 181920.55
501558 | 2026-01-25 | 202601 | 25-110 | 05-100 | Subcontract | AP | V1043 | Structural Steel Subcontractor E | Progress claim Jan 2026 | 0 | 71794.53
501788 | 2026-01-25 | 202601 | 25-112 | 05-100 | Subcontract | AP | V1053 | Structural Steel Subcontractor F | Progress claim Jan 2026 | 0 | 99273.83
501837 | 2026-01-25 | 202601 | 25-112 | 15-000 | Subcontract | AP | V1057 | Mechanical Subcontractor E | Progress claim Jan 2026 | 0 | 15452.31
501846 | 2026-01-25 | 202601 | 25-112 | 16-000 | Subcontract | AP | V1058 | Electrical Subcontractor G | Progress claim Jan 2026 | 0 | 11435.92
501913 | 2026-01-25 | 202601 | 25-115 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 35605 | 0 | 6312
501948 | 2026-01-25 | 202601 | 25-115 | 02-200 | Subcontract | AP | V1059 | Earthwork Subcontractor B | Progress claim Jan 2026 | 0 | 84562.05
502156 | 2026-01-25 | 202601 | 25-118 | 02-200 | Subcontract | AP | V1069 | Earthwork Subcontractor E | Progress claim Jan 2026 | 0 | 432118.19
502194 | 2026-01-25 | 202601 | 25-118 | 03-200 | Material | AP | V1070 | Reinforcing Steel Supplier C | Invoice 37946 | 0 | 125619.15
502335 | 2026-01-25 | 202601 | 25-121 | 02-200 | Subcontract | AP | V1078 | Earthwork Subcontractor A | Progress claim Jan 2026 | 0 | 35114.64
501686 | 2026-01-26 | 202601 | 25-112 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 41574 | 0 | 9618.2
502005 | 2026-01-26 | 202601 | 25-115 | 03-300 | Material | AP | V1061 | Cast-in-Place Concrete Supplier A | Invoice 56350 | 0 | 66104.69
502125 | 2026-01-27 | 202601 | 25-118 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 15961 | 0 | 9169.7
500087 | 2026-01-30 | 202601 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jan 30 | 55.4 | 5098.37
500361 | 2026-01-30 | 202601 | 23-098 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Jan 30 | 109.7 | 7789.99
500495 | 2026-01-30 | 202601 | 24-101 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jan 30 | 267.3 | 24589.78
500697 | 2026-01-30 | 202601 | 24-101 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Jan 30 | 105.8 | 7509.63
500824 | 2026-01-30 | 202601 | 24-104 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jan 30 | 335 | 30821.32
500952 | 2026-01-30 | 202601 | 24-104 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Jan 30 | 320.4 | 23710.97
501017 | 2026-01-30 | 202601 | 24-104 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Jan 30 | 34 | 2414.46
501131 | 2026-01-30 | 202601 | 24-107 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jan 30 | 140.9 | 12966.82
501245 | 2026-01-30 | 202601 | 24-107 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Jan 30 | 17.9 | 1321.51
501291 | 2026-01-30 | 202601 | 24-107 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Jan 30 | 12 | 851.24
501392 | 2026-01-30 | 202601 | 25-110 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jan 30 | 142.6 | 13120.93
501496 | 2026-01-30 | 202601 | 25-110 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Jan 30 | 622.5 | 46068.55
501638 | 2026-01-30 | 202601 | 25-112 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jan 30 | 192.4 | 17698.41
501742 | 2026-01-30 | 202601 | 25-112 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Jan 30 | 82.3 | 6093.27
501872 | 2026-01-30 | 202601 | 25-115 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jan 30 | 130.5 | 12004.48
501962 | 2026-01-30 | 202601 | 25-115 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Jan 30 | 973 | 72001.47
502088 | 2026-01-30 | 202601 | 25-118 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jan 30 | 91.8 | 8442.16
502167 | 2026-01-30 | 202601 | 25-118 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Jan 30 | 291.5 | 21571.2
502271 | 2026-01-30 | 202601 | 25-121 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jan 30 | 39.8 | 3665.8
500193 | 2026-01-31 | 202601 | 23-098 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 9779.24
500580 | 2026-01-31 | 202601 | 24-101 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 87059.19
500902 | 2026-01-31 | 202601 | 24-104 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 45106.27
501202 | 2026-01-31 | 202601 | 24-107 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 45207.02
501460 | 2026-01-31 | 202601 | 25-110 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 40360.15
501711 | 2026-01-31 | 202601 | 25-112 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 25425.61
501936 | 2026-01-31 | 202601 | 25-115 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 17385.11
502145 | 2026-01-31 | 202601 | 25-118 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 37461.45
502326 | 2026-01-31 | 202601 | 25-121 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 2066.89
501274 | 2026-02-03 | 202602 | 24-107 | 03-300 | Material | AP | V1032 | Cast-in-Place Concrete Supplier G | Invoice 78633 | 0 | 651.23
501276 | 2026-02-03 | 202602 | 24-107 | 03-300 | Material | AP | V1032 | Cast-in-Place Concrete Supplier G | Invoice 16195 | 0 | 780.83
502008 | 2026-02-04 | 202602 | 25-115 | 03-300 | Material | AP | V1061 | Cast-in-Place Concrete Supplier A | Invoice 67151 | 0 | 45959.1
500554 | 2026-02-05 | 202602 | 24-101 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 20620 | 0 | 27156.67
500555 | 2026-02-05 | 202602 | 24-101 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 99070 | 0 | 31765.07
502208 | 2026-02-05 | 202602 | 25-118 | 03-300 | Material | AP | V1071 | Cast-in-Place Concrete Supplier A | Invoice 68920 | 0 | 159129.83
502309 | 2026-02-05 | 202602 | 25-121 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 83096 | 0 | 5459.15
500088 | 2026-02-06 | 202602 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Feb 06 | 54.4 | 5006.44
500362 | 2026-02-06 | 202602 | 23-098 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Feb 06 | 67.1 | 4766.86
500496 | 2026-02-06 | 202602 | 24-101 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Feb 06 | 322.3 | 29653.87
500698 | 2026-02-06 | 202602 | 24-101 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Feb 06 | 183.4 | 13022.66
500825 | 2026-02-06 | 202602 | 24-104 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Feb 06 | 277.1 | 25493.48
500879 | 2026-02-06 | 202602 | 24-104 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 42413 | 0 | 7650.02
500953 | 2026-02-06 | 202602 | 24-104 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Feb 06 | 62.3 | 4612.57
501018 | 2026-02-06 | 202602 | 24-104 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Feb 06 | 94.7 | 6725.06
501132 | 2026-02-06 | 202602 | 24-107 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Feb 06 | 173.7 | 15976.99
501292 | 2026-02-06 | 202602 | 24-107 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Feb 06 | 61.6 | 4373.2
501393 | 2026-02-06 | 202602 | 25-110 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Feb 06 | 303.5 | 27921.58
501497 | 2026-02-06 | 202602 | 25-110 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Feb 06 | 378 | 27971.23
501639 | 2026-02-06 | 202602 | 25-112 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Feb 06 | 212.3 | 19527.17
501743 | 2026-02-06 | 202602 | 25-112 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Feb 06 | 254.6 | 18838.75
501873 | 2026-02-06 | 202602 | 25-115 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Feb 06 | 181 | 16653.51
501963 | 2026-02-06 | 202602 | 25-115 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Feb 06 | 551.9 | 40839.67
502089 | 2026-02-06 | 202602 | 25-118 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Feb 06 | 153 | 14080.2
502168 | 2026-02-06 | 202602 | 25-118 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Feb 06 | 363.2 | 26873.89
502196 | 2026-02-06 | 202602 | 25-118 | 03-200 | Material | AP | V1070 | Reinforcing Steel Supplier C | Invoice 24237 | 0 | 189624.85
502272 | 2026-02-06 | 202602 | 25-121 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Feb 06 | 70.8 | 6516.04
501916 | 2026-02-08 | 202602 | 25-115 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 59705 | 0 | 6729.81
502207 | 2026-02-08 | 202602 | 25-118 | 03-300 | Material | AP | V1071 | Cast-in-Place Concrete Supplier A | Invoice 14395 | 0 | 76541.33
502308 | 2026-02-09 | 202602 | 25-121 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 42297 | 0 | 4700.27
501774 | 2026-02-10 | 202602 | 25-112 | 03-300 | Material | AP | V1051 | Cast-in-Place Concrete Supplier F | Invoice 21585 | 0 | 60874.89
501917 | 2026-02-10 | 202602 | 25-115 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 72892 | 0 | 9532.43
502128 | 2026-02-10 | 202602 | 25-118 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 85921 | 0 | 26726.39
501990 | 2026-02-11 | 202602 | 25-115 | 03-200 | Material | AP | V1060 | Reinforcing Steel Supplier B | Invoice 17006 | 0 | 62620.41
502007 | 2026-02-11 | 202602 | 25-115 | 03-300 | Material | AP | V1061 | Cast-in-Place Concrete Supplier A | Invoice 10854 | 0 | 77233.35
501992 | 2026-02-12 | 202602 | 25-115 | 03-200 | Material | AP | V1060 | Reinforcing Steel Supplier B | Invoice 70002 | 0 | 13548.64
500089 | 2026-02-13 | 202602 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Feb 13 | 55 | 5055.57
500363 | 2026-02-13 | 202602 | 23-098 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Feb 13 | 98.8 | 7013.11
500497 | 2026-02-13 | 202602 | 24-101 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Feb 13 | 310 | 28519.11
500699 | 2026-02-13 | 202602 | 24-101 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Feb 13 | 119.7 | 8497.98
500826 | 2026-02-13 | 202602 | 24-104 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Feb 13 | 208.1 | 19142.12
500954 | 2026-02-13 | 202602 | 24-104 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Feb 13 | 57.5 | 4254.69
501019 | 2026-02-13 | 202602 | 24-104 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Feb 13 | 169.3 | 12017.75
501133 | 2026-02-13 | 202602 | 24-107 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Feb 13 | 135.9 | 12500.74
501275 | 2026-02-13 | 202602 | 24-107 | 03-300 | Material | AP | V1032 | Cast-in-Place Concrete Supplier G | Invoice 36969 | 0 | 1756.45
501293 | 2026-02-13 | 202602 | 24-107 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Feb 13 | 107.2 | 7609.59
501394 | 2026-02-13 | 202602 | 25-110 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Feb 13 | 205.2 | 18875.34
501498 | 2026-02-13 | 202602 | 25-110 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Feb 13 | 576.5 | 42659.59
501640 | 2026-02-13 | 202602 | 25-112 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Feb 13 | 158.5 | 14585.45
501744 | 2026-02-13 | 202602 | 25-112 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Feb 13 | 236.7 | 17518.55
501773 | 2026-02-13 | 202602 | 25-112 | 03-300 | Material | AP | V1051 | Cast-in-Place Concrete Supplier F | Invoice 47005 | 0 | 10303.51
501874 | 2026-02-13 | 202602 | 25-115 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Feb 13 | 80.3 | 7385.03
501964 | 2026-02-13 | 202602 | 25-115 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Feb 13 | 918.3 | 67957.04
502090 | 2026-02-13 | 202602 | 25-118 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Feb 13 | 191.6 | 17631.37
502169 | 2026-02-13 | 202602 | 25-118 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Feb 13 | 624.2 | 46193.37
502273 | 2026-02-13 | 202602 | 25-121 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Feb 13 | 33.3 | 3063.88
501527 | 2026-02-14 | 202602 | 25-110 | 03-200 | Material | AP | V1040 | Reinforcing Steel Supplier B | Invoice 14702 | 0 | 79853.39
502195 | 2026-02-14 | 202602 | 25-118 | 03-200 | Material | AP | V1070 | Reinforcing Steel Supplier C | Invoice 10591 | 0 | 48640.22
500157 | 2026-02-15 | 202602 | 23-098 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 21572 | 0 | 11560.57
501441 | 2026-02-15 | 202602 | 25-110 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 37136 | 0 | 26431.48
500878 | 2026-02-16 | 202602 | 24-104 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 76932 | 0 | 13983.68
501176 | 2026-02-16 | 202602 | 24-107 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 88077 | 0 | 11951.29
501689 | 2026-02-16 | 202602 | 25-112 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 95765 | 0 | 2412.62
501991 | 2026-02-17 | 202602 | 25-115 | 03-200 | Material | AP | V1060 | Reinforcing Steel Supplier B | Invoice 91000 | 0 | 50679.82
500387 | 2026-02-19 | 202602 | 23-098 | 08-100 | Material | AP | V1007 | Doors Supplier G | Invoice 83827 | 0 | 56620.89
501177 | 2026-02-19 | 202602 | 24-107 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 64000 | 0 | 12482.24
500090 | 2026-02-20 | 202602 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Feb 20 | 102.8 | 9461.62
500364 | 2026-02-20 | 202602 | 23-098 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Feb 20 | 66.6 | 4730.12
500498 | 2026-02-20 | 202602 | 24-101 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Feb 20 | 235.4 | 21652.46
500700 | 2026-02-20 | 202602 | 24-101 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Feb 20 | 86.5 | 6141.32
500827 | 2026-02-20 | 202602 | 24-104 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Feb 20 | 273.5 | 25158.04
500880 | 2026-02-20 | 202602 | 24-104 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 21054 | 0 | 18436.58
500955 | 2026-02-20 | 202602 | 24-104 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Feb 20 | 33 | 2441.14
501020 | 2026-02-20 | 202602 | 24-104 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Feb 20 | 203.2 | 14425.36
501134 | 2026-02-20 | 202602 | 24-107 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Feb 20 | 492 | 45267.27
501294 | 2026-02-20 | 202602 | 24-107 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Feb 20 | 36.7 | 2605.61
501395 | 2026-02-20 | 202602 | 25-110 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Feb 20 | 104.9 | 9654.6
501499 | 2026-02-20 | 202602 | 25-110 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Feb 20 | 1112.3 | 82309.65
501641 | 2026-02-20 | 202602 | 25-112 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Feb 20 | 160.7 | 14782.05
501745 | 2026-02-20 | 202602 | 25-112 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Feb 20 | 88.8 | 6574.68
501875 | 2026-02-20 | 202602 | 25-115 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Feb 20 | 133.7 | 12296.72
501965 | 2026-02-20 | 202602 | 25-115 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Feb 20 | 1441.3 | 106653.84
502091 | 2026-02-20 | 202602 | 25-118 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Feb 20 | 267.9 | 24647.35
502170 | 2026-02-20 | 202602 | 25-118 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Feb 20 | 998.3 | 73873.07
502274 | 2026-02-20 | 202602 | 25-121 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Feb 20 | 66.5 | 6117.29
501761 | 2026-02-21 | 202602 | 25-112 | 03-200 | Material | AP | V1050 | Reinforcing Steel Supplier A | Invoice 99819 | 0 | 38730.63
502006 | 2026-02-22 | 202602 | 25-115 | 03-300 | Material | AP | V1061 | Cast-in-Place Concrete Supplier A | Invoice 73738 | 0 | 13295.95
501688 | 2026-02-23 | 202602 | 25-112 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 16489 | 0 | 5928.38
500404 | 2026-02-25 | 202602 | 23-098 | 09-200 | Subcontract | AP | V1008 | Drywall Subcontractor B | Progress claim Feb 2026 | 0 | 217782.12
500422 | 2026-02-25 | 202602 | 23-098 | 15-000 | Subcontract | AP | V1009 | Mechanical Subcontractor B | Progress claim Feb 2026 | 0 | 178176.83
500441 | 2026-02-25 | 202602 | 23-098 | 16-000 | Subcontract | AP | V1010 | Electrical Subcontractor C | Progress claim Feb 2026 | 0 | 110030.25
500684 | 2026-02-25 | 202602 | 24-101 | 05-100 | Subcontract | AP | V1014 | Structural Steel Subcontractor B | Progress claim Feb 2026 | 0 | 149583.71
500734 | 2026-02-25 | 202602 | 24-101 | 07-200 | Subcontract | AP | V1015 | Roofing Subcontractor A | Progress claim Feb 2026 | 0 | 192584.6
500764 | 2026-02-25 | 202602 | 24-101 | 15-000 | Subcontract | AP | V1018 | Mechanical Subcontractor F | Progress claim Feb 2026 | 0 | 217590.71
500777 | 2026-02-25 | 202602 | 24-101 | 16-000 | Subcontract | AP | V1019 | Electrical Subcontractor G | Progress claim Feb 2026 | 0 | 256180.13
500993 | 2026-02-25 | 202602 | 24-104 | 03-300 | Material | AP | V1022 | Cast-in-Place Concrete Supplier F | Invoice 37679 | 0 | 32774.57
501001 | 2026-02-25 | 202602 | 24-104 | 04-200 | Subcontract | AP | V1023 | Masonry Subcontractor D | Progress claim Feb 2026 | 0 | 196176.43
501010 | 2026-02-25 | 202602 | 24-104 | 05-100 | Subcontract | AP | V1024 | Structural Steel Subcontractor A | Progress claim Feb 2026 | 0 | 255939.67
501052 | 2026-02-25 | 202602 | 24-104 | 07-200 | Subcontract | AP | V1025 | Roofing Subcontractor F | Progress claim Feb 2026 | 0 | 32302.89
501078 | 2026-02-25 | 202602 | 24-104 | 15-000 | Subcontract | AP | V1028 | Mechanical Subcontractor B | Progress claim Feb 2026 | 0 | 126505.33
501089 | 2026-02-25 | 202602 | 24-104 | 16-000 | Subcontract | AP | V1029 | Electrical Subcontractor F | Progress claim Feb 2026 | 0 | 98893.96
501281 | 2026-02-25 | 202602 | 24-107 | 05-100 | Subcontract | AP | V1033 | Structural Steel Subcontractor D | Progress claim Feb 2026 | 0 | 151052.96
501319 | 2026-02-25 | 202602 | 24-107 | 07-200 | Subcontract | AP | V1034 | Roofing Subcontractor A | Progress claim Feb 2026 | 0 | 83873.23
501347 | 2026-02-25 | 202602 | 24-107 | 15-000 | Subcontract | AP | V1037 | Mechanical Subcontractor A | Progress claim Feb 2026 | 0 | 107982.77
501358 | 2026-02-25 | 202602 | 24-107 | 16-000 | Subcontract | AP | V1038 | Electrical Subcontractor A | Progress claim Feb 2026 | 0 | 132400.01
501525 | 2026-02-25 | 202602 | 25-110 | 03-200 | Material | AP | V1040 | Reinforcing Steel Supplier B | Invoice 42737 | 0 | 44313.99
501542 | 2026-02-25 | 202602 | 25-110 | 03-300 | Material | AP | V1041 | Cast-in-Place Concrete Supplier A | Invoice 24719 | 0 | 351703.14
501559 | 2026-02-25 | 202602 | 25-110 | 05-100 | Subcontract | AP | V1043 | Structural Steel Subcontractor E | Progress claim Feb 2026 | 0 | 257811.27
501601 | 2026-02-25 | 202602 | 25-110 | 15-000 | Subcontract | AP | V1047 | Mechanical Subcontractor B | Progress claim Feb 2026 | 0 | 18382.24
501609 | 2026-02-25 | 202602 | 25-110 | 16-000 | Subcontract | AP | V1048 | Electrical Subcontractor E | Progress claim Feb 2026 | 0 | 15809.81
501775 | 2026-02-25 | 202602 | 25-112 | 03-300 | Material | AP | V1051 | Cast-in-Place Concrete Supplier F | Invoice 86221 | 0 | 35315.06
501782 | 2026-02-25 | 202602 | 25-112 | 04-200 | Subcontract | AP | V1052 | Masonry Subcontractor D | Progress claim Feb 2026 | 0 | 22180.87
501789 | 2026-02-25 | 202602 | 25-112 | 05-100 | Subcontract | AP | V1053 | Structural Steel Subcontractor F | Progress claim Feb 2026 | 0 | 204958.5
501838 | 2026-02-25 | 202602 | 25-112 | 15-000 | Subcontract | AP | V1057 | Mechanical Subcontractor E | Progress claim Feb 2026 | 0 | 47164.57
501847 | 2026-02-25 | 202602 | 25-112 | 16-000 | Subcontract | AP | V1058 | Electrical Subcontractor G | Progress claim Feb 2026 | 0 | 41337.99
501949 | 2026-02-25 | 202602 | 25-115 | 02-200 | Subcontract | AP | V1059 | Earthwork Subcontractor B | Progress claim Feb 2026 | 0 | 21599.78
502024 | 2026-02-25 | 202602 | 25-115 | 05-100 | Subcontract | AP | V1063 | Structural Steel Subcontractor B | Progress claim Feb 2026 | 0 | 16204.7
502157 | 2026-02-25 | 202602 | 25-118 | 02-200 | Subcontract | AP | V1069 | Earthwork Subcontractor E | Progress claim Feb 2026 | 0 | 184074.15
502336 | 2026-02-25 | 202602 | 25-121 | 02-200 | Subcontract | AP | V1078 | Earthwork Subcontractor A | Progress claim Feb 2026 | 0 | 110700.29
500388 | 2026-02-26 | 202602 | 23-098 | 08-100 | Material | AP | V1007 | Doors Supplier G | Invoice 56850 | 0 | 51298.51
501526 | 2026-02-26 | 202602 | 25-110 | 03-200 | Material | AP | V1040 | Reinforcing Steel Supplier B | Invoice 90627 | 0 | 29862.44
500091 | 2026-02-27 | 202602 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Feb 27 | 168.9 | 15535.11
500365 | 2026-02-27 | 202602 | 23-098 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Feb 27 | 55.3 | 3925.64
500389 | 2026-02-27 | 202602 | 23-098 | 08-100 | Material | AP | V1007 | Doors Supplier G | Invoice 40075 | 0 | 59181.61
500499 | 2026-02-27 | 202602 | 24-101 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Feb 27 | 173.6 | 15970.62
500701 | 2026-02-27 | 202602 | 24-101 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Feb 27 | 244.4 | 17351.07
500828 | 2026-02-27 | 202602 | 24-104 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Feb 27 | 289.6 | 26645.95
500956 | 2026-02-27 | 202602 | 24-104 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Feb 27 | 86.1 | 6368.33
501021 | 2026-02-27 | 202602 | 24-104 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Feb 27 | 59.5 | 4221.18
501135 | 2026-02-27 | 202602 | 24-107 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Feb 27 | 334.3 | 30755.51
501295 | 2026-02-27 | 202602 | 24-107 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Feb 27 | 113.7 | 8070.88
501396 | 2026-02-27 | 202602 | 25-110 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Feb 27 | 451.6 | 41545.27
501442 | 2026-02-27 | 202602 | 25-110 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 65846 | 0 | 21022.18
501500 | 2026-02-27 | 202602 | 25-110 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Feb 27 | 1402.4 | 103779.99
501642 | 2026-02-27 | 202602 | 25-112 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Feb 27 | 129.9 | 11948.51
501687 | 2026-02-27 | 202602 | 25-112 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 13755 | 0 | 10999.19
501746 | 2026-02-27 | 202602 | 25-112 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Feb 27 | 297 | 21980.16
501876 | 2026-02-27 | 202602 | 25-115 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Feb 27 | 173 | 15915.32
501915 | 2026-02-27 | 202602 | 25-115 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 87344 | 0 | 3144.76
501966 | 2026-02-27 | 202602 | 25-115 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Feb 27 | 979.3 | 72468.54
502092 | 2026-02-27 | 202602 | 25-118 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Feb 27 | 130.1 | 11966.55
502171 | 2026-02-27 | 202602 | 25-118 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Feb 27 | 361.8 | 26775.89
502275 | 2026-02-27 | 202602 | 25-121 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Feb 27 | 116.5 | 10717.88
502310 | 2026-02-27 | 202602 | 25-121 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 61604 | 0 | 3026.89
500194 | 2026-02-28 | 202602 | 23-098 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 8433.71
500581 | 2026-02-28 | 202602 | 24-101 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 67728.98
500903 | 2026-02-28 | 202602 | 24-104 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 34436.59
501203 | 2026-02-28 | 202602 | 24-107 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 41294.72
501461 | 2026-02-28 | 202602 | 25-110 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 35970.85
501712 | 2026-02-28 | 202602 | 25-112 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 29265.64
501937 | 2026-02-28 | 202602 | 25-115 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 18675.03
502146 | 2026-02-28 | 202602 | 25-118 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 47162.66
502327 | 2026-02-28 | 202602 | 25-121 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 10093.35
502450 | 2026-03-04 | 202603 | 26-124 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 75507 | 0 | 3286.12
500994 | 2026-03-05 | 202603 | 24-104 | 03-300 | Material | AP | V1022 | Cast-in-Place Concrete Supplier F | Invoice 71633 | 0 | 1407.19
501544 | 2026-03-05 | 202603 | 25-110 | 03-300 | Material | AP | V1041 | Cast-in-Place Concrete Supplier A | Invoice 78387 | 0 | 102227
501920 | 2026-03-05 | 202603 | 25-115 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 60956 | 0 | 6113.77
500092 | 2026-03-06 | 202603 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Mar 06 | 50 | 4599.89
500366 | 2026-03-06 | 202603 | 23-098 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Mar 06 | 34.7 | 2466.7
500500 | 2026-03-06 | 202603 | 24-101 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Mar 06 | 222.3 | 20452.2
500702 | 2026-03-06 | 202603 | 24-101 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Mar 06 | 178.3 | 12656.54
500829 | 2026-03-06 | 202603 | 24-104 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Mar 06 | 643.7 | 59218.17
501022 | 2026-03-06 | 202603 | 24-104 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Mar 06 | 181.3 | 12870.29
501136 | 2026-03-06 | 202603 | 24-107 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Mar 06 | 202.9 | 18669.14
501296 | 2026-03-06 | 202603 | 24-107 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Mar 06 | 258.3 | 18337.04
501397 | 2026-03-06 | 202603 | 25-110 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Mar 06 | 309.6 | 28483.63
501501 | 2026-03-06 | 202603 | 25-110 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Mar 06 | 257 | 19015.97
501643 | 2026-03-06 | 202603 | 25-112 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Mar 06 | 115.9 | 10665.4
501747 | 2026-03-06 | 202603 | 25-112 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Mar 06 | 112.4 | 8314.94
501793 | 2026-03-06 | 202603 | 25-112 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Mar 06 | 34 | 2416.89
501877 | 2026-03-06 | 202603 | 25-115 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Mar 06 | 180.9 | 16644.15
501967 | 2026-03-06 | 202603 | 25-115 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Mar 06 | 1130.7 | 83668.55
502093 | 2026-03-06 | 202603 | 25-118 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Mar 06 | 359.6 | 33078.75
502172 | 2026-03-06 | 202603 | 25-118 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Mar 06 | 338.9 | 25076.47
502276 | 2026-03-06 | 202603 | 25-121 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Mar 06 | 27.1 | 2492.31
502341 | 2026-03-06 | 202603 | 25-121 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Mar 06 | 163.8 | 12121.74
502419 | 2026-03-06 | 202603 | 26-124 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Mar 06 | 56.3 | 5177.08
500996 | 2026-03-07 | 202603 | 24-104 | 03-300 | Material | AP | V1022 | Cast-in-Place Concrete Supplier F | Invoice 21504 | 0 | 2425.29
501918 | 2026-03-07 | 202603 | 25-115 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 66708 | 0 | 10140.58
502009 | 2026-03-07 | 202603 | 25-115 | 03-300 | Material | AP | V1061 | Cast-in-Place Concrete Supplier A | Invoice 30512 | 0 | 202155.85
502129 | 2026-03-09 | 202603 | 25-118 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 28579 | 0 | 8566.19
500556 | 2026-03-10 | 202603 | 24-101 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 32020 | 0 | 9797.92
501690 | 2026-03-11 | 202603 | 25-112 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 38813 | 0 | 8743.49
501776 | 2026-03-11 | 202603 | 25-112 | 03-300 | Material | AP | V1051 | Cast-in-Place Concrete Supplier F | Invoice 94936 | 0 | 51417.3
502130 | 2026-03-11 | 202603 | 25-118 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 33229 | 0 | 25231.34
500995 | 2026-03-12 | 202603 | 24-104 | 03-300 | Material | AP | V1022 | Cast-in-Place Concrete Supplier F | Invoice 61661 | 0 | 1158.8
502389 | 2026-03-12 | 202603 | 25-121 | 03-300 | Material | AP | V1080 | Cast-in-Place Concrete Supplier E | Invoice 92939 | 0 | 21811.07
500093 | 2026-03-13 | 202603 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Mar 13 | 38.9 | 3578.75
500367 | 2026-03-13 | 202603 | 23-098 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Mar 13 | 41.1 | 2920.7
500501 | 2026-03-13 | 202603 | 24-101 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Mar 13 | 170.4 | 15680.3
500703 | 2026-03-13 | 202603 | 24-101 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Mar 13 | 584.8 | 41520.12
500830 | 2026-03-13 | 202603 | 24-104 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Mar 13 | 267.6 | 24617.95
500881 | 2026-03-13 | 202603 | 24-104 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 32529 | 0 | 43670.75
501023 | 2026-03-13 | 202603 | 24-104 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Mar 13 | 254.5 | 18067.31
501137 | 2026-03-13 | 202603 | 24-107 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Mar 13 | 330.2 | 30382.21
501297 | 2026-03-13 | 202603 | 24-107 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Mar 13 | 102.9 | 7308.42
501398 | 2026-03-13 | 202603 | 25-110 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Mar 13 | 443 | 40756.3
501502 | 2026-03-13 | 202603 | 25-110 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Mar 13 | 1145.5 | 84764.54
501644 | 2026-03-13 | 202603 | 25-112 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Mar 13 | 310.4 | 28555.71
501748 | 2026-03-13 | 202603 | 25-112 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Mar 13 | 150.4 | 11131.25
501794 | 2026-03-13 | 202603 | 25-112 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Mar 13 | 59.4 | 4217.41
501878 | 2026-03-13 | 202603 | 25-115 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Mar 13 | 196.1 | 18043.99
501968 | 2026-03-13 | 202603 | 25-115 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Mar 13 | 785.4 | 58119.05
502094 | 2026-03-13 | 202603 | 25-118 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Mar 13 | 198.4 | 18251.08
502173 | 2026-03-13 | 202603 | 25-118 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Mar 13 | 623.1 | 46109.24
502197 | 2026-03-13 | 202603 | 25-118 | 03-200 | Material | AP | V1070 | Reinforcing Steel Supplier C | Invoice 53725 | 0 | 60926.39
502277 | 2026-03-13 | 202603 | 25-121 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Mar 13 | 103.4 | 9516.03
502342 | 2026-03-13 | 202603 | 25-121 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Mar 13 | 131.9 | 9760.87
502420 | 2026-03-13 | 202603 | 26-124 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Mar 13 | 29.4 | 2703.23
502449 | 2026-03-13 | 202603 | 26-124 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 42526 | 0 | 2226.29
500558 | 2026-03-14 | 202603 | 24-101 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 63451 | 0 | 29504.34
501543 | 2026-03-14 | 202603 | 25-110 | 03-300 | Material | AP | V1041 | Cast-in-Place Concrete Supplier A | Invoice 88913 | 0 | 121182.79
501529 | 2026-03-15 | 202603 | 25-110 | 03-200 | Material | AP | V1040 | Reinforcing Steel Supplier B | Invoice 18879 | 0 | 26828.88
501919 | 2026-03-15 | 202603 | 25-115 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 41111 | 0 | 6085.9
501692 | 2026-03-16 | 202603 | 25-112 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 82692 | 0 | 2821.33
502198 | 2026-03-16 | 202603 | 25-118 | 03-200 | Material | AP | V1070 | Reinforcing Steel Supplier C | Invoice 54105 | 0 | 142908.04
502311 | 2026-03-16 | 202603 | 25-121 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 53992 | 0 | 18370.5
500159 | 2026-03-17 | 202603 | 23-098 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 83024 | 0 | 4987.07
501180 | 2026-03-17 | 202603 | 24-107 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 94377 | 0 | 6900.64
501762 | 2026-03-17 | 202603 | 25-112 | 03-200 | Material | AP | V1050 | Reinforcing Steel Supplier A | Invoice 73105 | 0 | 9853.46
502209 | 2026-03-17 | 202603 | 25-118 | 03-300 | Material | AP | V1071 | Cast-in-Place Concrete Supplier A | Invoice 30480 | 0 | 331809.24
500557 | 2026-03-18 | 202603 | 24-101 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 64780 | 0 | 35835.73
500094 | 2026-03-20 | 202603 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Mar 20 | 67 | 6166.82
500368 | 2026-03-20 | 202603 | 23-098 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Mar 20 | 32 | 2268.96
500502 | 2026-03-20 | 202603 | 24-101 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Mar 20 | 262.3 | 24130.06
500704 | 2026-03-20 | 202603 | 24-101 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Mar 20 | 138.4 | 9823.77
500831 | 2026-03-20 | 202603 | 24-104 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Mar 20 | 162.6 | 14958.68
501024 | 2026-03-20 | 202603 | 24-104 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Mar 20 | 129.3 | 9178.46
501138 | 2026-03-20 | 202603 | 24-107 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Mar 20 | 498.8 | 45893.78
501298 | 2026-03-20 | 202603 | 24-107 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Mar 20 | 60.5 | 4292.39
501399 | 2026-03-20 | 202603 | 25-110 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Mar 20 | 282.3 | 25972.65
501503 | 2026-03-20 | 202603 | 25-110 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Mar 20 | 490.4 | 36286.79
501645 | 2026-03-20 | 202603 | 25-112 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Mar 20 | 258.3 | 23759.01
501749 | 2026-03-20 | 202603 | 25-112 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Mar 20 | 54 | 3997.46
501795 | 2026-03-20 | 202603 | 25-112 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Mar 20 | 114.8 | 8151.89
501879 | 2026-03-20 | 202603 | 25-115 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Mar 20 | 164.7 | 15151.84
501969 | 2026-03-20 | 202603 | 25-115 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Mar 20 | 1929.2 | 142757.26
502095 | 2026-03-20 | 202603 | 25-118 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Mar 20 | 64.7 | 5949.95
502174 | 2026-03-20 | 202603 | 25-118 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Mar 20 | 1935.4 | 143220.74
502278 | 2026-03-20 | 202603 | 25-121 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Mar 20 | 53.2 | 4896.71
502343 | 2026-03-20 | 202603 | 25-121 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Mar 20 | 31.5 | 2331.09
502373 | 2026-03-20 | 202603 | 25-121 | 03-200 | Material | AP | V1079 | Reinforcing Steel Supplier C | Invoice 52538 | 0 | 11965.74
502421 | 2026-03-20 | 202603 | 26-124 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Mar 20 | 37.9 | 3487.72
500390 | 2026-03-21 | 202603 | 23-098 | 08-100 | Material | AP | V1007 | Doors Supplier G | Invoice 35907 | 0 | 112016.01
501443 | 2026-03-22 | 202603 | 25-110 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 24390 | 0 | 56476.19
501528 | 2026-03-22 | 202603 | 25-110 | 03-200 | Material | AP | V1040 | Reinforcing Steel Supplier B | Invoice 65688 | 0 | 81411.06
501691 | 2026-03-23 | 202603 | 25-112 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 34606 | 0 | 17091.71
502371 | 2026-03-23 | 202603 | 25-121 | 03-200 | Material | AP | V1079 | Reinforcing Steel Supplier C | Invoice 25953 | 0 | 8055.29
501545 | 2026-03-24 | 202603 | 25-110 | 03-300 | Material | AP | V1041 | Cast-in-Place Concrete Supplier A | Invoice 92603 | 0 | 87466.36
502199 | 2026-03-24 | 202603 | 25-118 | 03-200 | Material | AP | V1070 | Reinforcing Steel Supplier C | Invoice 84560 | 0 | 39016.68
500158 | 2026-03-25 | 202603 | 23-098 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 51789 | 0 | 5781.16
500405 | 2026-03-25 | 202603 | 23-098 | 09-200 | Subcontract | AP | V1008 | Drywall Subcontractor B | Progress claim Mar 2026 | 0 | 202945.99
500423 | 2026-03-25 | 202603 | 23-098 | 15-000 | Subcontract | AP | V1009 | Mechanical Subcontractor B | Progress claim Mar 2026 | 0 | 158802.18
500442 | 2026-03-25 | 202603 | 23-098 | 16-000 | Subcontract | AP | V1010 | Electrical Subcontractor C | Progress claim Mar 2026 | 0 | 91089.54
500735 | 2026-03-25 | 202603 | 24-101 | 07-200 | Subcontract | AP | V1015 | Roofing Subcontractor A | Progress claim Mar 2026 | 0 | 353179.63
500765 | 2026-03-25 | 202603 | 24-101 | 15-000 | Subcontract | AP | V1018 | Mechanical Subcontractor F | Progress claim Mar 2026 | 0 | 322462.6
500778 | 2026-03-25 | 202603 | 24-101 | 16-000 | Subcontract | AP | V1019 | Electrical Subcontractor G | Progress claim Mar 2026 | 0 | 278478.37
501002 | 2026-03-25 | 202603 | 24-104 | 04-200 | Subcontract | AP | V1023 | Masonry Subcontractor D | Progress claim Mar 2026 | 0 | 258402.25
501011 | 2026-03-25 | 202603 | 24-104 | 05-100 | Subcontract | AP | V1024 | Structural Steel Subcontractor A | Progress claim Mar 2026 | 0 | 153788.31
501053 | 2026-03-25 | 202603 | 24-104 | 07-200 | Subcontract | AP | V1025 | Roofing Subcontractor F | Progress claim Mar 2026 | 0 | 146296.25
501079 | 2026-03-25 | 202603 | 24-104 | 15-000 | Subcontract | AP | V1028 | Mechanical Subcontractor B | Progress claim Mar 2026 | 0 | 161794.73
501090 | 2026-03-25 | 202603 | 24-104 | 16-000 | Subcontract | AP | V1029 | Electrical Subcontractor F | Progress claim Mar 2026 | 0 | 160335.66
501282 | 2026-03-25 | 202603 | 24-107 | 05-100 | Subcontract | AP | V1033 | Structural Steel Subcontractor D | Progress claim Mar 2026 | 0 | 25613.58
501320 | 2026-03-25 | 202603 | 24-107 | 07-200 | Subcontract | AP | V1034 | Roofing Subcontractor A | Progress claim Mar 2026 | 0 | 179153
501348 | 2026-03-25 | 202603 | 24-107 | 15-000 | Subcontract | AP | V1037 | Mechanical Subcontractor A | Progress claim Mar 2026 | 0 | 145033.74
501359 | 2026-03-25 | 202603 | 24-107 | 16-000 | Subcontract | AP | V1038 | Electrical Subcontractor A | Progress claim Mar 2026 | 0 | 182051.29
501551 | 2026-03-25 | 202603 | 25-110 | 04-200 | Subcontract | AP | V1042 | Masonry Subcontractor G | Progress claim Mar 2026 | 0 | 6916.01
501560 | 2026-03-25 | 202603 | 25-110 | 05-100 | Subcontract | AP | V1043 | Structural Steel Subcontractor E | Progress claim Mar 2026 | 0 | 502652.96
501602 | 2026-03-25 | 202603 | 25-110 | 15-000 | Subcontract | AP | V1047 | Mechanical Subcontractor B | Progress claim Mar 2026 | 0 | 83553.36
501610 | 2026-03-25 | 202603 | 25-110 | 16-000 | Subcontract | AP | V1048 | Electrical Subcontractor E | Progress claim Mar 2026 | 0 | 67278.67
501783 | 2026-03-25 | 202603 | 25-112 | 04-200 | Subcontract | AP | V1052 | Masonry Subcontractor D | Progress claim Mar 2026 | 0 | 104469.02
501790 | 2026-03-25 | 202603 | 25-112 | 05-100 | Subcontract | AP | V1053 | Structural Steel Subcontractor F | Progress claim Mar 2026 | 0 | 240921.85
501819 | 2026-03-25 | 202603 | 25-112 | 07-200 | Subcontract | AP | V1054 | Roofing Subcontractor A | Progress claim Mar 2026 | 0 | 3395.56
501839 | 2026-03-25 | 202603 | 25-112 | 15-000 | Subcontract | AP | V1057 | Mechanical Subcontractor E | Progress claim Mar 2026 | 0 | 96043.18
501848 | 2026-03-25 | 202603 | 25-112 | 16-000 | Subcontract | AP | V1058 | Electrical Subcontractor G | Progress claim Mar 2026 | 0 | 65651.08
502025 | 2026-03-25 | 202603 | 25-115 | 05-100 | Subcontract | AP | V1063 | Structural Steel Subcontractor B | Progress claim Mar 2026 | 0 | 97280.91
502062 | 2026-03-25 | 202603 | 25-115 | 15-000 | Subcontract | AP | V1067 | Mechanical Subcontractor C | Progress claim Mar 2026 | 0 | 21954.27
502069 | 2026-03-25 | 202603 | 25-115 | 16-000 | Subcontract | AP | V1068 | Electrical Subcontractor D | Progress claim Mar 2026 | 0 | 10735.7
502158 | 2026-03-25 | 202603 | 25-118 | 02-200 | Subcontract | AP | V1069 | Earthwork Subcontractor E | Progress claim Mar 2026 | 0 | 9966.71
502216 | 2026-03-25 | 202603 | 25-118 | 05-100 | Subcontract | AP | V1072 | Structural Steel Subcontractor D | Progress claim Mar 2026 | 0 | 241056.26
502253 | 2026-03-25 | 202603 | 25-118 | 15-000 | Subcontract | AP | V1076 | Mechanical Subcontractor E | Progress claim Mar 2026 | 0 | 8096.53
502260 | 2026-03-25 | 202603 | 25-118 | 16-000 | Subcontract | AP | V1077 | Electrical Subcontractor A | Progress claim Mar 2026 | 0 | 6192.82
502337 | 2026-03-25 | 202603 | 25-121 | 02-200 | Subcontract | AP | V1078 | Earthwork Subcontractor A | Progress claim Mar 2026 | 0 | 224608.86
502372 | 2026-03-25 | 202603 | 25-121 | 03-200 | Material | AP | V1079 | Reinforcing Steel Supplier C | Invoice 47316 | 0 | 8106.53
502472 | 2026-03-25 | 202603 | 26-124 | 02-200 | Subcontract | AP | V1085 | Earthwork Subcontractor E | Progress claim Mar 2026 | 0 | 129778.99
500391 | 2026-03-26 | 202603 | 23-098 | 08-100 | Material | AP | V1007 | Doors Supplier G | Invoice 89703 | 0 | 80485.19
501178 | 2026-03-26 | 202603 | 24-107 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 56064 | 0 | 6058.74
501179 | 2026-03-26 | 202603 | 24-107 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 58805 | 0 | 8674.93
500095 | 2026-03-27 | 202603 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Mar 27 | 152.8 | 14058.21
500369 | 2026-03-27 | 202603 | 23-098 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Mar 27 | 26.8 | 1904.43
500503 | 2026-03-27 | 202603 | 24-101 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Mar 27 | 606.2 | 55771.08
500705 | 2026-03-27 | 202603 | 24-101 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Mar 27 | 218.1 | 15487.63
500832 | 2026-03-27 | 202603 | 24-104 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Mar 27 | 279.8 | 25739.93
501025 | 2026-03-27 | 202603 | 24-104 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Mar 27 | 230.9 | 16396.62
501139 | 2026-03-27 | 202603 | 24-107 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Mar 27 | 155.8 | 14335.91
501299 | 2026-03-27 | 202603 | 24-107 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Mar 27 | 61.4 | 4359.45
501400 | 2026-03-27 | 202603 | 25-110 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Mar 27 | 364.6 | 33547.43
501504 | 2026-03-27 | 202603 | 25-110 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Mar 27 | 485 | 35888.94
501646 | 2026-03-27 | 202603 | 25-112 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Mar 27 | 311.1 | 28618.89
501750 | 2026-03-27 | 202603 | 25-112 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Mar 27 | 61.4 | 4546.59
501796 | 2026-03-27 | 202603 | 25-112 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Mar 27 | 59 | 4186.85
501880 | 2026-03-27 | 202603 | 25-115 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Mar 27 | 147.6 | 13577.4
501970 | 2026-03-27 | 202603 | 25-115 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Mar 27 | 606.2 | 44859.35
501993 | 2026-03-27 | 202603 | 25-115 | 03-200 | Material | AP | V1060 | Reinforcing Steel Supplier B | Invoice 88084 | 0 | 103186.98
502096 | 2026-03-27 | 202603 | 25-118 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Mar 27 | 257.3 | 23667.64
502175 | 2026-03-27 | 202603 | 25-118 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Mar 27 | 708.6 | 52438.74
502279 | 2026-03-27 | 202603 | 25-121 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Mar 27 | 155.9 | 14339.16
502344 | 2026-03-27 | 202603 | 25-121 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Mar 27 | 378.4 | 27999.23
502422 | 2026-03-27 | 202603 | 26-124 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Mar 27 | 54.5 | 5013.03
500195 | 2026-03-31 | 202603 | 23-098 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 6900.01
500582 | 2026-03-31 | 202603 | 24-101 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 59296.82
500904 | 2026-03-31 | 202603 | 24-104 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 33303.98
501204 | 2026-03-31 | 202603 | 24-107 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 39548.78
501462 | 2026-03-31 | 202603 | 25-110 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 51557.58
501713 | 2026-03-31 | 202603 | 25-112 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 35988.19
501938 | 2026-03-31 | 202603 | 25-115 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 24738.69
502147 | 2026-03-31 | 202603 | 25-118 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 61446.71
502328 | 2026-03-31 | 202603 | 25-121 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 19110.93
502465 | 2026-03-31 | 202603 | 26-124 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 7260.68
500096 | 2026-04-03 | 202604 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Apr 03 | 53.3 | 4902.81
500504 | 2026-04-03 | 202604 | 24-101 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Apr 03 | 261.9 | 24095.78
500706 | 2026-04-03 | 202604 | 24-101 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Apr 03 | 303.7 | 21562.64
500833 | 2026-04-03 | 202604 | 24-104 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Apr 03 | 453.1 | 41685.3
501026 | 2026-04-03 | 202604 | 24-104 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Apr 03 | 423.4 | 30059.61
501140 | 2026-04-03 | 202604 | 24-107 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Apr 03 | 284.7 | 26189.28
501300 | 2026-04-03 | 202604 | 24-107 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Apr 03 | 145.1 | 10304.88
501401 | 2026-04-03 | 202604 | 25-110 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Apr 03 | 444.4 | 40885.22
501505 | 2026-04-03 | 202604 | 25-110 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Apr 03 | 474.3 | 35099.69
501567 | 2026-04-03 | 202604 | 25-110 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Apr 03 | 15.9 | 1130.53
501647 | 2026-04-03 | 202604 | 25-112 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Apr 03 | 227.8 | 20953.89
501797 | 2026-04-03 | 202604 | 25-112 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Apr 03 | 256.6 | 18221.43
501881 | 2026-04-03 | 202604 | 25-115 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Apr 03 | 237.2 | 21825.38
501971 | 2026-04-03 | 202604 | 25-115 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Apr 03 | 574.1 | 42483.23
502010 | 2026-04-03 | 202604 | 25-115 | 03-300 | Material | AP | V1061 | Cast-in-Place Concrete Supplier A | Invoice 70054 | 0 | 39116.11
502097 | 2026-04-03 | 202604 | 25-118 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Apr 03 | 480 | 44156.19
502176 | 2026-04-03 | 202604 | 25-118 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Apr 03 | 590.3 | 43679.47
502280 | 2026-04-03 | 202604 | 25-121 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Apr 03 | 125.8 | 11569.08
502345 | 2026-04-03 | 202604 | 25-121 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Apr 03 | 186.9 | 13830.27
502423 | 2026-04-03 | 202604 | 26-124 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Apr 03 | 38.3 | 3527.01
502477 | 2026-04-03 | 202604 | 26-124 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Apr 03 | 97.1 | 7188.59
501994 | 2026-04-04 | 202604 | 25-115 | 03-200 | Material | AP | V1060 | Reinforcing Steel Supplier B | Invoice 24562 | 0 | 51664.93
502210 | 2026-04-04 | 202604 | 25-118 | 03-300 | Material | AP | V1071 | Cast-in-Place Concrete Supplier A | Invoice 15320 | 0 | 348060.83
501922 | 2026-04-05 | 202604 | 25-115 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 30924 | 0 | 11892.39
502451 | 2026-04-05 | 202604 | 26-124 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 11175 | 0 | 3688.04
502518 | 2026-04-05 | 202604 | 26-124 | 03-300 | Material | AP | V1087 | Cast-in-Place Concrete Supplier B | Invoice 87114 | 0 | 4431.73
500160 | 2026-04-06 | 202604 | 23-098 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 45581 | 0 | 3820.32
501530 | 2026-04-09 | 202604 | 25-110 | 03-200 | Material | AP | V1040 | Reinforcing Steel Supplier B | Invoice 90015 | 0 | 49297.45
502504 | 2026-04-09 | 202604 | 26-124 | 03-200 | Material | AP | V1086 | Reinforcing Steel Supplier A | Invoice 20036 | 0 | 20125.04
500097 | 2026-04-10 | 202604 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Apr 10 | 48.5 | 4465.52
500392 | 2026-04-10 | 202604 | 23-098 | 08-100 | Material | AP | V1007 | Doors Supplier G | Invoice 31749 | 0 | 47144.33
500505 | 2026-04-10 | 202604 | 24-101 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Apr 10 | 283.5 | 26079.39
500707 | 2026-04-10 | 202604 | 24-101 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Apr 10 | 112.1 | 7962.36
500834 | 2026-04-10 | 202604 | 24-104 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Apr 10 | 233.1 | 21446
501027 | 2026-04-10 | 202604 | 24-104 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Apr 10 | 243.7 | 17304.56
501141 | 2026-04-10 | 202604 | 24-107 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Apr 10 | 211.2 | 19431.21
501301 | 2026-04-10 | 202604 | 24-107 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Apr 10 | 182.1 | 12929.02
501402 | 2026-04-10 | 202604 | 25-110 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Apr 10 | 310.6 | 28577.31
501506 | 2026-04-10 | 202604 | 25-110 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Apr 10 | 559.8 | 41423.49
501568 | 2026-04-10 | 202604 | 25-110 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Apr 10 | 9.5 | 671.71
501648 | 2026-04-10 | 202604 | 25-112 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Apr 10 | 263.5 | 24238.16
501798 | 2026-04-10 | 202604 | 25-112 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Apr 10 | 194.5 | 13807.81
501882 | 2026-04-10 | 202604 | 25-115 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Apr 10 | 82.1 | 7557.73
501972 | 2026-04-10 | 202604 | 25-115 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Apr 10 | 699.1 | 51731.83
502098 | 2026-04-10 | 202604 | 25-118 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Apr 10 | 314 | 28885.68
502177 | 2026-04-10 | 202604 | 25-118 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Apr 10 | 464.3 | 34360.07
502281 | 2026-04-10 | 202604 | 25-121 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Apr 10 | 199.3 | 18337.4
502346 | 2026-04-10 | 202604 | 25-121 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Apr 10 | 332 | 24565.28
502375 | 2026-04-10 | 202604 | 25-121 | 03-200 | Material | AP | V1079 | Reinforcing Steel Supplier C | Invoice 63784 | 0 | 16918.11
502376 | 2026-04-10 | 202604 | 25-121 | 03-200 | Material | AP | V1079 | Reinforcing Steel Supplier C | Invoice 95966 | 0 | 30920.26
502390 | 2026-04-10 | 202604 | 25-121 | 03-300 | Material | AP | V1080 | Cast-in-Place Concrete Supplier E | Invoice 19841 | 0 | 22300.67
502391 | 2026-04-10 | 202604 | 25-121 | 03-300 | Material | AP | V1080 | Cast-in-Place Concrete Supplier E | Invoice 62872 | 0 | 60233.19
502424 | 2026-04-10 | 202604 | 26-124 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Apr 10 | 59.3 | 5454.48
502478 | 2026-04-10 | 202604 | 26-124 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Apr 10 | 106.9 | 7907.89
500739 | 2026-04-11 | 202604 | 24-101 | 08-100 | Material | AP | V1016 | Doors Supplier F | Invoice 64440 | 0 | 21127.01
501181 | 2026-04-11 | 202604 | 24-107 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 48095 | 0 | 17977.9
502374 | 2026-04-11 | 202604 | 25-121 | 03-200 | Material | AP | V1079 | Reinforcing Steel Supplier C | Invoice 22488 | 0 | 31171.56
501445 | 2026-04-12 | 202604 | 25-110 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 51232 | 0 | 10380.03
500162 | 2026-04-13 | 202604 | 23-098 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 70390 | 0 | 2237.35
500393 | 2026-04-15 | 202604 | 23-098 | 08-100 | Material | AP | V1007 | Doors Supplier G | Invoice 99119 | 0 | 52262.62
501921 | 2026-04-15 | 202604 | 25-115 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 16722 | 0 | 10734.4
501777 | 2026-04-16 | 202604 | 25-112 | 03-300 | Material | AP | V1051 | Cast-in-Place Concrete Supplier F | Invoice 10884 | 0 | 4463.23
501778 | 2026-04-16 | 202604 | 25-112 | 03-300 | Material | AP | V1051 | Cast-in-Place Concrete Supplier F | Invoice 80423 | 0 | 2825.81
502131 | 2026-04-16 | 202604 | 25-118 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 45695 | 0 | 18718.91
502452 | 2026-04-16 | 202604 | 26-124 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 24981 | 0 | 1954.3
500098 | 2026-04-17 | 202604 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Apr 17 | 114.6 | 10539.32
500506 | 2026-04-17 | 202604 | 24-101 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Apr 17 | 149.8 | 13784.22
500708 | 2026-04-17 | 202604 | 24-101 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Apr 17 | 152.7 | 10842.2
500835 | 2026-04-17 | 202604 | 24-104 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Apr 17 | 388.7 | 35759.37
501028 | 2026-04-17 | 202604 | 24-104 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Apr 17 | 549 | 38975.92
501142 | 2026-04-17 | 202604 | 24-107 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Apr 17 | 223.2 | 20535.88
501302 | 2026-04-17 | 202604 | 24-107 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Apr 17 | 181.4 | 12876.76
501324 | 2026-04-17 | 202604 | 24-107 | 08-100 | Material | AP | V1035 | Doors Supplier D | Invoice 95912 | 0 | 5358.14
501403 | 2026-04-17 | 202604 | 25-110 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Apr 17 | 195.4 | 17975.54
501507 | 2026-04-17 | 202604 | 25-110 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Apr 17 | 180.5 | 13355.12
501569 | 2026-04-17 | 202604 | 25-110 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Apr 17 | 11.9 | 844.12
501649 | 2026-04-17 | 202604 | 25-112 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Apr 17 | 359.3 | 33057.02
501799 | 2026-04-17 | 202604 | 25-112 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Apr 17 | 73 | 5185.29
501883 | 2026-04-17 | 202604 | 25-115 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Apr 17 | 270.1 | 24850.71
501973 | 2026-04-17 | 202604 | 25-115 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Apr 17 | 934.1 | 69119.76
502099 | 2026-04-17 | 202604 | 25-118 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Apr 17 | 205.4 | 18894.77
502178 | 2026-04-17 | 202604 | 25-118 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Apr 17 | 1110.5 | 82179.69
502201 | 2026-04-17 | 202604 | 25-118 | 03-200 | Material | AP | V1070 | Reinforcing Steel Supplier C | Invoice 56973 | 0 | 31198.92
502282 | 2026-04-17 | 202604 | 25-121 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Apr 17 | 42.8 | 3939.98
502347 | 2026-04-17 | 202604 | 25-121 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Apr 17 | 341.8 | 25294.15
502425 | 2026-04-17 | 202604 | 26-124 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Apr 17 | 95.5 | 8788.99
502479 | 2026-04-17 | 202604 | 26-124 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Apr 17 | 72.5 | 5362.82
501326 | 2026-04-18 | 202604 | 24-107 | 08-100 | Material | AP | V1035 | Doors Supplier D | Invoice 38648 | 0 | 681.59
501693 | 2026-04-19 | 202604 | 25-112 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 95509 | 0 | 15297.83
501546 | 2026-04-20 | 202604 | 25-110 | 03-300 | Material | AP | V1041 | Cast-in-Place Concrete Supplier A | Invoice 71087 | 0 | 90225.38
502312 | 2026-04-20 | 202604 | 25-121 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 48314 | 0 | 21816.01
502519 | 2026-04-20 | 202604 | 26-124 | 03-300 | Material | AP | V1087 | Cast-in-Place Concrete Supplier B | Invoice 32021 | 0 | 10424.97
501325 | 2026-04-21 | 202604 | 24-107 | 08-100 | Material | AP | V1035 | Doors Supplier D | Invoice 46279 | 0 | 1655.29
502132 | 2026-04-21 | 202604 | 25-118 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 11856 | 0 | 17275.81
501779 | 2026-04-22 | 202604 | 25-112 | 03-300 | Material | AP | V1051 | Cast-in-Place Concrete Supplier F | Invoice 51946 | 0 | 2711.96
501444 | 2026-04-23 | 202604 | 25-110 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 35855 | 0 | 32770.31
502011 | 2026-04-23 | 202604 | 25-115 | 03-300 | Material | AP | V1061 | Cast-in-Place Concrete Supplier A | Invoice 84883 | 0 | 32830.39
500099 | 2026-04-24 | 202604 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Apr 24 | 52.8 | 4857.48
500507 | 2026-04-24 | 202604 | 24-101 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Apr 24 | 362 | 33304.68
500709 | 2026-04-24 | 202604 | 24-101 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Apr 24 | 441.3 | 31334.71
500836 | 2026-04-24 | 202604 | 24-104 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Apr 24 | 98.5 | 9058.12
501029 | 2026-04-24 | 202604 | 24-104 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Apr 24 | 289.9 | 20580.52
501143 | 2026-04-24 | 202604 | 24-107 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Apr 24 | 205.2 | 18881.84
501303 | 2026-04-24 | 202604 | 24-107 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Apr 24 | 151.2 | 10738.3
501404 | 2026-04-24 | 202604 | 25-110 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Apr 24 | 503.8 | 46346.36
501508 | 2026-04-24 | 202604 | 25-110 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Apr 24 | 118.8 | 8791.34
501547 | 2026-04-24 | 202604 | 25-110 | 03-300 | Material | AP | V1041 | Cast-in-Place Concrete Supplier A | Invoice 46494 | 0 | 87439.96
501570 | 2026-04-24 | 202604 | 25-110 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Apr 24 | 12.6 | 896.28
501650 | 2026-04-24 | 202604 | 25-112 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Apr 24 | 198.1 | 18225.03
501800 | 2026-04-24 | 202604 | 25-112 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Apr 24 | 205.4 | 14585.61
501884 | 2026-04-24 | 202604 | 25-115 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Apr 24 | 179 | 16472.57
501974 | 2026-04-24 | 202604 | 25-115 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Apr 24 | 504.1 | 37302.44
502012 | 2026-04-24 | 202604 | 25-115 | 03-300 | Material | AP | V1061 | Cast-in-Place Concrete Supplier A | Invoice 23611 | 0 | 79097.91
502100 | 2026-04-24 | 202604 | 25-118 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Apr 24 | 76.5 | 7034.45
502179 | 2026-04-24 | 202604 | 25-118 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Apr 24 | 401.8 | 29736.51
502283 | 2026-04-24 | 202604 | 25-121 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Apr 24 | 82 | 7547.96
502348 | 2026-04-24 | 202604 | 25-121 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Apr 24 | 228.2 | 16883.56
502426 | 2026-04-24 | 202604 | 26-124 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Apr 24 | 57.9 | 5323.1
502453 | 2026-04-24 | 202604 | 26-124 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 70063 | 0 | 3044.83
502480 | 2026-04-24 | 202604 | 26-124 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Apr 24 | 42.1 | 3116.03
502503 | 2026-04-24 | 202604 | 26-124 | 03-200 | Material | AP | V1086 | Reinforcing Steel Supplier A | Invoice 96314 | 0 | 17258.48
500161 | 2026-04-25 | 202604 | 23-098 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 46344 | 0 | 4820.95
500406 | 2026-04-25 | 202604 | 23-098 | 09-200 | Subcontract | AP | V1008 | Drywall Subcontractor B | Progress claim Apr 2026 | 0 | 169161.44
500424 | 2026-04-25 | 202604 | 23-098 | 15-000 | Subcontract | AP | V1009 | Mechanical Subcontractor B | Progress claim Apr 2026 | 0 | 118664.01
500443 | 2026-04-25 | 202604 | 23-098 | 16-000 | Subcontract | AP | V1010 | Electrical Subcontractor C | Progress claim Apr 2026 | 0 | 59941.98
500736 | 2026-04-25 | 202604 | 24-101 | 07-200 | Subcontract | AP | V1015 | Roofing Subcontractor A | Progress claim Apr 2026 | 0 | 251147.88
500753 | 2026-04-25 | 202604 | 24-101 | 09-200 | Subcontract | AP | V1017 | Drywall Subcontractor B | Progress claim Apr 2026 | 0 | 35635.65
500766 | 2026-04-25 | 202604 | 24-101 | 15-000 | Subcontract | AP | V1018 | Mechanical Subcontractor F | Progress claim Apr 2026 | 0 | 340832.37
500779 | 2026-04-25 | 202604 | 24-101 | 16-000 | Subcontract | AP | V1019 | Electrical Subcontractor G | Progress claim Apr 2026 | 0 | 337528.75
500882 | 2026-04-25 | 202604 | 24-104 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 26309 | 0 | 42166.74
501003 | 2026-04-25 | 202604 | 24-104 | 04-200 | Subcontract | AP | V1023 | Masonry Subcontractor D | Progress claim Apr 2026 | 0 | 225622.55
501012 | 2026-04-25 | 202604 | 24-104 | 05-100 | Subcontract | AP | V1024 | Structural Steel Subcontractor A | Progress claim Apr 2026 | 0 | 42342.87
501054 | 2026-04-25 | 202604 | 24-104 | 07-200 | Subcontract | AP | V1025 | Roofing Subcontractor F | Progress claim Apr 2026 | 0 | 320455.65
501080 | 2026-04-25 | 202604 | 24-104 | 15-000 | Subcontract | AP | V1028 | Mechanical Subcontractor B | Progress claim Apr 2026 | 0 | 250062.02
501091 | 2026-04-25 | 202604 | 24-104 | 16-000 | Subcontract | AP | V1029 | Electrical Subcontractor F | Progress claim Apr 2026 | 0 | 203392.66
501321 | 2026-04-25 | 202604 | 24-107 | 07-200 | Subcontract | AP | V1034 | Roofing Subcontractor A | Progress claim Apr 2026 | 0 | 164928.79
501338 | 2026-04-25 | 202604 | 24-107 | 09-200 | Subcontract | AP | V1036 | Drywall Subcontractor F | Progress claim Apr 2026 | 0 | 15678.81
501349 | 2026-04-25 | 202604 | 24-107 | 15-000 | Subcontract | AP | V1037 | Mechanical Subcontractor A | Progress claim Apr 2026 | 0 | 181833.03
501360 | 2026-04-25 | 202604 | 24-107 | 16-000 | Subcontract | AP | V1038 | Electrical Subcontractor A | Progress claim Apr 2026 | 0 | 193488.83
501446 | 2026-04-25 | 202604 | 25-110 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 21733 | 0 | 21969.86
501552 | 2026-04-25 | 202604 | 25-110 | 04-200 | Subcontract | AP | V1042 | Masonry Subcontractor G | Progress claim Apr 2026 | 0 | 48913.45
501561 | 2026-04-25 | 202604 | 25-110 | 05-100 | Subcontract | AP | V1043 | Structural Steel Subcontractor E | Progress claim Apr 2026 | 0 | 799283.13
501603 | 2026-04-25 | 202604 | 25-110 | 15-000 | Subcontract | AP | V1047 | Mechanical Subcontractor B | Progress claim Apr 2026 | 0 | 115303.38
501611 | 2026-04-25 | 202604 | 25-110 | 16-000 | Subcontract | AP | V1048 | Electrical Subcontractor E | Progress claim Apr 2026 | 0 | 75916.95
501694 | 2026-04-25 | 202604 | 25-112 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 62241 | 0 | 9322.12
501784 | 2026-04-25 | 202604 | 25-112 | 04-200 | Subcontract | AP | V1052 | Masonry Subcontractor D | Progress claim Apr 2026 | 0 | 203056.67
501791 | 2026-04-25 | 202604 | 25-112 | 05-100 | Subcontract | AP | V1053 | Structural Steel Subcontractor F | Progress claim Apr 2026 | 0 | 131171.51
501820 | 2026-04-25 | 202604 | 25-112 | 07-200 | Subcontract | AP | V1054 | Roofing Subcontractor A | Progress claim Apr 2026 | 0 | 74507.8
501840 | 2026-04-25 | 202604 | 25-112 | 15-000 | Subcontract | AP | V1057 | Mechanical Subcontractor E | Progress claim Apr 2026 | 0 | 125125.85
501849 | 2026-04-25 | 202604 | 25-112 | 16-000 | Subcontract | AP | V1058 | Electrical Subcontractor G | Progress claim Apr 2026 | 0 | 107151.54
502018 | 2026-04-25 | 202604 | 25-115 | 04-200 | Subcontract | AP | V1062 | Masonry Subcontractor G | Progress claim Apr 2026 | 0 | 32073.66
502026 | 2026-04-25 | 202604 | 25-115 | 05-100 | Subcontract | AP | V1063 | Structural Steel Subcontractor B | Progress claim Apr 2026 | 0 | 198202.56
502063 | 2026-04-25 | 202604 | 25-115 | 15-000 | Subcontract | AP | V1067 | Mechanical Subcontractor C | Progress claim Apr 2026 | 0 | 61910.88
502070 | 2026-04-25 | 202604 | 25-115 | 16-000 | Subcontract | AP | V1068 | Electrical Subcontractor D | Progress claim Apr 2026 | 0 | 35998.32
502200 | 2026-04-25 | 202604 | 25-118 | 03-200 | Material | AP | V1070 | Reinforcing Steel Supplier C | Invoice 91118 | 0 | 130807.47
502217 | 2026-04-25 | 202604 | 25-118 | 05-100 | Subcontract | AP | V1072 | Structural Steel Subcontractor D | Progress claim Apr 2026 | 0 | 690799.72
502254 | 2026-04-25 | 202604 | 25-118 | 15-000 | Subcontract | AP | V1076 | Mechanical Subcontractor E | Progress claim Apr 2026 | 0 | 78330.28
502261 | 2026-04-25 | 202604 | 25-118 | 16-000 | Subcontract | AP | V1077 | Electrical Subcontractor A | Progress claim Apr 2026 | 0 | 58221.01
502338 | 2026-04-25 | 202604 | 25-121 | 02-200 | Subcontract | AP | V1078 | Earthwork Subcontractor A | Progress claim Apr 2026 | 0 | 208226.27
502473 | 2026-04-25 | 202604 | 26-124 | 02-200 | Subcontract | AP | V1085 | Earthwork Subcontractor E | Progress claim Apr 2026 | 0 | 299145.81
500740 | 2026-04-26 | 202604 | 24-101 | 08-100 | Material | AP | V1016 | Doors Supplier F | Invoice 96988 | 0 | 1673.1
501923 | 2026-04-26 | 202604 | 25-115 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 98791 | 0 | 10136
500559 | 2026-04-27 | 202604 | 24-101 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 10993 | 0 | 56383.76
500196 | 2026-04-30 | 202604 | 23-098 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 4953.67
500583 | 2026-04-30 | 202604 | 24-101 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 42320.84
500905 | 2026-04-30 | 202604 | 24-104 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 33735.15
501205 | 2026-04-30 | 202604 | 24-107 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 32232.19
501463 | 2026-04-30 | 202604 | 25-110 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 47979.93
501714 | 2026-04-30 | 202604 | 25-112 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 40315.81
501939 | 2026-04-30 | 202604 | 25-115 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 32986.03
502148 | 2026-04-30 | 202604 | 25-118 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 82486.16
502329 | 2026-04-30 | 202604 | 25-121 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 21331.06
502466 | 2026-04-30 | 202604 | 26-124 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 18310.09
500100 | 2026-05-01 | 202605 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e May 01 | 25.1 | 2312.8
500508 | 2026-05-01 | 202605 | 24-101 | 01-100 | Labour | PR |  | Payroll | Payroll w/e May 01 | 206 | 18950.18
500710 | 2026-05-01 | 202605 | 24-101 | 06-100 | Labour | PR |  | Payroll | Payroll w/e May 01 | 67.3 | 4778.65
500837 | 2026-05-01 | 202605 | 24-104 | 01-100 | Labour | PR |  | Payroll | Payroll w/e May 01 | 260.3 | 23943.39
501030 | 2026-05-01 | 202605 | 24-104 | 06-100 | Labour | PR |  | Payroll | Payroll w/e May 01 | 84.5 | 5998.75
501144 | 2026-05-01 | 202605 | 24-107 | 01-100 | Labour | PR |  | Payroll | Payroll w/e May 01 | 124.1 | 11419.99
501304 | 2026-05-01 | 202605 | 24-107 | 06-100 | Labour | PR |  | Payroll | Payroll w/e May 01 | 53.1 | 3768.08
501405 | 2026-05-01 | 202605 | 25-110 | 01-100 | Labour | PR |  | Payroll | Payroll w/e May 01 | 296 | 27232.02
501509 | 2026-05-01 | 202605 | 25-110 | 03-100 | Labour | PR |  | Payroll | Payroll w/e May 01 | 126.7 | 9377.94
501571 | 2026-05-01 | 202605 | 25-110 | 06-100 | Labour | PR |  | Payroll | Payroll w/e May 01 | 103 | 7315.14
501651 | 2026-05-01 | 202605 | 25-112 | 01-100 | Labour | PR |  | Payroll | Payroll w/e May 01 | 155.3 | 14290.45
501801 | 2026-05-01 | 202605 | 25-112 | 06-100 | Labour | PR |  | Payroll | Payroll w/e May 01 | 171.4 | 12170.18
501885 | 2026-05-01 | 202605 | 25-115 | 01-100 | Labour | PR |  | Payroll | Payroll w/e May 01 | 182.6 | 16801.04
501975 | 2026-05-01 | 202605 | 25-115 | 03-100 | Labour | PR |  | Payroll | Payroll w/e May 01 | 256 | 18943.45
502030 | 2026-05-01 | 202605 | 25-115 | 06-100 | Labour | PR |  | Payroll | Payroll w/e May 01 | 30 | 2130.7
502101 | 2026-05-01 | 202605 | 25-118 | 01-100 | Labour | PR |  | Payroll | Payroll w/e May 01 | 207.6 | 19102.2
502180 | 2026-05-01 | 202605 | 25-118 | 03-100 | Labour | PR |  | Payroll | Payroll w/e May 01 | 289.2 | 21402.22
502222 | 2026-05-01 | 202605 | 25-118 | 06-100 | Labour | PR |  | Payroll | Payroll w/e May 01 | 22.2 | 1574.93
502284 | 2026-05-01 | 202605 | 25-121 | 01-100 | Labour | PR |  | Payroll | Payroll w/e May 01 | 250.4 | 23035.24
502349 | 2026-05-01 | 202605 | 25-121 | 03-100 | Labour | PR |  | Payroll | Payroll w/e May 01 | 382.7 | 28319.81
502427 | 2026-05-01 | 202605 | 26-124 | 01-100 | Labour | PR |  | Payroll | Payroll w/e May 01 | 87.4 | 8043.67
502481 | 2026-05-01 | 202605 | 26-124 | 03-100 | Labour | PR |  | Payroll | Payroll w/e May 01 | 191.3 | 14159.36
502543 | 2026-05-01 | 202605 | 26-127 | 01-100 | Labour | PR |  | Payroll | Payroll w/e May 01 | 36.1 | 3325.71
501549 | 2026-05-03 | 202605 | 25-110 | 03-300 | Material | AP | V1041 | Cast-in-Place Concrete Supplier A | Invoice 95136 | 0 | 69088.06
501533 | 2026-05-05 | 202605 | 25-110 | 03-200 | Material | AP | V1040 | Reinforcing Steel Supplier B | Invoice 83640 | 0 | 4766.58
501695 | 2026-05-05 | 202605 | 25-112 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 18712 | 0 | 13437.91
502211 | 2026-05-05 | 202605 | 25-118 | 03-300 | Material | AP | V1071 | Cast-in-Place Concrete Supplier A | Invoice 94032 | 0 | 60188.66
502521 | 2026-05-05 | 202605 | 26-124 | 03-300 | Material | AP | V1087 | Cast-in-Place Concrete Supplier B | Invoice 54762 | 0 | 55594.04
500394 | 2026-05-06 | 202605 | 23-098 | 08-100 | Material | AP | V1007 | Doors Supplier G | Invoice 62839 | 0 | 31062.2
502202 | 2026-05-06 | 202605 | 25-118 | 03-200 | Material | AP | V1070 | Reinforcing Steel Supplier C | Invoice 14596 | 0 | 50420.56
500163 | 2026-05-07 | 202605 | 23-098 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 54850 | 0 | 4168.14
500885 | 2026-05-07 | 202605 | 24-104 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 31871 | 0 | 10059.69
502377 | 2026-05-07 | 202605 | 25-121 | 03-200 | Material | AP | V1079 | Reinforcing Steel Supplier C | Invoice 19286 | 0 | 66881.17
502505 | 2026-05-07 | 202605 | 26-124 | 03-200 | Material | AP | V1086 | Reinforcing Steel Supplier A | Invoice 61605 | 0 | 52883.92
500101 | 2026-05-08 | 202605 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e May 08 | 46.3 | 4261.18
500165 | 2026-05-08 | 202605 | 23-098 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 28679 | 0 | 3752.77
500509 | 2026-05-08 | 202605 | 24-101 | 01-100 | Labour | PR |  | Payroll | Payroll w/e May 08 | 230.2 | 21179.98
500711 | 2026-05-08 | 202605 | 24-101 | 06-100 | Labour | PR |  | Payroll | Payroll w/e May 08 | 138.5 | 9833.32
500838 | 2026-05-08 | 202605 | 24-104 | 01-100 | Labour | PR |  | Payroll | Payroll w/e May 08 | 320.9 | 29524.39
501031 | 2026-05-08 | 202605 | 24-104 | 06-100 | Labour | PR |  | Payroll | Payroll w/e May 08 | 211.8 | 15040.24
501145 | 2026-05-08 | 202605 | 24-107 | 01-100 | Labour | PR |  | Payroll | Payroll w/e May 08 | 168.6 | 15514.02
501305 | 2026-05-08 | 202605 | 24-107 | 06-100 | Labour | PR |  | Payroll | Payroll w/e May 08 | 159.4 | 11315.22
501406 | 2026-05-08 | 202605 | 25-110 | 01-100 | Labour | PR |  | Payroll | Payroll w/e May 08 | 364.2 | 33505.99
501510 | 2026-05-08 | 202605 | 25-110 | 03-100 | Labour | PR |  | Payroll | Payroll w/e May 08 | 120.4 | 8913.29
501532 | 2026-05-08 | 202605 | 25-110 | 03-200 | Material | AP | V1040 | Reinforcing Steel Supplier B | Invoice 30363 | 0 | 3586.42
501548 | 2026-05-08 | 202605 | 25-110 | 03-300 | Material | AP | V1041 | Cast-in-Place Concrete Supplier A | Invoice 30119 | 0 | 44182.15
501572 | 2026-05-08 | 202605 | 25-110 | 06-100 | Labour | PR |  | Payroll | Payroll w/e May 08 | 71 | 5042.16
501652 | 2026-05-08 | 202605 | 25-112 | 01-100 | Labour | PR |  | Payroll | Payroll w/e May 08 | 178.5 | 16418.62
501802 | 2026-05-08 | 202605 | 25-112 | 06-100 | Labour | PR |  | Payroll | Payroll w/e May 08 | 393.9 | 27969.03
501886 | 2026-05-08 | 202605 | 25-115 | 01-100 | Labour | PR |  | Payroll | Payroll w/e May 08 | 119.1 | 10955.38
501976 | 2026-05-08 | 202605 | 25-115 | 03-100 | Labour | PR |  | Payroll | Payroll w/e May 08 | 315.7 | 23362.85
502014 | 2026-05-08 | 202605 | 25-115 | 03-300 | Material | AP | V1061 | Cast-in-Place Concrete Supplier A | Invoice 86704 | 0 | 30240.34
502031 | 2026-05-08 | 202605 | 25-115 | 06-100 | Labour | PR |  | Payroll | Payroll w/e May 08 | 68.9 | 4894.26
502102 | 2026-05-08 | 202605 | 25-118 | 01-100 | Labour | PR |  | Payroll | Payroll w/e May 08 | 131.6 | 12103.98
502181 | 2026-05-08 | 202605 | 25-118 | 03-100 | Labour | PR |  | Payroll | Payroll w/e May 08 | 165.9 | 12275.96
502223 | 2026-05-08 | 202605 | 25-118 | 06-100 | Labour | PR |  | Payroll | Payroll w/e May 08 | 30.9 | 2192.24
502285 | 2026-05-08 | 202605 | 25-121 | 01-100 | Labour | PR |  | Payroll | Payroll w/e May 08 | 147.6 | 13578.71
502350 | 2026-05-08 | 202605 | 25-121 | 03-100 | Labour | PR |  | Payroll | Payroll w/e May 08 | 285.9 | 21159.51
502428 | 2026-05-08 | 202605 | 26-124 | 01-100 | Labour | PR |  | Payroll | Payroll w/e May 08 | 39.1 | 3601.18
502482 | 2026-05-08 | 202605 | 26-124 | 03-100 | Labour | PR |  | Payroll | Payroll w/e May 08 | 289.3 | 21408.25
502544 | 2026-05-08 | 202605 | 26-127 | 01-100 | Labour | PR |  | Payroll | Payroll w/e May 08 | 41.8 | 3847.44
500561 | 2026-05-09 | 202605 | 24-101 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 12621 | 0 | 29316.73
501327 | 2026-05-09 | 202605 | 24-107 | 08-100 | Material | AP | V1035 | Doors Supplier D | Invoice 16903 | 0 | 5356.02
502506 | 2026-05-09 | 202605 | 26-124 | 03-200 | Material | AP | V1086 | Reinforcing Steel Supplier A | Invoice 97387 | 0 | 50530.62
501183 | 2026-05-10 | 202605 | 24-107 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 38018 | 0 | 6222.08
500883 | 2026-05-11 | 202605 | 24-104 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 69292 | 0 | 6226.48
501696 | 2026-05-12 | 202605 | 25-112 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 11297 | 0 | 11213.29
501924 | 2026-05-12 | 202605 | 25-115 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 27463 | 0 | 32943.27
502133 | 2026-05-12 | 202605 | 25-118 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 14188 | 0 | 53571.02
500741 | 2026-05-14 | 202605 | 24-101 | 08-100 | Material | AP | V1016 | Doors Supplier F | Invoice 13336 | 0 | 42351.99
502378 | 2026-05-14 | 202605 | 25-121 | 03-200 | Material | AP | V1079 | Reinforcing Steel Supplier C | Invoice 62737 | 0 | 36761.67
502393 | 2026-05-14 | 202605 | 25-121 | 03-300 | Material | AP | V1080 | Cast-in-Place Concrete Supplier E | Invoice 62333 | 0 | 86955.46
502454 | 2026-05-14 | 202605 | 26-124 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 25954 | 0 | 4091.93
500102 | 2026-05-15 | 202605 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e May 15 | 45.1 | 4152.99
500510 | 2026-05-15 | 202605 | 24-101 | 01-100 | Labour | PR |  | Payroll | Payroll w/e May 15 | 128.8 | 11852.2
500712 | 2026-05-15 | 202605 | 24-101 | 06-100 | Labour | PR |  | Payroll | Payroll w/e May 15 | 55.8 | 3960.94
500839 | 2026-05-15 | 202605 | 24-104 | 01-100 | Labour | PR |  | Payroll | Payroll w/e May 15 | 206.8 | 19027.34
501032 | 2026-05-15 | 202605 | 24-104 | 06-100 | Labour | PR |  | Payroll | Payroll w/e May 15 | 548.6 | 38950.3
501059 | 2026-05-15 | 202605 | 24-104 | 08-100 | Material | AP | V1026 | Doors Supplier B | Invoice 31479 | 0 | 1256.73
501146 | 2026-05-15 | 202605 | 24-107 | 01-100 | Labour | PR |  | Payroll | Payroll w/e May 15 | 171.7 | 15795
501306 | 2026-05-15 | 202605 | 24-107 | 06-100 | Labour | PR |  | Payroll | Payroll w/e May 15 | 63.6 | 4518.63
501407 | 2026-05-15 | 202605 | 25-110 | 01-100 | Labour | PR |  | Payroll | Payroll w/e May 15 | 220.1 | 20252.69
501511 | 2026-05-15 | 202605 | 25-110 | 03-100 | Labour | PR |  | Payroll | Payroll w/e May 15 | 34.1 | 2525.65
501573 | 2026-05-15 | 202605 | 25-110 | 06-100 | Labour | PR |  | Payroll | Payroll w/e May 15 | 81.3 | 5770.66
501653 | 2026-05-15 | 202605 | 25-112 | 01-100 | Labour | PR |  | Payroll | Payroll w/e May 15 | 149.1 | 13715.24
501803 | 2026-05-15 | 202605 | 25-112 | 06-100 | Labour | PR |  | Payroll | Payroll w/e May 15 | 168.4 | 11957.03
501887 | 2026-05-15 | 202605 | 25-115 | 01-100 | Labour | PR |  | Payroll | Payroll w/e May 15 | 256.3 | 23579.87
501977 | 2026-05-15 | 202605 | 25-115 | 03-100 | Labour | PR |  | Payroll | Payroll w/e May 15 | 179 | 13245.02
502015 | 2026-05-15 | 202605 | 25-115 | 03-300 | Material | AP | V1061 | Cast-in-Place Concrete Supplier A | Invoice 29680 | 0 | 24146.97
502032 | 2026-05-15 | 202605 | 25-115 | 06-100 | Labour | PR |  | Payroll | Payroll w/e May 15 | 65.8 | 4668.45
502103 | 2026-05-15 | 202605 | 25-118 | 01-100 | Labour | PR |  | Payroll | Payroll w/e May 15 | 169 | 15548.14
502182 | 2026-05-15 | 202605 | 25-118 | 03-100 | Labour | PR |  | Payroll | Payroll w/e May 15 | 219.6 | 16253.83
502224 | 2026-05-15 | 202605 | 25-118 | 06-100 | Labour | PR |  | Payroll | Payroll w/e May 15 | 22.1 | 1571
502286 | 2026-05-15 | 202605 | 25-121 | 01-100 | Labour | PR |  | Payroll | Payroll w/e May 15 | 119.7 | 11016.56
502351 | 2026-05-15 | 202605 | 25-121 | 03-100 | Labour | PR |  | Payroll | Payroll w/e May 15 | 432.5 | 32007.02
502392 | 2026-05-15 | 202605 | 25-121 | 03-300 | Material | AP | V1080 | Cast-in-Place Concrete Supplier E | Invoice 11380 | 0 | 59127.5
502429 | 2026-05-15 | 202605 | 26-124 | 01-100 | Labour | PR |  | Payroll | Payroll w/e May 15 | 98.9 | 9103.19
502483 | 2026-05-15 | 202605 | 26-124 | 03-100 | Labour | PR |  | Payroll | Payroll w/e May 15 | 226.3 | 16747.39
502545 | 2026-05-15 | 202605 | 26-127 | 01-100 | Labour | PR |  | Payroll | Payroll w/e May 15 | 50 | 4599.11
502565 | 2026-05-15 | 202605 | 26-127 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 45503 | 0 | 1193.29
501061 | 2026-05-16 | 202605 | 24-104 | 08-100 | Material | AP | V1026 | Doors Supplier B | Invoice 68440 | 0 | 6039.48
502212 | 2026-05-16 | 202605 | 25-118 | 03-300 | Material | AP | V1071 | Cast-in-Place Concrete Supplier A | Invoice 79092 | 0 | 107932.38
501447 | 2026-05-17 | 202605 | 25-110 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 88693 | 0 | 76637.21
500560 | 2026-05-18 | 202605 | 24-101 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 14962 | 0 | 29364.67
501995 | 2026-05-18 | 202605 | 25-115 | 03-200 | Material | AP | V1060 | Reinforcing Steel Supplier B | Invoice 97981 | 0 | 14609.91
502455 | 2026-05-18 | 202605 | 26-124 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 84608 | 0 | 2221.09
502520 | 2026-05-18 | 202605 | 26-124 | 03-300 | Material | AP | V1087 | Cast-in-Place Concrete Supplier B | Invoice 35600 | 0 | 36927.94
501328 | 2026-05-19 | 202605 | 24-107 | 08-100 | Material | AP | V1035 | Doors Supplier D | Invoice 36080 | 0 | 23139.18
502314 | 2026-05-19 | 202605 | 25-121 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 89583 | 0 | 12498.08
502313 | 2026-05-20 | 202605 | 25-121 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 51582 | 0 | 15440.71
500395 | 2026-05-21 | 202605 | 23-098 | 08-100 | Material | AP | V1007 | Doors Supplier G | Invoice 95067 | 0 | 38561.71
502315 | 2026-05-21 | 202605 | 25-121 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 36737 | 0 | 4027.1
502456 | 2026-05-21 | 202605 | 26-124 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 12783 | 0 | 7270.09
500103 | 2026-05-22 | 202605 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e May 22 | 75.8 | 6973.52
500511 | 2026-05-22 | 202605 | 24-101 | 01-100 | Labour | PR |  | Payroll | Payroll w/e May 22 | 348.5 | 32060.83
500713 | 2026-05-22 | 202605 | 24-101 | 06-100 | Labour | PR |  | Payroll | Payroll w/e May 22 | 249.4 | 17710.4
500840 | 2026-05-22 | 202605 | 24-104 | 01-100 | Labour | PR |  | Payroll | Payroll w/e May 22 | 240.6 | 22131.68
501033 | 2026-05-22 | 202605 | 24-104 | 06-100 | Labour | PR |  | Payroll | Payroll w/e May 22 | 611.1 | 43391
501147 | 2026-05-22 | 202605 | 24-107 | 01-100 | Labour | PR |  | Payroll | Payroll w/e May 22 | 56 | 5151.98
501307 | 2026-05-22 | 202605 | 24-107 | 06-100 | Labour | PR |  | Payroll | Payroll w/e May 22 | 75.8 | 5381.36
501408 | 2026-05-22 | 202605 | 25-110 | 01-100 | Labour | PR |  | Payroll | Payroll w/e May 22 | 327.7 | 30148.83
501512 | 2026-05-22 | 202605 | 25-110 | 03-100 | Labour | PR |  | Payroll | Payroll w/e May 22 | 280.3 | 20743.33
501574 | 2026-05-22 | 202605 | 25-110 | 06-100 | Labour | PR |  | Payroll | Payroll w/e May 22 | 209.5 | 14874.43
501654 | 2026-05-22 | 202605 | 25-112 | 01-100 | Labour | PR |  | Payroll | Payroll w/e May 22 | 329.2 | 30287.44
501804 | 2026-05-22 | 202605 | 25-112 | 06-100 | Labour | PR |  | Payroll | Payroll w/e May 22 | 431.9 | 30667.21
501888 | 2026-05-22 | 202605 | 25-115 | 01-100 | Labour | PR |  | Payroll | Payroll w/e May 22 | 224.7 | 20675.16
501978 | 2026-05-22 | 202605 | 25-115 | 03-100 | Labour | PR |  | Payroll | Payroll w/e May 22 | 293.2 | 21697.2
502013 | 2026-05-22 | 202605 | 25-115 | 03-300 | Material | AP | V1061 | Cast-in-Place Concrete Supplier A | Invoice 69720 | 0 | 22094.44
502033 | 2026-05-22 | 202605 | 25-115 | 06-100 | Labour | PR |  | Payroll | Payroll w/e May 22 | 73.1 | 5191.45
502104 | 2026-05-22 | 202605 | 25-118 | 01-100 | Labour | PR |  | Payroll | Payroll w/e May 22 | 148.5 | 13661.3
502183 | 2026-05-22 | 202605 | 25-118 | 03-100 | Labour | PR |  | Payroll | Payroll w/e May 22 | 281.2 | 20810.82
502225 | 2026-05-22 | 202605 | 25-118 | 06-100 | Labour | PR |  | Payroll | Payroll w/e May 22 | 25 | 1775
502287 | 2026-05-22 | 202605 | 25-121 | 01-100 | Labour | PR |  | Payroll | Payroll w/e May 22 | 93.6 | 8613.01
502352 | 2026-05-22 | 202605 | 25-121 | 03-100 | Labour | PR |  | Payroll | Payroll w/e May 22 | 135.3 | 10013.93
502430 | 2026-05-22 | 202605 | 26-124 | 01-100 | Labour | PR |  | Payroll | Payroll w/e May 22 | 81.8 | 7522.81
502484 | 2026-05-22 | 202605 | 26-124 | 03-100 | Labour | PR |  | Payroll | Payroll w/e May 22 | 119.4 | 8835
502546 | 2026-05-22 | 202605 | 26-127 | 01-100 | Labour | PR |  | Payroll | Payroll w/e May 22 | 27.7 | 2546.77
502566 | 2026-05-22 | 202605 | 26-127 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 92299 | 0 | 1270.98
500164 | 2026-05-23 | 202605 | 23-098 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 17972 | 0 | 1262.94
501697 | 2026-05-23 | 202605 | 25-112 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 18508 | 0 | 4367.34
502567 | 2026-05-23 | 202605 | 26-127 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 33521 | 0 | 2293.59
501184 | 2026-05-24 | 202605 | 24-107 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 75839 | 0 | 4652.73
501531 | 2026-05-24 | 202605 | 25-110 | 03-200 | Material | AP | V1040 | Reinforcing Steel Supplier B | Invoice 13360 | 0 | 862.81
500407 | 2026-05-25 | 202605 | 23-098 | 09-200 | Subcontract | AP | V1008 | Drywall Subcontractor B | Progress claim May 2026 | 0 | 96540.66
500425 | 2026-05-25 | 202605 | 23-098 | 15-000 | Subcontract | AP | V1009 | Mechanical Subcontractor B | Progress claim May 2026 | 0 | 94279.53
500444 | 2026-05-25 | 202605 | 23-098 | 16-000 | Subcontract | AP | V1010 | Electrical Subcontractor C | Progress claim May 2026 | 0 | 52457.11
500737 | 2026-05-25 | 202605 | 24-101 | 07-200 | Subcontract | AP | V1015 | Roofing Subcontractor A | Progress claim May 2026 | 0 | 114437.34
500754 | 2026-05-25 | 202605 | 24-101 | 09-200 | Subcontract | AP | V1017 | Drywall Subcontractor B | Progress claim May 2026 | 0 | 82590.39
500767 | 2026-05-25 | 202605 | 24-101 | 15-000 | Subcontract | AP | V1018 | Mechanical Subcontractor F | Progress claim May 2026 | 0 | 299202.58
500780 | 2026-05-25 | 202605 | 24-101 | 16-000 | Subcontract | AP | V1019 | Electrical Subcontractor G | Progress claim May 2026 | 0 | 320594.74
500884 | 2026-05-25 | 202605 | 24-104 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 47905 | 0 | 16648.24
501004 | 2026-05-25 | 202605 | 24-104 | 04-200 | Subcontract | AP | V1023 | Masonry Subcontractor D | Progress claim May 2026 | 0 | 99447.91
501055 | 2026-05-25 | 202605 | 24-104 | 07-200 | Subcontract | AP | V1025 | Roofing Subcontractor F | Progress claim May 2026 | 0 | 334396.2
501070 | 2026-05-25 | 202605 | 24-104 | 09-200 | Subcontract | AP | V1027 | Drywall Subcontractor F | Progress claim May 2026 | 0 | 25666.18
501081 | 2026-05-25 | 202605 | 24-104 | 15-000 | Subcontract | AP | V1028 | Mechanical Subcontractor B | Progress claim May 2026 | 0 | 280471.88
501092 | 2026-05-25 | 202605 | 24-104 | 16-000 | Subcontract | AP | V1029 | Electrical Subcontractor F | Progress claim May 2026 | 0 | 184510.58
501182 | 2026-05-25 | 202605 | 24-107 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 30023 | 0 | 7238.24
501322 | 2026-05-25 | 202605 | 24-107 | 07-200 | Subcontract | AP | V1034 | Roofing Subcontractor A | Progress claim May 2026 | 0 | 67296.63
501339 | 2026-05-25 | 202605 | 24-107 | 09-200 | Subcontract | AP | V1036 | Drywall Subcontractor F | Progress claim May 2026 | 0 | 48041.69
501350 | 2026-05-25 | 202605 | 24-107 | 15-000 | Subcontract | AP | V1037 | Mechanical Subcontractor A | Progress claim May 2026 | 0 | 190847
501361 | 2026-05-25 | 202605 | 24-107 | 16-000 | Subcontract | AP | V1038 | Electrical Subcontractor A | Progress claim May 2026 | 0 | 201280.85
501553 | 2026-05-25 | 202605 | 25-110 | 04-200 | Subcontract | AP | V1042 | Masonry Subcontractor G | Progress claim May 2026 | 0 | 102379.69
501562 | 2026-05-25 | 202605 | 25-110 | 05-100 | Subcontract | AP | V1043 | Structural Steel Subcontractor E | Progress claim May 2026 | 0 | 763995.67
501593 | 2026-05-25 | 202605 | 25-110 | 07-200 | Subcontract | AP | V1044 | Roofing Subcontractor D | Progress claim May 2026 | 0 | 4924.04
501604 | 2026-05-25 | 202605 | 25-110 | 15-000 | Subcontract | AP | V1047 | Mechanical Subcontractor B | Progress claim May 2026 | 0 | 163813.72
501612 | 2026-05-25 | 202605 | 25-110 | 16-000 | Subcontract | AP | V1048 | Electrical Subcontractor E | Progress claim May 2026 | 0 | 118552.36
501785 | 2026-05-25 | 202605 | 25-112 | 04-200 | Subcontract | AP | V1052 | Masonry Subcontractor D | Progress claim May 2026 | 0 | 146220.87
501792 | 2026-05-25 | 202605 | 25-112 | 05-100 | Subcontract | AP | V1053 | Structural Steel Subcontractor F | Progress claim May 2026 | 0 | 21358.53
501821 | 2026-05-25 | 202605 | 25-112 | 07-200 | Subcontract | AP | V1054 | Roofing Subcontractor A | Progress claim May 2026 | 0 | 172561.66
501841 | 2026-05-25 | 202605 | 25-112 | 15-000 | Subcontract | AP | V1057 | Mechanical Subcontractor E | Progress claim May 2026 | 0 | 224830.74
501850 | 2026-05-25 | 202605 | 25-112 | 16-000 | Subcontract | AP | V1058 | Electrical Subcontractor G | Progress claim May 2026 | 0 | 130616.12
502019 | 2026-05-25 | 202605 | 25-115 | 04-200 | Subcontract | AP | V1062 | Masonry Subcontractor G | Progress claim May 2026 | 0 | 135805.9
502027 | 2026-05-25 | 202605 | 25-115 | 05-100 | Subcontract | AP | V1063 | Structural Steel Subcontractor B | Progress claim May 2026 | 0 | 233777.99
502064 | 2026-05-25 | 202605 | 25-115 | 15-000 | Subcontract | AP | V1067 | Mechanical Subcontractor C | Progress claim May 2026 | 0 | 94894.36
502071 | 2026-05-25 | 202605 | 25-115 | 16-000 | Subcontract | AP | V1068 | Electrical Subcontractor D | Progress claim May 2026 | 0 | 64569.18
502218 | 2026-05-25 | 202605 | 25-118 | 05-100 | Subcontract | AP | V1072 | Structural Steel Subcontractor D | Progress claim May 2026 | 0 | 897874.6
502255 | 2026-05-25 | 202605 | 25-118 | 15-000 | Subcontract | AP | V1076 | Mechanical Subcontractor E | Progress claim May 2026 | 0 | 152936.61
502262 | 2026-05-25 | 202605 | 25-118 | 16-000 | Subcontract | AP | V1077 | Electrical Subcontractor A | Progress claim May 2026 | 0 | 124059.72
502339 | 2026-05-25 | 202605 | 25-121 | 02-200 | Subcontract | AP | V1078 | Earthwork Subcontractor A | Progress claim May 2026 | 0 | 117602.42
502474 | 2026-05-25 | 202605 | 26-124 | 02-200 | Subcontract | AP | V1085 | Earthwork Subcontractor E | Progress claim May 2026 | 0 | 323803.74
502580 | 2026-05-25 | 202605 | 26-127 | 02-200 | Subcontract | AP | V1091 | Earthwork Subcontractor A | Progress claim May 2026 | 0 | 64180.67
501060 | 2026-05-26 | 202605 | 24-104 | 08-100 | Material | AP | V1026 | Doors Supplier B | Invoice 34644 | 0 | 2154.75
500104 | 2026-05-29 | 202605 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e May 29 | 41.7 | 3839.38
500512 | 2026-05-29 | 202605 | 24-101 | 01-100 | Labour | PR |  | Payroll | Payroll w/e May 29 | 66.5 | 6115.87
500714 | 2026-05-29 | 202605 | 24-101 | 06-100 | Labour | PR |  | Payroll | Payroll w/e May 29 | 254.3 | 18057.63
500841 | 2026-05-29 | 202605 | 24-104 | 01-100 | Labour | PR |  | Payroll | Payroll w/e May 29 | 188.7 | 17357.14
501034 | 2026-05-29 | 202605 | 24-104 | 06-100 | Labour | PR |  | Payroll | Payroll w/e May 29 | 422 | 29960.86
501148 | 2026-05-29 | 202605 | 24-107 | 01-100 | Labour | PR |  | Payroll | Payroll w/e May 29 | 242.2 | 22279.09
501308 | 2026-05-29 | 202605 | 24-107 | 06-100 | Labour | PR |  | Payroll | Payroll w/e May 29 | 143.5 | 10191.53
501409 | 2026-05-29 | 202605 | 25-110 | 01-100 | Labour | PR |  | Payroll | Payroll w/e May 29 | 306.3 | 28184.05
501513 | 2026-05-29 | 202605 | 25-110 | 03-100 | Labour | PR |  | Payroll | Payroll w/e May 29 | 98.9 | 7317.97
501575 | 2026-05-29 | 202605 | 25-110 | 06-100 | Labour | PR |  | Payroll | Payroll w/e May 29 | 103.7 | 7363.26
501655 | 2026-05-29 | 202605 | 25-112 | 01-100 | Labour | PR |  | Payroll | Payroll w/e May 29 | 250 | 23003.86
501805 | 2026-05-29 | 202605 | 25-112 | 06-100 | Labour | PR |  | Payroll | Payroll w/e May 29 | 199.4 | 14157.26
501889 | 2026-05-29 | 202605 | 25-115 | 01-100 | Labour | PR |  | Payroll | Payroll w/e May 29 | 132.4 | 12185.3
501979 | 2026-05-29 | 202605 | 25-115 | 03-100 | Labour | PR |  | Payroll | Payroll w/e May 29 | 225.4 | 16683.17
502034 | 2026-05-29 | 202605 | 25-115 | 06-100 | Labour | PR |  | Payroll | Payroll w/e May 29 | 19.3 | 1368.05
502105 | 2026-05-29 | 202605 | 25-118 | 01-100 | Labour | PR |  | Payroll | Payroll w/e May 29 | 591.2 | 54394.66
502184 | 2026-05-29 | 202605 | 25-118 | 03-100 | Labour | PR |  | Payroll | Payroll w/e May 29 | 186.5 | 13800.5
502226 | 2026-05-29 | 202605 | 25-118 | 06-100 | Labour | PR |  | Payroll | Payroll w/e May 29 | 24.6 | 1747.13
502288 | 2026-05-29 | 202605 | 25-121 | 01-100 | Labour | PR |  | Payroll | Payroll w/e May 29 | 32.8 | 3017.4
502353 | 2026-05-29 | 202605 | 25-121 | 03-100 | Labour | PR |  | Payroll | Payroll w/e May 29 | 778.1 | 57576.17
502431 | 2026-05-29 | 202605 | 26-124 | 01-100 | Labour | PR |  | Payroll | Payroll w/e May 29 | 79.2 | 7285.88
502485 | 2026-05-29 | 202605 | 26-124 | 03-100 | Labour | PR |  | Payroll | Payroll w/e May 29 | 481.9 | 35657.79
502547 | 2026-05-29 | 202605 | 26-127 | 01-100 | Labour | PR |  | Payroll | Payroll w/e May 29 | 18.6 | 1710.02
500584 | 2026-05-31 | 202605 | 24-101 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 33115.07
500906 | 2026-05-31 | 202605 | 24-104 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 31867.66
501206 | 2026-05-31 | 202605 | 24-107 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 18579.24
501464 | 2026-05-31 | 202605 | 25-110 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 50598.7
501715 | 2026-05-31 | 202605 | 25-112 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 26601.64
501940 | 2026-05-31 | 202605 | 25-115 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 41054.72
502149 | 2026-05-31 | 202605 | 25-118 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 83693.71
502330 | 2026-05-31 | 202605 | 25-121 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 28346.57
502467 | 2026-05-31 | 202605 | 26-124 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 29899.87
502575 | 2026-05-31 | 202605 | 26-127 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 4915.3
501186 | 2026-06-03 | 202606 | 24-107 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 85045 | 0 | 7172.06
502214 | 2026-06-03 | 202606 | 25-118 | 03-300 | Material | AP | V1071 | Cast-in-Place Concrete Supplier A | Invoice 36333 | 0 | 19375.3
502379 | 2026-06-03 | 202606 | 25-121 | 03-200 | Material | AP | V1079 | Reinforcing Steel Supplier C | Invoice 91159 | 0 | 77535.14
501824 | 2026-06-04 | 202606 | 25-112 | 08-100 | Material | AP | V1055 | Doors Supplier B | Invoice 87267 | 0 | 13057.1
502134 | 2026-06-04 | 202606 | 25-118 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 13203 | 0 | 19019.51
502569 | 2026-06-04 | 202606 | 26-127 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 53720 | 0 | 3037.54
500105 | 2026-06-05 | 202606 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jun 05 | 48 | 4417.43
500513 | 2026-06-05 | 202606 | 24-101 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jun 05 | 108.8 | 10005.53
500715 | 2026-06-05 | 202606 | 24-101 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Jun 05 | 153.2 | 10880.09
500742 | 2026-06-05 | 202606 | 24-101 | 08-100 | Material | AP | V1016 | Doors Supplier F | Invoice 47385 | 0 | 34982.47
500842 | 2026-06-05 | 202606 | 24-104 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jun 05 | 292 | 26861.07
501035 | 2026-06-05 | 202606 | 24-104 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Jun 05 | 302.1 | 21450.05
501149 | 2026-06-05 | 202606 | 24-107 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jun 05 | 212.1 | 19516.61
501309 | 2026-06-05 | 202606 | 24-107 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Jun 05 | 34.2 | 2429.11
501410 | 2026-06-05 | 202606 | 25-110 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jun 05 | 344.5 | 31698.19
501576 | 2026-06-05 | 202606 | 25-110 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Jun 05 | 218.9 | 15543.56
501656 | 2026-06-05 | 202606 | 25-112 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jun 05 | 167.8 | 15434.8
501806 | 2026-06-05 | 202606 | 25-112 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Jun 05 | 487.6 | 34617.95
501890 | 2026-06-05 | 202606 | 25-115 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jun 05 | 425.9 | 39182.82
501925 | 2026-06-05 | 202606 | 25-115 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 49256 | 0 | 13903.53
501980 | 2026-06-05 | 202606 | 25-115 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Jun 05 | 23.5 | 1738.32
502035 | 2026-06-05 | 202606 | 25-115 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Jun 05 | 194.7 | 13825.75
502106 | 2026-06-05 | 202606 | 25-118 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jun 05 | 220.3 | 20265.18
502185 | 2026-06-05 | 202606 | 25-118 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Jun 05 | 18.4 | 1358.51
502227 | 2026-06-05 | 202606 | 25-118 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Jun 05 | 224.8 | 15963.17
502289 | 2026-06-05 | 202606 | 25-121 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jun 05 | 110.2 | 10137.83
502354 | 2026-06-05 | 202606 | 25-121 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Jun 05 | 898.4 | 66478.19
502432 | 2026-06-05 | 202606 | 26-124 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jun 05 | 120.7 | 11101.02
502486 | 2026-06-05 | 202606 | 26-124 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Jun 05 | 348.6 | 25799.65
502524 | 2026-06-05 | 202606 | 26-124 | 03-300 | Material | AP | V1087 | Cast-in-Place Concrete Supplier B | Invoice 14673 | 0 | 25013.63
502548 | 2026-06-05 | 202606 | 26-127 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jun 05 | 58.2 | 5352.16
502585 | 2026-06-05 | 202606 | 26-127 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Jun 05 | 75.7 | 5604.13
500887 | 2026-06-06 | 202606 | 24-104 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 60244 | 0 | 10169.54
500396 | 2026-06-07 | 202606 | 23-098 | 08-100 | Material | AP | V1007 | Doors Supplier G | Invoice 24653 | 0 | 10561.54
500397 | 2026-06-07 | 202606 | 23-098 | 08-100 | Material | AP | V1007 | Doors Supplier G | Invoice 82456 | 0 | 18372.9
500886 | 2026-06-07 | 202606 | 24-104 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 11423 | 0 | 21625.42
502215 | 2026-06-08 | 202606 | 25-118 | 03-300 | Material | AP | V1071 | Cast-in-Place Concrete Supplier A | Invoice 96309 | 0 | 18492.17
500167 | 2026-06-09 | 202606 | 23-098 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 54693 | 0 | 4050.2
501699 | 2026-06-09 | 202606 | 25-112 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 60662 | 0 | 9526.31
501700 | 2026-06-10 | 202606 | 25-112 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 43189 | 0 | 6787.12
500743 | 2026-06-11 | 202606 | 24-101 | 08-100 | Material | AP | V1016 | Doors Supplier F | Invoice 88755 | 0 | 15581.55
502568 | 2026-06-11 | 202606 | 26-127 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 47136 | 0 | 5788.71
502604 | 2026-06-11 | 202606 | 26-127 | 03-200 | Material | AP | V1092 | Reinforcing Steel Supplier C | Invoice 22780 | 0 | 4613.59
500106 | 2026-06-12 | 202606 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jun 12 | 82.1 | 7551.23
500514 | 2026-06-12 | 202606 | 24-101 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jun 12 | 99.1 | 9120.57
500563 | 2026-06-12 | 202606 | 24-101 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 34579 | 0 | 22979.87
500716 | 2026-06-12 | 202606 | 24-101 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Jun 12 | 181.7 | 12900.21
500843 | 2026-06-12 | 202606 | 24-104 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jun 12 | 364.5 | 33531.16
501036 | 2026-06-12 | 202606 | 24-104 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Jun 12 | 367.6 | 26096.11
501150 | 2026-06-12 | 202606 | 24-107 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jun 12 | 121.8 | 11203.36
501185 | 2026-06-12 | 202606 | 24-107 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 20626 | 0 | 5663.78
501310 | 2026-06-12 | 202606 | 24-107 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Jun 12 | 31.2 | 2217.47
501411 | 2026-06-12 | 202606 | 25-110 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jun 12 | 570.8 | 52516.77
501577 | 2026-06-12 | 202606 | 25-110 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Jun 12 | 184.6 | 13103.06
501657 | 2026-06-12 | 202606 | 25-112 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jun 12 | 287.1 | 26410.95
501807 | 2026-06-12 | 202606 | 25-112 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Jun 12 | 159 | 11286.08
501891 | 2026-06-12 | 202606 | 25-115 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jun 12 | 289.2 | 26609.27
501981 | 2026-06-12 | 202606 | 25-115 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Jun 12 | 8.4 | 620.42
502036 | 2026-06-12 | 202606 | 25-115 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Jun 12 | 78.2 | 5551.09
502107 | 2026-06-12 | 202606 | 25-118 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jun 12 | 357.8 | 32914.53
502186 | 2026-06-12 | 202606 | 25-118 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Jun 12 | 47.3 | 3500.77
502228 | 2026-06-12 | 202606 | 25-118 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Jun 12 | 94.5 | 6711.6
502290 | 2026-06-12 | 202606 | 25-121 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jun 12 | 404.4 | 37202.85
502316 | 2026-06-12 | 202606 | 25-121 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 39294 | 0 | 16824.08
502355 | 2026-06-12 | 202606 | 25-121 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Jun 12 | 698.9 | 51721.82
502433 | 2026-06-12 | 202606 | 26-124 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jun 12 | 285.4 | 26257.04
502487 | 2026-06-12 | 202606 | 26-124 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Jun 12 | 311.6 | 23055.12
502549 | 2026-06-12 | 202606 | 26-127 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jun 12 | 43.4 | 3992.93
502586 | 2026-06-12 | 202606 | 26-127 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Jun 12 | 220.1 | 16286.01
501062 | 2026-06-13 | 202606 | 24-104 | 08-100 | Material | AP | V1026 | Doors Supplier B | Invoice 55913 | 0 | 35838.48
502457 | 2026-06-13 | 202606 | 26-124 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 49498 | 0 | 8342.18
502508 | 2026-06-13 | 202606 | 26-124 | 03-200 | Material | AP | V1086 | Reinforcing Steel Supplier A | Invoice 44515 | 0 | 55973.56
502458 | 2026-06-15 | 202606 | 26-124 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 30775 | 0 | 8616.6
502603 | 2026-06-15 | 202606 | 26-127 | 03-200 | Material | AP | V1092 | Reinforcing Steel Supplier C | Invoice 95377 | 0 | 18210.81
502135 | 2026-06-16 | 202606 | 25-118 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 20272 | 0 | 33567.26
502213 | 2026-06-16 | 202606 | 25-118 | 03-300 | Material | AP | V1071 | Cast-in-Place Concrete Supplier A | Invoice 94546 | 0 | 9863.55
500744 | 2026-06-17 | 202606 | 24-101 | 08-100 | Material | AP | V1016 | Doors Supplier F | Invoice 14056 | 0 | 14838.61
501063 | 2026-06-17 | 202606 | 24-104 | 08-100 | Material | AP | V1026 | Doors Supplier B | Invoice 10996 | 0 | 22154.22
501448 | 2026-06-17 | 202606 | 25-110 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 88610 | 0 | 67696.42
501550 | 2026-06-17 | 202606 | 25-110 | 03-300 | Material | AP | V1041 | Cast-in-Place Concrete Supplier A | Invoice 63159 | 0 | 32458.59
502509 | 2026-06-17 | 202606 | 26-124 | 03-200 | Material | AP | V1086 | Reinforcing Steel Supplier A | Invoice 85072 | 0 | 85240.89
500107 | 2026-06-19 | 202606 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jun 19 | 18.4 | 1690.63
500515 | 2026-06-19 | 202606 | 24-101 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jun 19 | 257.7 | 23709.29
500717 | 2026-06-19 | 202606 | 24-101 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Jun 19 | 39.8 | 2824.96
500844 | 2026-06-19 | 202606 | 24-104 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jun 19 | 155.8 | 14334.83
501037 | 2026-06-19 | 202606 | 24-104 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Jun 19 | 524.6 | 37244.99
501151 | 2026-06-19 | 202606 | 24-107 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jun 19 | 204.5 | 18811.83
501311 | 2026-06-19 | 202606 | 24-107 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Jun 19 | 98.9 | 7018.49
501412 | 2026-06-19 | 202606 | 25-110 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jun 19 | 400.6 | 36855.9
501578 | 2026-06-19 | 202606 | 25-110 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Jun 19 | 414.7 | 29442.86
501658 | 2026-06-19 | 202606 | 25-112 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jun 19 | 89.3 | 8219.24
501808 | 2026-06-19 | 202606 | 25-112 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Jun 19 | 164.9 | 11709.92
501892 | 2026-06-19 | 202606 | 25-115 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jun 19 | 368.3 | 33879.69
501982 | 2026-06-19 | 202606 | 25-115 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Jun 19 | 31.7 | 2346.37
502037 | 2026-06-19 | 202606 | 25-115 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Jun 19 | 179.6 | 12752.22
502108 | 2026-06-19 | 202606 | 25-118 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jun 19 | 215.7 | 19844
502187 | 2026-06-19 | 202606 | 25-118 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Jun 19 | 10.6 | 781.97
502229 | 2026-06-19 | 202606 | 25-118 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Jun 19 | 21.1 | 1500.37
502291 | 2026-06-19 | 202606 | 25-121 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jun 19 | 147.4 | 13557.2
502356 | 2026-06-19 | 202606 | 25-121 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Jun 19 | 176.4 | 13052.78
502380 | 2026-06-19 | 202606 | 25-121 | 03-200 | Material | AP | V1079 | Reinforcing Steel Supplier C | Invoice 13020 | 0 | 66065.6
502434 | 2026-06-19 | 202606 | 26-124 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jun 19 | 118.2 | 10876.62
502488 | 2026-06-19 | 202606 | 26-124 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Jun 19 | 932.4 | 68994.88
502550 | 2026-06-19 | 202606 | 26-127 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jun 19 | 93.2 | 8574.06
502587 | 2026-06-19 | 202606 | 26-127 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Jun 19 | 140.8 | 10421.04
502602 | 2026-06-19 | 202606 | 26-127 | 03-200 | Material | AP | V1092 | Reinforcing Steel Supplier C | Invoice 87188 | 0 | 5226.54
500562 | 2026-06-20 | 202606 | 24-101 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 96653 | 0 | 21121.39
502522 | 2026-06-20 | 202606 | 26-124 | 03-300 | Material | AP | V1087 | Cast-in-Place Concrete Supplier B | Invoice 37402 | 0 | 102701.39
502612 | 2026-06-20 | 202606 | 26-127 | 03-300 | Material | AP | V1093 | Cast-in-Place Concrete Supplier A | Invoice 57465 | 0 | 25634.08
501926 | 2026-06-21 | 202606 | 25-115 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 36552 | 0 | 17800.57
502016 | 2026-06-21 | 202606 | 25-115 | 03-300 | Material | AP | V1061 | Cast-in-Place Concrete Supplier A | Invoice 63130 | 0 | 8977.71
502394 | 2026-06-21 | 202606 | 25-121 | 03-300 | Material | AP | V1080 | Cast-in-Place Concrete Supplier E | Invoice 34008 | 0 | 170678.44
502523 | 2026-06-21 | 202606 | 26-124 | 03-300 | Material | AP | V1087 | Cast-in-Place Concrete Supplier B | Invoice 46059 | 0 | 52113.69
501825 | 2026-06-22 | 202606 | 25-112 | 08-100 | Material | AP | V1055 | Doors Supplier B | Invoice 44503 | 0 | 23317.53
502317 | 2026-06-22 | 202606 | 25-121 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 26984 | 0 | 24378.46
502611 | 2026-06-23 | 202606 | 26-127 | 03-300 | Material | AP | V1093 | Cast-in-Place Concrete Supplier A | Invoice 52015 | 0 | 6250.99
502017 | 2026-06-24 | 202606 | 25-115 | 03-300 | Material | AP | V1061 | Cast-in-Place Concrete Supplier A | Invoice 49936 | 0 | 18094.34
500408 | 2026-06-25 | 202606 | 23-098 | 09-200 | Subcontract | AP | V1008 | Drywall Subcontractor B | Progress claim Jun 2026 | 0 | 55498.84
500426 | 2026-06-25 | 202606 | 23-098 | 15-000 | Subcontract | AP | V1009 | Mechanical Subcontractor B | Progress claim Jun 2026 | 0 | 66700.15
500445 | 2026-06-25 | 202606 | 23-098 | 16-000 | Subcontract | AP | V1010 | Electrical Subcontractor C | Progress claim Jun 2026 | 0 | 36406.6
500738 | 2026-06-25 | 202606 | 24-101 | 07-200 | Subcontract | AP | V1015 | Roofing Subcontractor A | Progress claim Jun 2026 | 0 | 6604.34
500755 | 2026-06-25 | 202606 | 24-101 | 09-200 | Subcontract | AP | V1017 | Drywall Subcontractor B | Progress claim Jun 2026 | 0 | 120977.22
500768 | 2026-06-25 | 202606 | 24-101 | 15-000 | Subcontract | AP | V1018 | Mechanical Subcontractor F | Progress claim Jun 2026 | 0 | 259445.79
500781 | 2026-06-25 | 202606 | 24-101 | 16-000 | Subcontract | AP | V1019 | Electrical Subcontractor G | Progress claim Jun 2026 | 0 | 255469.59
501005 | 2026-06-25 | 202606 | 24-104 | 04-200 | Subcontract | AP | V1023 | Masonry Subcontractor D | Progress claim Jun 2026 | 0 | 36317.59
501056 | 2026-06-25 | 202606 | 24-104 | 07-200 | Subcontract | AP | V1025 | Roofing Subcontractor F | Progress claim Jun 2026 | 0 | 204492.55
501071 | 2026-06-25 | 202606 | 24-104 | 09-200 | Subcontract | AP | V1027 | Drywall Subcontractor F | Progress claim Jun 2026 | 0 | 109670.43
501082 | 2026-06-25 | 202606 | 24-104 | 15-000 | Subcontract | AP | V1028 | Mechanical Subcontractor B | Progress claim Jun 2026 | 0 | 260065.13
501093 | 2026-06-25 | 202606 | 24-104 | 16-000 | Subcontract | AP | V1029 | Electrical Subcontractor F | Progress claim Jun 2026 | 0 | 220695.56
501329 | 2026-06-25 | 202606 | 24-107 | 08-100 | Material | AP | V1035 | Doors Supplier D | Invoice 29508 | 0 | 40824.1
501340 | 2026-06-25 | 202606 | 24-107 | 09-200 | Subcontract | AP | V1036 | Drywall Subcontractor F | Progress claim Jun 2026 | 0 | 68225.44
501351 | 2026-06-25 | 202606 | 24-107 | 15-000 | Subcontract | AP | V1037 | Mechanical Subcontractor A | Progress claim Jun 2026 | 0 | 133529.21
501362 | 2026-06-25 | 202606 | 24-107 | 16-000 | Subcontract | AP | V1038 | Electrical Subcontractor A | Progress claim Jun 2026 | 0 | 147345.6
501554 | 2026-06-25 | 202606 | 25-110 | 04-200 | Subcontract | AP | V1042 | Masonry Subcontractor G | Progress claim Jun 2026 | 0 | 198225.45
501563 | 2026-06-25 | 202606 | 25-110 | 05-100 | Subcontract | AP | V1043 | Structural Steel Subcontractor E | Progress claim Jun 2026 | 0 | 471063.33
501594 | 2026-06-25 | 202606 | 25-110 | 07-200 | Subcontract | AP | V1044 | Roofing Subcontractor D | Progress claim Jun 2026 | 0 | 128466.74
501605 | 2026-06-25 | 202606 | 25-110 | 15-000 | Subcontract | AP | V1047 | Mechanical Subcontractor B | Progress claim Jun 2026 | 0 | 246243.53
501613 | 2026-06-25 | 202606 | 25-110 | 16-000 | Subcontract | AP | V1048 | Electrical Subcontractor E | Progress claim Jun 2026 | 0 | 197184.7
501786 | 2026-06-25 | 202606 | 25-112 | 04-200 | Subcontract | AP | V1052 | Masonry Subcontractor D | Progress claim Jun 2026 | 0 | 36137.72
501822 | 2026-06-25 | 202606 | 25-112 | 07-200 | Subcontract | AP | V1054 | Roofing Subcontractor A | Progress claim Jun 2026 | 0 | 114567.99
501833 | 2026-06-25 | 202606 | 25-112 | 09-200 | Subcontract | AP | V1056 | Drywall Subcontractor E | Progress claim Jun 2026 | 0 | 66917.28
501842 | 2026-06-25 | 202606 | 25-112 | 15-000 | Subcontract | AP | V1057 | Mechanical Subcontractor E | Progress claim Jun 2026 | 0 | 225359.17
501851 | 2026-06-25 | 202606 | 25-112 | 16-000 | Subcontract | AP | V1058 | Electrical Subcontractor G | Progress claim Jun 2026 | 0 | 182647.34
502020 | 2026-06-25 | 202606 | 25-115 | 04-200 | Subcontract | AP | V1062 | Masonry Subcontractor G | Progress claim Jun 2026 | 0 | 202065.93
502028 | 2026-06-25 | 202606 | 25-115 | 05-100 | Subcontract | AP | V1063 | Structural Steel Subcontractor B | Progress claim Jun 2026 | 0 | 134534.55
502052 | 2026-06-25 | 202606 | 25-115 | 07-200 | Subcontract | AP | V1064 | Roofing Subcontractor B | Progress claim Jun 2026 | 0 | 70277.52
502065 | 2026-06-25 | 202606 | 25-115 | 15-000 | Subcontract | AP | V1067 | Mechanical Subcontractor C | Progress claim Jun 2026 | 0 | 165716.21
502072 | 2026-06-25 | 202606 | 25-115 | 16-000 | Subcontract | AP | V1068 | Electrical Subcontractor D | Progress claim Jun 2026 | 0 | 86087.11
502219 | 2026-06-25 | 202606 | 25-118 | 05-100 | Subcontract | AP | V1072 | Structural Steel Subcontractor D | Progress claim Jun 2026 | 0 | 551403.85
502244 | 2026-06-25 | 202606 | 25-118 | 07-200 | Subcontract | AP | V1073 | Roofing Subcontractor A | Progress claim Jun 2026 | 0 | 93754.77
502256 | 2026-06-25 | 202606 | 25-118 | 15-000 | Subcontract | AP | V1076 | Mechanical Subcontractor E | Progress claim Jun 2026 | 0 | 218946.19
502263 | 2026-06-25 | 202606 | 25-118 | 16-000 | Subcontract | AP | V1077 | Electrical Subcontractor A | Progress claim Jun 2026 | 0 | 154775.79
502340 | 2026-06-25 | 202606 | 25-121 | 02-200 | Subcontract | AP | V1078 | Earthwork Subcontractor A | Progress claim Jun 2026 | 0 | 12387.95
502405 | 2026-06-25 | 202606 | 25-121 | 05-100 | Subcontract | AP | V1082 | Structural Steel Subcontractor F | Progress claim Jun 2026 | 0 | 36368.41
502475 | 2026-06-25 | 202606 | 26-124 | 02-200 | Subcontract | AP | V1085 | Earthwork Subcontractor E | Progress claim Jun 2026 | 0 | 134921.47
502581 | 2026-06-25 | 202606 | 26-127 | 02-200 | Subcontract | AP | V1091 | Earthwork Subcontractor A | Progress claim Jun 2026 | 0 | 161975.05
500108 | 2026-06-26 | 202606 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jun 26 | 14.6 | 1342.9
500516 | 2026-06-26 | 202606 | 24-101 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jun 26 | 236.9 | 21796.32
500718 | 2026-06-26 | 202606 | 24-101 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Jun 26 | 99.3 | 7049.68
500845 | 2026-06-26 | 202606 | 24-104 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jun 26 | 305.5 | 28103.79
501038 | 2026-06-26 | 202606 | 24-104 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Jun 26 | 439.4 | 31196.31
501152 | 2026-06-26 | 202606 | 24-107 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jun 26 | 43.8 | 4026.34
501312 | 2026-06-26 | 202606 | 24-107 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Jun 26 | 50.5 | 3586.4
501413 | 2026-06-26 | 202606 | 25-110 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jun 26 | 375.2 | 34516.63
501579 | 2026-06-26 | 202606 | 25-110 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Jun 26 | 246.1 | 17474.6
501659 | 2026-06-26 | 202606 | 25-112 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jun 26 | 221.7 | 20399.94
501809 | 2026-06-26 | 202606 | 25-112 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Jun 26 | 323.3 | 22954.57
501893 | 2026-06-26 | 202606 | 25-115 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jun 26 | 88.3 | 8121.92
501983 | 2026-06-26 | 202606 | 25-115 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Jun 26 | 16.3 | 1208.77
502038 | 2026-06-26 | 202606 | 25-115 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Jun 26 | 166.5 | 11821.49
502109 | 2026-06-26 | 202606 | 25-118 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jun 26 | 544.3 | 50077.17
502188 | 2026-06-26 | 202606 | 25-118 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Jun 26 | 65.5 | 4844.36
502230 | 2026-06-26 | 202606 | 25-118 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Jun 26 | 84.6 | 6009.39
502292 | 2026-06-26 | 202606 | 25-121 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jun 26 | 178.2 | 16398.55
502357 | 2026-06-26 | 202606 | 25-121 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Jun 26 | 625.2 | 46264.27
502435 | 2026-06-26 | 202606 | 26-124 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jun 26 | 45.3 | 4164.09
502489 | 2026-06-26 | 202606 | 26-124 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Jun 26 | 203 | 15023.76
502551 | 2026-06-26 | 202606 | 26-127 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jun 26 | 101 | 9288.82
502588 | 2026-06-26 | 202606 | 26-127 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Jun 26 | 67.4 | 4990.21
500166 | 2026-06-27 | 202606 | 23-098 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 11169 | 0 | 2298.77
501698 | 2026-06-27 | 202606 | 25-112 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 95259 | 0 | 6263.91
502507 | 2026-06-27 | 202606 | 26-124 | 03-200 | Material | AP | V1086 | Reinforcing Steel Supplier A | Invoice 74131 | 0 | 47654.32
500585 | 2026-06-30 | 202606 | 24-101 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 30621.7
500907 | 2026-06-30 | 202606 | 24-104 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 19759.4
501207 | 2026-06-30 | 202606 | 24-107 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 16407.26
501465 | 2026-06-30 | 202606 | 25-110 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 53663.61
501716 | 2026-06-30 | 202606 | 25-112 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 22042.48
501941 | 2026-06-30 | 202606 | 25-115 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 32662.09
502150 | 2026-06-30 | 202606 | 25-118 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 87749.46
502331 | 2026-06-30 | 202606 | 25-121 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 36237.42
502468 | 2026-06-30 | 202606 | 26-124 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 36003.49
502576 | 2026-06-30 | 202606 | 26-127 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 9774.57
500109 | 2026-07-03 | 202607 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jul 03 | 39.8 | 3662.05
500517 | 2026-07-03 | 202607 | 24-101 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jul 03 | 86.9 | 7998.76
500719 | 2026-07-03 | 202607 | 24-101 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Jul 03 | 56.5 | 4014.8
500846 | 2026-07-03 | 202607 | 24-104 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jul 03 | 116.3 | 10696.66
501039 | 2026-07-03 | 202607 | 24-104 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Jul 03 | 246.5 | 17504.7
501153 | 2026-07-03 | 202607 | 24-107 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jul 03 | 136.4 | 12548.28
501313 | 2026-07-03 | 202607 | 24-107 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Jul 03 | 21.2 | 1506.87
501414 | 2026-07-03 | 202607 | 25-110 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jul 03 | 164 | 15086.85
501580 | 2026-07-03 | 202607 | 25-110 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Jul 03 | 354.7 | 25184.8
501660 | 2026-07-03 | 202607 | 25-112 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jul 03 | 165.9 | 15262.78
501810 | 2026-07-03 | 202607 | 25-112 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Jul 03 | 212.1 | 15057.9
501894 | 2026-07-03 | 202607 | 25-115 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jul 03 | 233.2 | 21454.82
502039 | 2026-07-03 | 202607 | 25-115 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Jul 03 | 149.6 | 10619.15
502110 | 2026-07-03 | 202607 | 25-118 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jul 03 | 346.9 | 31918.15
502231 | 2026-07-03 | 202607 | 25-118 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Jul 03 | 164.2 | 11660.86
502293 | 2026-07-03 | 202607 | 25-121 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jul 03 | 128 | 11774.99
502358 | 2026-07-03 | 202607 | 25-121 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Jul 03 | 341.2 | 25249.56
502396 | 2026-07-03 | 202607 | 25-121 | 03-300 | Material | AP | V1080 | Cast-in-Place Concrete Supplier E | Invoice 86410 | 0 | 36856.42
502436 | 2026-07-03 | 202607 | 26-124 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jul 03 | 119.9 | 11031.88
502490 | 2026-07-03 | 202607 | 26-124 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Jul 03 | 393.7 | 29133.1
502552 | 2026-07-03 | 202607 | 26-127 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jul 03 | 106.4 | 9785.18
502589 | 2026-07-03 | 202607 | 26-127 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Jul 03 | 94 | 6955.35
502631 | 2026-07-03 | 202607 | 26-130 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jul 03 | 22 | 2026.35
502395 | 2026-07-04 | 202607 | 25-121 | 03-300 | Material | AP | V1080 | Cast-in-Place Concrete Supplier E | Invoice 61107 | 0 | 151272.59
501188 | 2026-07-06 | 202607 | 24-107 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 13110 | 0 | 5688.25
501332 | 2026-07-06 | 202607 | 24-107 | 08-100 | Material | AP | V1035 | Doors Supplier D | Invoice 97786 | 0 | 19133.68
502645 | 2026-07-06 | 202607 | 26-130 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 94117 | 0 | 2208.21
502320 | 2026-07-07 | 202607 | 25-121 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 82687 | 0 | 10387.02
500564 | 2026-07-08 | 202607 | 24-101 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 72065 | 0 | 34262.08
501187 | 2026-07-09 | 202607 | 24-107 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 63699 | 0 | 3828.24
501330 | 2026-07-09 | 202607 | 24-107 | 08-100 | Material | AP | V1035 | Doors Supplier D | Invoice 51836 | 0 | 12778.6
501827 | 2026-07-09 | 202607 | 25-112 | 08-100 | Material | AP | V1055 | Doors Supplier B | Invoice 34250 | 0 | 40094.79
502571 | 2026-07-09 | 202607 | 26-127 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 92644 | 0 | 8688.4
500110 | 2026-07-10 | 202607 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jul 10 | 19.6 | 1803.86
500518 | 2026-07-10 | 202607 | 24-101 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jul 10 | 169.3 | 15578.04
500720 | 2026-07-10 | 202607 | 24-101 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Jul 10 | 92.2 | 6548.96
500847 | 2026-07-10 | 202607 | 24-104 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jul 10 | 150.6 | 13854.95
501040 | 2026-07-10 | 202607 | 24-104 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Jul 10 | 119.8 | 8506.7
501064 | 2026-07-10 | 202607 | 24-104 | 08-100 | Material | AP | V1026 | Doors Supplier B | Invoice 81252 | 0 | 42071.93
501154 | 2026-07-10 | 202607 | 24-107 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jul 10 | 93.9 | 8639.46
501314 | 2026-07-10 | 202607 | 24-107 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Jul 10 | 6 | 423.04
501415 | 2026-07-10 | 202607 | 25-110 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jul 10 | 492 | 45263.63
501581 | 2026-07-10 | 202607 | 25-110 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Jul 10 | 315.1 | 22375.27
501661 | 2026-07-10 | 202607 | 25-112 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jul 10 | 202.7 | 18647.18
501811 | 2026-07-10 | 202607 | 25-112 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Jul 10 | 166.3 | 11803.92
501826 | 2026-07-10 | 202607 | 25-112 | 08-100 | Material | AP | V1055 | Doors Supplier B | Invoice 18726 | 0 | 15312.37
501895 | 2026-07-10 | 202607 | 25-115 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jul 10 | 283.8 | 26112.86
502040 | 2026-07-10 | 202607 | 25-115 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Jul 10 | 137 | 9725.59
502111 | 2026-07-10 | 202607 | 25-118 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jul 10 | 202.8 | 18660.87
502232 | 2026-07-10 | 202607 | 25-118 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Jul 10 | 288.5 | 20481.21
502294 | 2026-07-10 | 202607 | 25-121 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jul 10 | 252.9 | 23262.3
502359 | 2026-07-10 | 202607 | 25-121 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Jul 10 | 417.4 | 30889.56
502437 | 2026-07-10 | 202607 | 26-124 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jul 10 | 172.1 | 15832.08
502491 | 2026-07-10 | 202607 | 26-124 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Jul 10 | 979.9 | 72511.53
502553 | 2026-07-10 | 202607 | 26-127 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jul 10 | 56.8 | 5225.38
502590 | 2026-07-10 | 202607 | 26-127 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Jul 10 | 319.4 | 23639.13
502632 | 2026-07-10 | 202607 | 26-130 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jul 10 | 16.6 | 1525.47
500888 | 2026-07-11 | 202607 | 24-104 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 41335 | 0 | 8577.97
501927 | 2026-07-11 | 202607 | 25-115 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 58617 | 0 | 10884.81
501928 | 2026-07-11 | 202607 | 25-115 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 38966 | 0 | 21343.81
502319 | 2026-07-12 | 202607 | 25-121 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 28237 | 0 | 31410.09
502525 | 2026-07-12 | 202607 | 26-124 | 03-300 | Material | AP | V1087 | Cast-in-Place Concrete Supplier B | Invoice 83848 | 0 | 232877.43
502614 | 2026-07-12 | 202607 | 26-127 | 03-300 | Material | AP | V1093 | Cast-in-Place Concrete Supplier A | Invoice 94382 | 0 | 66589.25
502615 | 2026-07-12 | 202607 | 26-127 | 03-300 | Material | AP | V1093 | Cast-in-Place Concrete Supplier A | Invoice 74948 | 0 | 61501.19
501701 | 2026-07-13 | 202607 | 25-112 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 37613 | 0 | 19246.47
501449 | 2026-07-14 | 202607 | 25-110 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 88545 | 0 | 43658.33
500890 | 2026-07-15 | 202607 | 24-104 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 34447 | 0 | 4022.61
501065 | 2026-07-16 | 202607 | 24-104 | 08-100 | Material | AP | V1026 | Doors Supplier B | Invoice 90961 | 0 | 60009.88
502512 | 2026-07-16 | 202607 | 26-124 | 03-200 | Material | AP | V1086 | Reinforcing Steel Supplier A | Invoice 61003 | 0 | 45474.84
500111 | 2026-07-17 | 202607 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jul 17 | 13.6 | 1250.18
500519 | 2026-07-17 | 202607 | 24-101 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jul 17 | 100.1 | 9212.35
500721 | 2026-07-17 | 202607 | 24-101 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Jul 17 | 56.8 | 4033.57
500848 | 2026-07-17 | 202607 | 24-104 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jul 17 | 262.1 | 24116.57
501041 | 2026-07-17 | 202607 | 24-104 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Jul 17 | 370.4 | 26297.14
501155 | 2026-07-17 | 202607 | 24-107 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jul 17 | 89.9 | 8274.99
501315 | 2026-07-17 | 202607 | 24-107 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Jul 17 | 18 | 1280.58
501416 | 2026-07-17 | 202607 | 25-110 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jul 17 | 130.7 | 12023.24
501582 | 2026-07-17 | 202607 | 25-110 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Jul 17 | 250.9 | 17811.71
501662 | 2026-07-17 | 202607 | 25-112 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jul 17 | 92.5 | 8510.49
501812 | 2026-07-17 | 202607 | 25-112 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Jul 17 | 133.1 | 9450.31
501828 | 2026-07-17 | 202607 | 25-112 | 08-100 | Material | AP | V1055 | Doors Supplier B | Invoice 82536 | 0 | 48028.33
501896 | 2026-07-17 | 202607 | 25-115 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jul 17 | 427.2 | 39305.1
502041 | 2026-07-17 | 202607 | 25-115 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Jul 17 | 346.6 | 24609.17
502112 | 2026-07-17 | 202607 | 25-118 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jul 17 | 329 | 30264.61
502233 | 2026-07-17 | 202607 | 25-118 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Jul 17 | 245.8 | 17451.44
502295 | 2026-07-17 | 202607 | 25-121 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jul 17 | 192.3 | 17687.64
502360 | 2026-07-17 | 202607 | 25-121 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Jul 17 | 198.3 | 14675.06
502438 | 2026-07-17 | 202607 | 26-124 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jul 17 | 74.2 | 6826.13
502492 | 2026-07-17 | 202607 | 26-124 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Jul 17 | 158.7 | 11740.17
502554 | 2026-07-17 | 202607 | 26-127 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jul 17 | 157.8 | 14516.09
502570 | 2026-07-17 | 202607 | 26-127 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 17064 | 0 | 3850.11
502591 | 2026-07-17 | 202607 | 26-127 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Jul 17 | 98.2 | 7263.71
502633 | 2026-07-17 | 202607 | 26-130 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jul 17 | 23.2 | 2137.65
500745 | 2026-07-18 | 202607 | 24-101 | 08-100 | Material | AP | V1016 | Doors Supplier F | Invoice 76484 | 0 | 35777.47
500746 | 2026-07-18 | 202607 | 24-101 | 08-100 | Material | AP | V1016 | Doors Supplier F | Invoice 50680 | 0 | 67485.78
500889 | 2026-07-18 | 202607 | 24-104 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 33262 | 0 | 17888.46
502510 | 2026-07-18 | 202607 | 26-124 | 03-200 | Material | AP | V1086 | Reinforcing Steel Supplier A | Invoice 47515 | 0 | 81597.32
501331 | 2026-07-19 | 202607 | 24-107 | 08-100 | Material | AP | V1035 | Doors Supplier D | Invoice 64824 | 0 | 9898.54
500169 | 2026-07-20 | 202607 | 23-098 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 98604 | 0 | 2929.47
502459 | 2026-07-20 | 202607 | 26-124 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 15586 | 0 | 17024.2
502381 | 2026-07-21 | 202607 | 25-121 | 03-200 | Material | AP | V1079 | Reinforcing Steel Supplier C | Invoice 89659 | 0 | 20742.78
502511 | 2026-07-21 | 202607 | 26-124 | 03-200 | Material | AP | V1086 | Reinforcing Steel Supplier A | Invoice 34296 | 0 | 91775.07
500168 | 2026-07-23 | 202607 | 23-098 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 92241 | 0 | 2897.93
501450 | 2026-07-23 | 202607 | 25-110 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 67627 | 0 | 36384.77
502318 | 2026-07-23 | 202607 | 25-121 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 92843 | 0 | 7105.09
502605 | 2026-07-23 | 202607 | 26-127 | 03-200 | Material | AP | V1092 | Reinforcing Steel Supplier C | Invoice 35227 | 0 | 80349.2
500112 | 2026-07-24 | 202607 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jul 24 | 29.2 | 2687.77
500520 | 2026-07-24 | 202607 | 24-101 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jul 24 | 67.5 | 6206.45
500722 | 2026-07-24 | 202607 | 24-101 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Jul 24 | 52.9 | 3756.29
500849 | 2026-07-24 | 202607 | 24-104 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jul 24 | 156.2 | 14371.45
501042 | 2026-07-24 | 202607 | 24-104 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Jul 24 | 321.3 | 22811.04
501156 | 2026-07-24 | 202607 | 24-107 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jul 24 | 90.9 | 8360.16
501316 | 2026-07-24 | 202607 | 24-107 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Jul 24 | 10.5 | 748.48
501417 | 2026-07-24 | 202607 | 25-110 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jul 24 | 505.1 | 46470.43
501583 | 2026-07-24 | 202607 | 25-110 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Jul 24 | 544.3 | 38647.97
501663 | 2026-07-24 | 202607 | 25-112 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jul 24 | 49.5 | 4550.26
501813 | 2026-07-24 | 202607 | 25-112 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Jul 24 | 63.2 | 4489.44
501897 | 2026-07-24 | 202607 | 25-115 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jul 24 | 46 | 4228.33
502042 | 2026-07-24 | 202607 | 25-115 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Jul 24 | 479.6 | 34054.55
502113 | 2026-07-24 | 202607 | 25-118 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jul 24 | 390.2 | 35897.27
502234 | 2026-07-24 | 202607 | 25-118 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Jul 24 | 77.5 | 5499.13
502296 | 2026-07-24 | 202607 | 25-121 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jul 24 | 243.7 | 22417.89
502361 | 2026-07-24 | 202607 | 25-121 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Jul 24 | 635.4 | 47019.1
502439 | 2026-07-24 | 202607 | 26-124 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jul 24 | 125.8 | 11575.18
502460 | 2026-07-24 | 202607 | 26-124 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 10998 | 0 | 8633.44
502493 | 2026-07-24 | 202607 | 26-124 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Jul 24 | 477.6 | 35345.77
502555 | 2026-07-24 | 202607 | 26-127 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jul 24 | 50.1 | 4610.18
502592 | 2026-07-24 | 202607 | 26-127 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Jul 24 | 453.1 | 33530.93
502634 | 2026-07-24 | 202607 | 26-130 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jul 24 | 24.1 | 2219.56
502644 | 2026-07-24 | 202607 | 26-130 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 92287 | 0 | 1201.7
500409 | 2026-07-25 | 202607 | 23-098 | 09-200 | Subcontract | AP | V1008 | Drywall Subcontractor B | Progress claim Jul 2026 | 0 | 22565.27
500427 | 2026-07-25 | 202607 | 23-098 | 15-000 | Subcontract | AP | V1009 | Mechanical Subcontractor B | Progress claim Jul 2026 | 0 | 42066.53
500446 | 2026-07-25 | 202607 | 23-098 | 16-000 | Subcontract | AP | V1010 | Electrical Subcontractor C | Progress claim Jul 2026 | 0 | 27268.08
500756 | 2026-07-25 | 202607 | 24-101 | 09-200 | Subcontract | AP | V1017 | Drywall Subcontractor B | Progress claim Jul 2026 | 0 | 167207.06
500769 | 2026-07-25 | 202607 | 24-101 | 15-000 | Subcontract | AP | V1018 | Mechanical Subcontractor F | Progress claim Jul 2026 | 0 | 183378.71
500782 | 2026-07-25 | 202607 | 24-101 | 16-000 | Subcontract | AP | V1019 | Electrical Subcontractor G | Progress claim Jul 2026 | 0 | 255705.39
501057 | 2026-07-25 | 202607 | 24-104 | 07-200 | Subcontract | AP | V1025 | Roofing Subcontractor F | Progress claim Jul 2026 | 0 | 69979.07
501072 | 2026-07-25 | 202607 | 24-104 | 09-200 | Subcontract | AP | V1027 | Drywall Subcontractor F | Progress claim Jul 2026 | 0 | 258002.99
501083 | 2026-07-25 | 202607 | 24-104 | 15-000 | Subcontract | AP | V1028 | Mechanical Subcontractor B | Progress claim Jul 2026 | 0 | 230066.44
501094 | 2026-07-25 | 202607 | 24-104 | 16-000 | Subcontract | AP | V1029 | Electrical Subcontractor F | Progress claim Jul 2026 | 0 | 176989.59
501341 | 2026-07-25 | 202607 | 24-107 | 09-200 | Subcontract | AP | V1036 | Drywall Subcontractor F | Progress claim Jul 2026 | 0 | 73609.58
501352 | 2026-07-25 | 202607 | 24-107 | 15-000 | Subcontract | AP | V1037 | Mechanical Subcontractor A | Progress claim Jul 2026 | 0 | 110784.82
501363 | 2026-07-25 | 202607 | 24-107 | 16-000 | Subcontract | AP | V1038 | Electrical Subcontractor A | Progress claim Jul 2026 | 0 | 127317.35
501555 | 2026-07-25 | 202607 | 25-110 | 04-200 | Subcontract | AP | V1042 | Masonry Subcontractor G | Progress claim Jul 2026 | 0 | 178770.33
501564 | 2026-07-25 | 202607 | 25-110 | 05-100 | Subcontract | AP | V1043 | Structural Steel Subcontractor E | Progress claim Jul 2026 | 0 | 173827.31
501595 | 2026-07-25 | 202607 | 25-110 | 07-200 | Subcontract | AP | V1044 | Roofing Subcontractor D | Progress claim Jul 2026 | 0 | 346203.27
501606 | 2026-07-25 | 202607 | 25-110 | 15-000 | Subcontract | AP | V1047 | Mechanical Subcontractor B | Progress claim Jul 2026 | 0 | 275523.97
501614 | 2026-07-25 | 202607 | 25-110 | 16-000 | Subcontract | AP | V1048 | Electrical Subcontractor E | Progress claim Jul 2026 | 0 | 199970.82
501823 | 2026-07-25 | 202607 | 25-112 | 07-200 | Subcontract | AP | V1054 | Roofing Subcontractor A | Progress claim Jul 2026 | 0 | 24023.74
501834 | 2026-07-25 | 202607 | 25-112 | 09-200 | Subcontract | AP | V1056 | Drywall Subcontractor E | Progress claim Jul 2026 | 0 | 192225.69
501843 | 2026-07-25 | 202607 | 25-112 | 15-000 | Subcontract | AP | V1057 | Mechanical Subcontractor E | Progress claim Jul 2026 | 0 | 187468.78
501852 | 2026-07-25 | 202607 | 25-112 | 16-000 | Subcontract | AP | V1058 | Electrical Subcontractor G | Progress claim Jul 2026 | 0 | 169734.77
502021 | 2026-07-25 | 202607 | 25-115 | 04-200 | Subcontract | AP | V1062 | Masonry Subcontractor G | Progress claim Jul 2026 | 0 | 255325.99
502029 | 2026-07-25 | 202607 | 25-115 | 05-100 | Subcontract | AP | V1063 | Structural Steel Subcontractor B | Progress claim Jul 2026 | 0 | 51077.09
502053 | 2026-07-25 | 202607 | 25-115 | 07-200 | Subcontract | AP | V1064 | Roofing Subcontractor B | Progress claim Jul 2026 | 0 | 178243.12
502066 | 2026-07-25 | 202607 | 25-115 | 15-000 | Subcontract | AP | V1067 | Mechanical Subcontractor C | Progress claim Jul 2026 | 0 | 223408
502073 | 2026-07-25 | 202607 | 25-115 | 16-000 | Subcontract | AP | V1068 | Electrical Subcontractor D | Progress claim Jul 2026 | 0 | 122208.2
502220 | 2026-07-25 | 202607 | 25-118 | 05-100 | Subcontract | AP | V1072 | Structural Steel Subcontractor D | Progress claim Jul 2026 | 0 | 172858.49
502245 | 2026-07-25 | 202607 | 25-118 | 07-200 | Subcontract | AP | V1073 | Roofing Subcontractor A | Progress claim Jul 2026 | 0 | 340901.87
502257 | 2026-07-25 | 202607 | 25-118 | 15-000 | Subcontract | AP | V1076 | Mechanical Subcontractor E | Progress claim Jul 2026 | 0 | 370646.76
502264 | 2026-07-25 | 202607 | 25-118 | 16-000 | Subcontract | AP | V1077 | Electrical Subcontractor A | Progress claim Jul 2026 | 0 | 250358.74
502406 | 2026-07-25 | 202607 | 25-121 | 05-100 | Subcontract | AP | V1082 | Structural Steel Subcontractor F | Progress claim Jul 2026 | 0 | 103965.66
502413 | 2026-07-25 | 202607 | 25-121 | 15-000 | Subcontract | AP | V1083 | Mechanical Subcontractor E | Progress claim Jul 2026 | 0 | 43373.94
502416 | 2026-07-25 | 202607 | 25-121 | 16-000 | Subcontract | AP | V1084 | Electrical Subcontractor F | Progress claim Jul 2026 | 0 | 47329.71
502530 | 2026-07-25 | 202607 | 26-124 | 05-100 | Subcontract | AP | V1088 | Structural Steel Subcontractor B | Progress claim Jul 2026 | 0 | 167380.07
502537 | 2026-07-25 | 202607 | 26-124 | 15-000 | Subcontract | AP | V1089 | Mechanical Subcontractor C | Progress claim Jul 2026 | 0 | 11444.1
502540 | 2026-07-25 | 202607 | 26-124 | 16-000 | Subcontract | AP | V1090 | Electrical Subcontractor C | Progress claim Jul 2026 | 0 | 9955.35
502582 | 2026-07-25 | 202607 | 26-127 | 02-200 | Subcontract | AP | V1091 | Earthwork Subcontractor A | Progress claim Jul 2026 | 0 | 89469.39
502653 | 2026-07-25 | 202607 | 26-130 | 02-200 | Subcontract | AP | V1098 | Earthwork Subcontractor D | Progress claim Jul 2026 | 0 | 25762.74
502382 | 2026-07-26 | 202607 | 25-121 | 03-200 | Material | AP | V1079 | Reinforcing Steel Supplier C | Invoice 39899 | 0 | 84429.03
502136 | 2026-07-27 | 202607 | 25-118 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 52331 | 0 | 55436.45
502613 | 2026-07-27 | 202607 | 26-127 | 03-300 | Material | AP | V1093 | Cast-in-Place Concrete Supplier A | Invoice 26801 | 0 | 6828.77
500113 | 2026-07-31 | 202607 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jul 31 | 58.2 | 5353.6
500521 | 2026-07-31 | 202607 | 24-101 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jul 31 | 122.2 | 11238.82
500586 | 2026-07-31 | 202607 | 24-101 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 22525.86
500723 | 2026-07-31 | 202607 | 24-101 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Jul 31 | 43.2 | 3065.36
500850 | 2026-07-31 | 202607 | 24-104 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jul 31 | 285.8 | 26289.29
500908 | 2026-07-31 | 202607 | 24-104 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 15448.02
501043 | 2026-07-31 | 202607 | 24-104 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Jul 31 | 201 | 14268.42
501157 | 2026-07-31 | 202607 | 24-107 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jul 31 | 62.3 | 5728.81
501208 | 2026-07-31 | 202607 | 24-107 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 9170.52
501317 | 2026-07-31 | 202607 | 24-107 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Jul 31 | 15.6 | 1108.12
501418 | 2026-07-31 | 202607 | 25-110 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jul 31 | 452.5 | 41630.51
501466 | 2026-07-31 | 202607 | 25-110 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 53130.22
501584 | 2026-07-31 | 202607 | 25-110 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Jul 31 | 331.4 | 23531.14
501664 | 2026-07-31 | 202607 | 25-112 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jul 31 | 180.3 | 16587.47
501717 | 2026-07-31 | 202607 | 25-112 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 18235.51
501814 | 2026-07-31 | 202607 | 25-112 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Jul 31 | 100.1 | 7106.73
501898 | 2026-07-31 | 202607 | 25-115 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jul 31 | 223.5 | 20558.8
501942 | 2026-07-31 | 202607 | 25-115 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 32431.93
502043 | 2026-07-31 | 202607 | 25-115 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Jul 31 | 147.3 | 10459.38
502114 | 2026-07-31 | 202607 | 25-118 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jul 31 | 160.5 | 14762.88
502151 | 2026-07-31 | 202607 | 25-118 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 72507.89
502235 | 2026-07-31 | 202607 | 25-118 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Jul 31 | 102.4 | 7267.48
502297 | 2026-07-31 | 202607 | 25-121 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jul 31 | 134.6 | 12386.15
502332 | 2026-07-31 | 202607 | 25-121 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 59086.23
502362 | 2026-07-31 | 202607 | 25-121 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Jul 31 | 601.1 | 44478.25
502440 | 2026-07-31 | 202607 | 26-124 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jul 31 | 236.6 | 21769.86
502469 | 2026-07-31 | 202607 | 26-124 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 62060.68
502494 | 2026-07-31 | 202607 | 26-124 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Jul 31 | 631.4 | 46724.71
502556 | 2026-07-31 | 202607 | 26-127 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jul 31 | 42.2 | 3885.12
502577 | 2026-07-31 | 202607 | 26-127 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 20199.5
502593 | 2026-07-31 | 202607 | 26-127 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Jul 31 | 268 | 19833.32
502635 | 2026-07-31 | 202607 | 26-130 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Jul 31 | 27.9 | 2569.44
502650 | 2026-07-31 | 202607 | 26-130 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 2241
502137 | 2026-08-04 | 202608 | 25-118 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 96062 | 0 | 17558.11
500748 | 2026-08-05 | 202608 | 24-101 | 08-100 | Material | AP | V1016 | Doors Supplier F | Invoice 25958 | 0 | 18458.42
500747 | 2026-08-06 | 202608 | 24-101 | 08-100 | Material | AP | V1016 | Doors Supplier F | Invoice 77784 | 0 | 31528.77
501929 | 2026-08-06 | 202608 | 25-115 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 47690 | 0 | 36394.53
502385 | 2026-08-06 | 202608 | 25-121 | 03-200 | Material | AP | V1079 | Reinforcing Steel Supplier C | Invoice 39353 | 0 | 20556.1
502526 | 2026-08-06 | 202608 | 26-124 | 03-300 | Material | AP | V1087 | Cast-in-Place Concrete Supplier B | Invoice 36107 | 0 | 51105.97
502647 | 2026-08-06 | 202608 | 26-130 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 66574 | 0 | 758.57
502665 | 2026-08-06 | 202608 | 26-130 | 03-200 | Material | AP | V1099 | Reinforcing Steel Supplier C | Invoice 17652 | 0 | 2874.74
500114 | 2026-08-07 | 202608 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Aug 07 | 26.3 | 2420.97
500522 | 2026-08-07 | 202608 | 24-101 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Aug 07 | 151.5 | 13941.88
500724 | 2026-08-07 | 202608 | 24-101 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Aug 07 | 14.8 | 1053.23
500851 | 2026-08-07 | 202608 | 24-104 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Aug 07 | 250 | 23002.97
501044 | 2026-08-07 | 202608 | 24-104 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Aug 07 | 212.1 | 15062.64
501158 | 2026-08-07 | 202608 | 24-107 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Aug 07 | 100.9 | 9279.26
501419 | 2026-08-07 | 202608 | 25-110 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Aug 07 | 241.6 | 22225.27
501585 | 2026-08-07 | 202608 | 25-110 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Aug 07 | 718 | 50978.07
501665 | 2026-08-07 | 202608 | 25-112 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Aug 07 | 127.3 | 11716.08
501815 | 2026-08-07 | 202608 | 25-112 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Aug 07 | 97.4 | 6914.64
501829 | 2026-08-07 | 202608 | 25-112 | 08-100 | Material | AP | V1055 | Doors Supplier B | Invoice 79504 | 0 | 79168.55
501899 | 2026-08-07 | 202608 | 25-115 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Aug 07 | 121.7 | 11199.42
502044 | 2026-08-07 | 202608 | 25-115 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Aug 07 | 165 | 11716.23
502057 | 2026-08-07 | 202608 | 25-115 | 08-100 | Material | AP | V1065 | Doors Supplier D | Invoice 15061 | 0 | 2209.86
502115 | 2026-08-07 | 202608 | 25-118 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Aug 07 | 355.6 | 32711.2
502236 | 2026-08-07 | 202608 | 25-118 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Aug 07 | 250.2 | 17763.15
502298 | 2026-08-07 | 202608 | 25-121 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Aug 07 | 336.7 | 30978.52
502363 | 2026-08-07 | 202608 | 25-121 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Aug 07 | 153.8 | 11379.04
502441 | 2026-08-07 | 202608 | 26-124 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Aug 07 | 232.5 | 21389.24
502495 | 2026-08-07 | 202608 | 26-124 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Aug 07 | 282.5 | 20903.72
502557 | 2026-08-07 | 202608 | 26-127 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Aug 07 | 232.5 | 21389.06
502594 | 2026-08-07 | 202608 | 26-127 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Aug 07 | 307.6 | 22764.39
502636 | 2026-08-07 | 202608 | 26-130 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Aug 07 | 89.8 | 8263.67
502656 | 2026-08-07 | 202608 | 26-130 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Aug 07 | 95.3 | 7051.48
502058 | 2026-08-08 | 202608 | 25-115 | 08-100 | Material | AP | V1065 | Doors Supplier D | Invoice 98580 | 0 | 2247.55
502139 | 2026-08-08 | 202608 | 25-118 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 79424 | 0 | 25325.3
502248 | 2026-08-08 | 202608 | 25-118 | 08-100 | Material | AP | V1074 | Doors Supplier D | Invoice 67860 | 0 | 8741.2
502397 | 2026-08-08 | 202608 | 25-121 | 03-300 | Material | AP | V1080 | Cast-in-Place Concrete Supplier E | Invoice 62187 | 0 | 43371.99
502383 | 2026-08-10 | 202608 | 25-121 | 03-200 | Material | AP | V1079 | Reinforcing Steel Supplier C | Invoice 53676 | 0 | 6299.52
502461 | 2026-08-10 | 202608 | 26-124 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 35934 | 0 | 12773
502463 | 2026-08-10 | 202608 | 26-124 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 89532 | 0 | 7879.16
501191 | 2026-08-12 | 202608 | 24-107 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 42071 | 0 | 1589.76
502515 | 2026-08-12 | 202608 | 26-124 | 03-200 | Material | AP | V1086 | Reinforcing Steel Supplier A | Invoice 97466 | 0 | 63605.74
502668 | 2026-08-12 | 202608 | 26-130 | 03-300 | Material | AP | V1100 | Cast-in-Place Concrete Supplier B | Invoice 17926 | 0 | 16752.22
502322 | 2026-08-13 | 202608 | 25-121 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 15773 | 0 | 17284.21
502572 | 2026-08-13 | 202608 | 26-127 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 49898 | 0 | 10174.27
502664 | 2026-08-13 | 202608 | 26-130 | 03-200 | Material | AP | V1099 | Reinforcing Steel Supplier C | Invoice 48506 | 0 | 17786.85
500115 | 2026-08-14 | 202608 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Aug 14 | 15.9 | 1458.68
500523 | 2026-08-14 | 202608 | 24-101 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Aug 14 | 132.3 | 12167.59
500725 | 2026-08-14 | 202608 | 24-101 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Aug 14 | 12.3 | 872.76
500852 | 2026-08-14 | 202608 | 24-104 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Aug 14 | 284.1 | 26140.27
501045 | 2026-08-14 | 202608 | 24-104 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Aug 14 | 71.4 | 5071.53
501159 | 2026-08-14 | 202608 | 24-107 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Aug 14 | 92.8 | 8534.29
501420 | 2026-08-14 | 202608 | 25-110 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Aug 14 | 304.7 | 28032.27
501586 | 2026-08-14 | 202608 | 25-110 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Aug 14 | 319.7 | 22698.39
501666 | 2026-08-14 | 202608 | 25-112 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Aug 14 | 187.3 | 17234.61
501816 | 2026-08-14 | 202608 | 25-112 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Aug 14 | 83.3 | 5914.94
501900 | 2026-08-14 | 202608 | 25-115 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Aug 14 | 354.1 | 32573.37
502045 | 2026-08-14 | 202608 | 25-115 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Aug 14 | 623.1 | 44237.12
502116 | 2026-08-14 | 202608 | 25-118 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Aug 14 | 395.6 | 36396.38
502237 | 2026-08-14 | 202608 | 25-118 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Aug 14 | 447.2 | 31750.98
502299 | 2026-08-14 | 202608 | 25-121 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Aug 14 | 379.7 | 34932.29
502364 | 2026-08-14 | 202608 | 25-121 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Aug 14 | 153.4 | 11349.86
502442 | 2026-08-14 | 202608 | 26-124 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Aug 14 | 290.7 | 26742.33
502496 | 2026-08-14 | 202608 | 26-124 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Aug 14 | 600.7 | 44454.8
502513 | 2026-08-14 | 202608 | 26-124 | 03-200 | Material | AP | V1086 | Reinforcing Steel Supplier A | Invoice 90333 | 0 | 47120.31
502558 | 2026-08-14 | 202608 | 26-127 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Aug 14 | 180.7 | 16625.34
502595 | 2026-08-14 | 202608 | 26-127 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Aug 14 | 639.6 | 47331.81
502637 | 2026-08-14 | 202608 | 26-130 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Aug 14 | 54.5 | 5016.26
502657 | 2026-08-14 | 202608 | 26-130 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Aug 14 | 30.7 | 2272
500892 | 2026-08-15 | 202608 | 24-104 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 67288 | 0 | 12242.32
501189 | 2026-08-15 | 202608 | 24-107 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 11355 | 0 | 2405.46
501451 | 2026-08-15 | 202608 | 25-110 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 53353 | 0 | 60199.63
502573 | 2026-08-15 | 202608 | 26-127 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 73558 | 0 | 5822.05
502056 | 2026-08-16 | 202608 | 25-115 | 08-100 | Material | AP | V1065 | Doors Supplier D | Invoice 62796 | 0 | 982.25
502527 | 2026-08-16 | 202608 | 26-124 | 03-300 | Material | AP | V1087 | Cast-in-Place Concrete Supplier B | Invoice 83368 | 0 | 116454.55
502607 | 2026-08-16 | 202608 | 26-127 | 03-200 | Material | AP | V1092 | Reinforcing Steel Supplier C | Invoice 67911 | 0 | 18226.11
500171 | 2026-08-17 | 202608 | 23-098 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 90461 | 0 | 817
501190 | 2026-08-17 | 202608 | 24-107 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 66383 | 0 | 3398.87
502606 | 2026-08-17 | 202608 | 26-127 | 03-200 | Material | AP | V1092 | Reinforcing Steel Supplier C | Invoice 64414 | 0 | 53600.82
502608 | 2026-08-17 | 202608 | 26-127 | 03-200 | Material | AP | V1092 | Reinforcing Steel Supplier C | Invoice 78768 | 0 | 18679.99
500567 | 2026-08-18 | 202608 | 24-101 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 93508 | 0 | 7762.2
501334 | 2026-08-18 | 202608 | 24-107 | 08-100 | Material | AP | V1035 | Doors Supplier D | Invoice 12009 | 0 | 9668
502399 | 2026-08-18 | 202608 | 25-121 | 03-300 | Material | AP | V1080 | Cast-in-Place Concrete Supplier E | Invoice 38362 | 0 | 86804.15
502514 | 2026-08-18 | 202608 | 26-124 | 03-200 | Material | AP | V1086 | Reinforcing Steel Supplier A | Invoice 95240 | 0 | 11784.22
501066 | 2026-08-19 | 202608 | 24-104 | 08-100 | Material | AP | V1026 | Doors Supplier B | Invoice 83144 | 0 | 154770.26
502646 | 2026-08-19 | 202608 | 26-130 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 99270 | 0 | 5620.44
500891 | 2026-08-20 | 202608 | 24-104 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 59890 | 0 | 8750.16
501335 | 2026-08-20 | 202608 | 24-107 | 08-100 | Material | AP | V1035 | Doors Supplier D | Invoice 79798 | 0 | 10417.05
501830 | 2026-08-20 | 202608 | 25-112 | 08-100 | Material | AP | V1055 | Doors Supplier B | Invoice 83465 | 0 | 37588.83
500116 | 2026-08-21 | 202608 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Aug 21 | 33.1 | 3042.51
500170 | 2026-08-21 | 202608 | 23-098 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 33984 | 0 | 1004.38
500524 | 2026-08-21 | 202608 | 24-101 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Aug 21 | 66.7 | 6139.67
500726 | 2026-08-21 | 202608 | 24-101 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Aug 21 | 15.9 | 1128.51
500749 | 2026-08-21 | 202608 | 24-101 | 08-100 | Material | AP | V1016 | Doors Supplier F | Invoice 74021 | 0 | 31694.76
500853 | 2026-08-21 | 202608 | 24-104 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Aug 21 | 116.8 | 10748.94
501046 | 2026-08-21 | 202608 | 24-104 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Aug 21 | 93.5 | 6636.34
501160 | 2026-08-21 | 202608 | 24-107 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Aug 21 | 34 | 3131.74
501421 | 2026-08-21 | 202608 | 25-110 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Aug 21 | 586.6 | 53966.17
501587 | 2026-08-21 | 202608 | 25-110 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Aug 21 | 543 | 38552.14
501667 | 2026-08-21 | 202608 | 25-112 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Aug 21 | 95.2 | 8755.46
501817 | 2026-08-21 | 202608 | 25-112 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Aug 21 | 98.8 | 7015.85
501901 | 2026-08-21 | 202608 | 25-115 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Aug 21 | 300.7 | 27663.93
502046 | 2026-08-21 | 202608 | 25-115 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Aug 21 | 288.4 | 20476.69
502117 | 2026-08-21 | 202608 | 25-118 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Aug 21 | 491.7 | 45240.83
502238 | 2026-08-21 | 202608 | 25-118 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Aug 21 | 336.2 | 23866.98
502300 | 2026-08-21 | 202608 | 25-121 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Aug 21 | 255.5 | 23501.91
502365 | 2026-08-21 | 202608 | 25-121 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Aug 21 | 922 | 68231.62
502384 | 2026-08-21 | 202608 | 25-121 | 03-200 | Material | AP | V1079 | Reinforcing Steel Supplier C | Invoice 99099 | 0 | 30415.33
502443 | 2026-08-21 | 202608 | 26-124 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Aug 21 | 180.6 | 16614.58
502497 | 2026-08-21 | 202608 | 26-124 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Aug 21 | 422.5 | 31261.57
502559 | 2026-08-21 | 202608 | 26-127 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Aug 21 | 57.6 | 5298.36
502596 | 2026-08-21 | 202608 | 26-127 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Aug 21 | 529.6 | 39193.17
502638 | 2026-08-21 | 202608 | 26-130 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Aug 21 | 71.3 | 6559.34
502658 | 2026-08-21 | 202608 | 26-130 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Aug 21 | 93 | 6883.78
501333 | 2026-08-22 | 202608 | 24-107 | 08-100 | Material | AP | V1035 | Doors Supplier D | Invoice 95975 | 0 | 4543.87
501703 | 2026-08-22 | 202608 | 25-112 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 60452 | 0 | 8454.25
501702 | 2026-08-23 | 202608 | 25-112 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 84004 | 0 | 4850.8
500565 | 2026-08-24 | 202608 | 24-101 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 76756 | 0 | 15073.73
500566 | 2026-08-24 | 202608 | 24-101 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 37641 | 0 | 10397.27
500428 | 2026-08-25 | 202608 | 23-098 | 15-000 | Subcontract | AP | V1009 | Mechanical Subcontractor B | Progress claim Aug 2026 | 0 | 3665.15
500447 | 2026-08-25 | 202608 | 23-098 | 16-000 | Subcontract | AP | V1010 | Electrical Subcontractor C | Progress claim Aug 2026 | 0 | 2178
500757 | 2026-08-25 | 202608 | 24-101 | 09-200 | Subcontract | AP | V1017 | Drywall Subcontractor B | Progress claim Aug 2026 | 0 | 155232.21
500770 | 2026-08-25 | 202608 | 24-101 | 15-000 | Subcontract | AP | V1018 | Mechanical Subcontractor F | Progress claim Aug 2026 | 0 | 174743.52
500783 | 2026-08-25 | 202608 | 24-101 | 16-000 | Subcontract | AP | V1019 | Electrical Subcontractor G | Progress claim Aug 2026 | 0 | 160430.76
501073 | 2026-08-25 | 202608 | 24-104 | 09-200 | Subcontract | AP | V1027 | Drywall Subcontractor F | Progress claim Aug 2026 | 0 | 387616.07
501084 | 2026-08-25 | 202608 | 24-104 | 15-000 | Subcontract | AP | V1028 | Mechanical Subcontractor B | Progress claim Aug 2026 | 0 | 217656.57
501095 | 2026-08-25 | 202608 | 24-104 | 16-000 | Subcontract | AP | V1029 | Electrical Subcontractor F | Progress claim Aug 2026 | 0 | 175725.18
501342 | 2026-08-25 | 202608 | 24-107 | 09-200 | Subcontract | AP | V1036 | Drywall Subcontractor F | Progress claim Aug 2026 | 0 | 49828.19
501353 | 2026-08-25 | 202608 | 24-107 | 15-000 | Subcontract | AP | V1037 | Mechanical Subcontractor A | Progress claim Aug 2026 | 0 | 64931.65
501364 | 2026-08-25 | 202608 | 24-107 | 16-000 | Subcontract | AP | V1038 | Electrical Subcontractor A | Progress claim Aug 2026 | 0 | 67908.92
501556 | 2026-08-25 | 202608 | 25-110 | 04-200 | Subcontract | AP | V1042 | Masonry Subcontractor G | Progress claim Aug 2026 | 0 | 107855.6
501565 | 2026-08-25 | 202608 | 25-110 | 05-100 | Subcontract | AP | V1043 | Structural Steel Subcontractor E | Progress claim Aug 2026 | 0 | 11111.29
501596 | 2026-08-25 | 202608 | 25-110 | 07-200 | Subcontract | AP | V1044 | Roofing Subcontractor D | Progress claim Aug 2026 | 0 | 415650.87
501607 | 2026-08-25 | 202608 | 25-110 | 15-000 | Subcontract | AP | V1047 | Mechanical Subcontractor B | Progress claim Aug 2026 | 0 | 305006.47
501615 | 2026-08-25 | 202608 | 25-110 | 16-000 | Subcontract | AP | V1048 | Electrical Subcontractor E | Progress claim Aug 2026 | 0 | 305262.23
501835 | 2026-08-25 | 202608 | 25-112 | 09-200 | Subcontract | AP | V1056 | Drywall Subcontractor E | Progress claim Aug 2026 | 0 | 288112.7
501844 | 2026-08-25 | 202608 | 25-112 | 15-000 | Subcontract | AP | V1057 | Mechanical Subcontractor E | Progress claim Aug 2026 | 0 | 161681.37
501853 | 2026-08-25 | 202608 | 25-112 | 16-000 | Subcontract | AP | V1058 | Electrical Subcontractor G | Progress claim Aug 2026 | 0 | 105076.98
502022 | 2026-08-25 | 202608 | 25-115 | 04-200 | Subcontract | AP | V1062 | Masonry Subcontractor G | Progress claim Aug 2026 | 0 | 143593.67
502054 | 2026-08-25 | 202608 | 25-115 | 07-200 | Subcontract | AP | V1064 | Roofing Subcontractor B | Progress claim Aug 2026 | 0 | 251829.55
502060 | 2026-08-25 | 202608 | 25-115 | 09-200 | Subcontract | AP | V1066 | Drywall Subcontractor F | Progress claim Aug 2026 | 0 | 9357.94
502067 | 2026-08-25 | 202608 | 25-115 | 15-000 | Subcontract | AP | V1067 | Mechanical Subcontractor C | Progress claim Aug 2026 | 0 | 308859.19
502074 | 2026-08-25 | 202608 | 25-115 | 16-000 | Subcontract | AP | V1068 | Electrical Subcontractor D | Progress claim Aug 2026 | 0 | 147137.4
502138 | 2026-08-25 | 202608 | 25-118 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 80302 | 0 | 10835.19
502246 | 2026-08-25 | 202608 | 25-118 | 07-200 | Subcontract | AP | V1073 | Roofing Subcontractor A | Progress claim Aug 2026 | 0 | 359913.88
502251 | 2026-08-25 | 202608 | 25-118 | 09-200 | Subcontract | AP | V1075 | Drywall Subcontractor G | Progress claim Aug 2026 | 0 | 13837.77
502258 | 2026-08-25 | 202608 | 25-118 | 15-000 | Subcontract | AP | V1076 | Mechanical Subcontractor E | Progress claim Aug 2026 | 0 | 460644.34
502265 | 2026-08-25 | 202608 | 25-118 | 16-000 | Subcontract | AP | V1077 | Electrical Subcontractor A | Progress claim Aug 2026 | 0 | 302389.74
502321 | 2026-08-25 | 202608 | 25-121 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 10209 | 0 | 28505.11
502398 | 2026-08-25 | 202608 | 25-121 | 03-300 | Material | AP | V1080 | Cast-in-Place Concrete Supplier E | Invoice 48480 | 0 | 41426.64
502403 | 2026-08-25 | 202608 | 25-121 | 04-200 | Subcontract | AP | V1081 | Masonry Subcontractor E | Progress claim Aug 2026 | 0 | 61160.96
502407 | 2026-08-25 | 202608 | 25-121 | 05-100 | Subcontract | AP | V1082 | Structural Steel Subcontractor F | Progress claim Aug 2026 | 0 | 214816.07
502414 | 2026-08-25 | 202608 | 25-121 | 15-000 | Subcontract | AP | V1083 | Mechanical Subcontractor E | Progress claim Aug 2026 | 0 | 76799.58
502417 | 2026-08-25 | 202608 | 25-121 | 16-000 | Subcontract | AP | V1084 | Electrical Subcontractor F | Progress claim Aug 2026 | 0 | 84408.48
502531 | 2026-08-25 | 202608 | 26-124 | 05-100 | Subcontract | AP | V1088 | Structural Steel Subcontractor B | Progress claim Aug 2026 | 0 | 459248.31
502538 | 2026-08-25 | 202608 | 26-124 | 15-000 | Subcontract | AP | V1089 | Mechanical Subcontractor C | Progress claim Aug 2026 | 0 | 73732.46
502541 | 2026-08-25 | 202608 | 26-124 | 16-000 | Subcontract | AP | V1090 | Electrical Subcontractor C | Progress claim Aug 2026 | 0 | 67561.07
502583 | 2026-08-25 | 202608 | 26-127 | 02-200 | Subcontract | AP | V1091 | Earthwork Subcontractor A | Progress claim Aug 2026 | 0 | 2292.63
502616 | 2026-08-25 | 202608 | 26-127 | 03-300 | Material | AP | V1093 | Cast-in-Place Concrete Supplier A | Invoice 80534 | 0 | 183654.62
502621 | 2026-08-25 | 202608 | 26-127 | 05-100 | Subcontract | AP | V1095 | Structural Steel Subcontractor D | Progress claim Aug 2026 | 0 | 86256.67
502627 | 2026-08-25 | 202608 | 26-127 | 15-000 | Subcontract | AP | V1096 | Mechanical Subcontractor B | Progress claim Aug 2026 | 0 | 11686.52
502629 | 2026-08-25 | 202608 | 26-127 | 16-000 | Subcontract | AP | V1097 | Electrical Subcontractor F | Progress claim Aug 2026 | 0 | 8383.98
502654 | 2026-08-25 | 202608 | 26-130 | 02-200 | Subcontract | AP | V1098 | Earthwork Subcontractor D | Progress claim Aug 2026 | 0 | 100386.71
500172 | 2026-08-26 | 202608 | 23-098 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 37547 | 0 | 2204.38
502528 | 2026-08-26 | 202608 | 26-124 | 03-300 | Material | AP | V1087 | Cast-in-Place Concrete Supplier B | Invoice 45100 | 0 | 47362.64
502462 | 2026-08-27 | 202608 | 26-124 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 29002 | 0 | 3455.54
500117 | 2026-08-28 | 202608 | 23-098 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Aug 28 | 35.8 | 3294.57
500525 | 2026-08-28 | 202608 | 24-101 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Aug 28 | 145.7 | 13405.58
500727 | 2026-08-28 | 202608 | 24-101 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Aug 28 | 4.3 | 307.64
500854 | 2026-08-28 | 202608 | 24-104 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Aug 28 | 100 | 9200.51
501047 | 2026-08-28 | 202608 | 24-104 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Aug 28 | 328.1 | 23292
501161 | 2026-08-28 | 202608 | 24-107 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Aug 28 | 89.5 | 8230.27
501422 | 2026-08-28 | 202608 | 25-110 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Aug 28 | 282.6 | 25998.23
501588 | 2026-08-28 | 202608 | 25-110 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Aug 28 | 869.7 | 61752.06
501668 | 2026-08-28 | 202608 | 25-112 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Aug 28 | 115.9 | 10661.64
501818 | 2026-08-28 | 202608 | 25-112 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Aug 28 | 37.5 | 2661.59
501902 | 2026-08-28 | 202608 | 25-115 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Aug 28 | 239.5 | 22037.24
502047 | 2026-08-28 | 202608 | 25-115 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Aug 28 | 417.1 | 29612.4
502118 | 2026-08-28 | 202608 | 25-118 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Aug 28 | 127.9 | 11763.25
502239 | 2026-08-28 | 202608 | 25-118 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Aug 28 | 209.3 | 14862.77
502301 | 2026-08-28 | 202608 | 25-121 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Aug 28 | 289.2 | 26609.71
502366 | 2026-08-28 | 202608 | 25-121 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Aug 28 | 338.5 | 25050.64
502444 | 2026-08-28 | 202608 | 26-124 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Aug 28 | 163.5 | 15043.35
502498 | 2026-08-28 | 202608 | 26-124 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Aug 28 | 253.8 | 18778.12
502560 | 2026-08-28 | 202608 | 26-127 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Aug 28 | 104.2 | 9583.72
502597 | 2026-08-28 | 202608 | 26-127 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Aug 28 | 200.4 | 14828.24
502639 | 2026-08-28 | 202608 | 26-130 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Aug 28 | 38 | 3497.59
502659 | 2026-08-28 | 202608 | 26-130 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Aug 28 | 116.5 | 8621.95
500587 | 2026-08-31 | 202608 | 24-101 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 16409.07
500909 | 2026-08-31 | 202608 | 24-104 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 10879.8
501209 | 2026-08-31 | 202608 | 24-107 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 2885.41
501467 | 2026-08-31 | 202608 | 25-110 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 41436.21
501718 | 2026-08-31 | 202608 | 25-112 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 11483.34
501943 | 2026-08-31 | 202608 | 25-115 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 23424.73
502152 | 2026-08-31 | 202608 | 25-118 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 71491.21
502333 | 2026-08-31 | 202608 | 25-121 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 58624.63
502470 | 2026-08-31 | 202608 | 26-124 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 77845.56
502578 | 2026-08-31 | 202608 | 26-127 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 27714.6
502651 | 2026-08-31 | 202608 | 26-130 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 6868.16
501067 | 2026-09-03 | 202609 | 24-104 | 08-100 | Material | AP | V1026 | Doors Supplier B | Invoice 29876 | 0 | 55191.59
501765 | 2026-09-03 | 202609 | 25-112 | 03-200 | Material | AP | V1050 | Reinforcing Steel Supplier A | Invoice 65548 | 0 | 0.01
502059 | 2026-09-03 | 202609 | 25-115 | 08-100 | Material | AP | V1065 | Doors Supplier D | Invoice 67158 | 0 | 41352.98
500173 | 2026-09-04 | 202609 | 23-098 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 18883 | 0 | 0.01
500526 | 2026-09-04 | 202609 | 24-101 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Sep 04 | 104.6 | 9619.2
500728 | 2026-09-04 | 202609 | 24-101 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Sep 04 | 0 | 0.01
500855 | 2026-09-04 | 202609 | 24-104 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Sep 04 | 102.9 | 9462.61
501048 | 2026-09-04 | 202609 | 24-104 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Sep 04 | 96.4 | 6845.98
501162 | 2026-09-04 | 202609 | 24-107 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Sep 04 | 38.5 | 3538.76
501423 | 2026-09-04 | 202609 | 25-110 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Sep 04 | 149.8 | 13777.9
501589 | 2026-09-04 | 202609 | 25-110 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Sep 04 | 744.9 | 52887.12
501599 | 2026-09-04 | 202609 | 25-110 | 08-100 | Material | AP | V1045 | Doors Supplier B | Invoice 14185 | 0 | 11967.5
501669 | 2026-09-04 | 202609 | 25-112 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Sep 04 | 70.3 | 6469.83
501903 | 2026-09-04 | 202609 | 25-115 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Sep 04 | 140.1 | 12886.42
502048 | 2026-09-04 | 202609 | 25-115 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Sep 04 | 575.4 | 40853.68
502119 | 2026-09-04 | 202609 | 25-118 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Sep 04 | 157.3 | 14469.34
502189 | 2026-09-04 | 202609 | 25-118 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Sep 04 | 0 | 0
502240 | 2026-09-04 | 202609 | 25-118 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Sep 04 | 294.5 | 20908.92
502302 | 2026-09-04 | 202609 | 25-121 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Sep 04 | 194 | 17848.03
502367 | 2026-09-04 | 202609 | 25-121 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Sep 04 | 219.9 | 16272.66
502409 | 2026-09-04 | 202609 | 25-121 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Sep 04 | 182.7 | 12973.87
502445 | 2026-09-04 | 202609 | 26-124 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Sep 04 | 162.9 | 14984.69
502499 | 2026-09-04 | 202609 | 26-124 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Sep 04 | 401.1 | 29678.05
502533 | 2026-09-04 | 202609 | 26-124 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Sep 04 | 34.8 | 2470.04
502561 | 2026-09-04 | 202609 | 26-127 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Sep 04 | 307.2 | 28265.46
502598 | 2026-09-04 | 202609 | 26-127 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Sep 04 | 164.7 | 12184.51
502619 | 2026-09-04 | 202609 | 26-127 | 03-300 | Material | AP | V1093 | Cast-in-Place Concrete Supplier A | Invoice 25185 | 0 | 47440.81
502623 | 2026-09-04 | 202609 | 26-127 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Sep 04 | 6.9 | 486.94
502640 | 2026-09-04 | 202609 | 26-130 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Sep 04 | 44.1 | 4061.13
502660 | 2026-09-04 | 202609 | 26-130 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Sep 04 | 170.1 | 12585.61
501453 | 2026-09-05 | 202609 | 25-110 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 98220 | 0 | 19641.4
501704 | 2026-09-05 | 202609 | 25-112 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 26629 | 0 | 1987.56
501997 | 2026-09-05 | 202609 | 25-115 | 03-200 | Material | AP | V1060 | Reinforcing Steel Supplier B | Invoice 79940 | 0 | 0.01
502610 | 2026-09-05 | 202609 | 26-127 | 03-200 | Material | AP | V1092 | Reinforcing Steel Supplier C | Invoice 17325 | 0 | 7487.59
500398 | 2026-09-06 | 202609 | 23-098 | 08-100 | Material | AP | V1007 | Doors Supplier G | Invoice 53750 | 0 | 0.01
501932 | 2026-09-06 | 202609 | 25-115 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 98943 | 0 | 3388.7
502141 | 2026-09-06 | 202609 | 25-118 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 65585 | 0 | 13423.07
502325 | 2026-09-06 | 202609 | 25-121 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 66265 | 0 | 16868.95
502529 | 2026-09-06 | 202609 | 26-124 | 03-300 | Material | AP | V1087 | Cast-in-Place Concrete Supplier B | Invoice 76311 | 0 | 99894.41
501454 | 2026-09-07 | 202609 | 25-110 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 37334 | 0 | 5141.9
501831 | 2026-09-07 | 202609 | 25-112 | 08-100 | Material | AP | V1055 | Doors Supplier B | Invoice 53060 | 0 | 46271.18
501930 | 2026-09-07 | 202609 | 25-115 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 40764 | 0 | 4934.86
501931 | 2026-09-07 | 202609 | 25-115 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 18874 | 0 | 18605
502323 | 2026-09-07 | 202609 | 25-121 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 82207 | 0 | 21936.51
502649 | 2026-09-07 | 202609 | 26-130 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 83451 | 0 | 2639.73
501598 | 2026-09-08 | 202609 | 25-110 | 08-100 | Material | AP | V1045 | Doors Supplier B | Invoice 73438 | 0 | 25308.34
502387 | 2026-09-08 | 202609 | 25-121 | 03-200 | Material | AP | V1079 | Reinforcing Steel Supplier C | Invoice 52336 | 0 | 4812.95
502400 | 2026-09-08 | 202609 | 25-121 | 03-300 | Material | AP | V1080 | Cast-in-Place Concrete Supplier E | Invoice 60917 | 0 | 42660.28
502464 | 2026-09-08 | 202609 | 26-124 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 80862 | 0 | 33948.38
502669 | 2026-09-08 | 202609 | 26-130 | 03-300 | Material | AP | V1100 | Cast-in-Place Concrete Supplier B | Invoice 20238 | 0 | 42127.32
500893 | 2026-09-09 | 202609 | 24-104 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 32187 | 0 | 18840.25
501706 | 2026-09-09 | 202609 | 25-112 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 93853 | 0 | 1503.14
502401 | 2026-09-09 | 202609 | 25-121 | 03-300 | Material | AP | V1080 | Cast-in-Place Concrete Supplier E | Invoice 81201 | 0 | 28561.12
502574 | 2026-09-09 | 202609 | 26-127 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 41092 | 0 | 21483.6
500399 | 2026-09-11 | 202609 | 23-098 | 08-100 | Material | AP | V1007 | Doors Supplier G | Invoice 92302 | 0 | 0.01
500527 | 2026-09-11 | 202609 | 24-101 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Sep 11 | 54.7 | 5036.69
500729 | 2026-09-11 | 202609 | 24-101 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Sep 11 | 0 | 0
500752 | 2026-09-11 | 202609 | 24-101 | 08-100 | Material | AP | V1016 | Doors Supplier F | Invoice 19679 | 0 | 1179.07
500856 | 2026-09-11 | 202609 | 24-104 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Sep 11 | 204.9 | 18850.21
501049 | 2026-09-11 | 202609 | 24-104 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Sep 11 | 39.2 | 2783.44
501163 | 2026-09-11 | 202609 | 24-107 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Sep 11 | 61.7 | 5680.06
501424 | 2026-09-11 | 202609 | 25-110 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Sep 11 | 440.3 | 40508.78
501590 | 2026-09-11 | 202609 | 25-110 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Sep 11 | 545.1 | 38704.72
501670 | 2026-09-11 | 202609 | 25-112 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Sep 11 | 116.9 | 10757.55
501764 | 2026-09-11 | 202609 | 25-112 | 03-200 | Material | AP | V1050 | Reinforcing Steel Supplier A | Invoice 19899 | 0 | 0
501904 | 2026-09-11 | 202609 | 25-115 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Sep 11 | 227.8 | 20956.63
502049 | 2026-09-11 | 202609 | 25-115 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Sep 11 | 432.7 | 30719.55
502120 | 2026-09-11 | 202609 | 25-118 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Sep 11 | 307.8 | 28315.42
502190 | 2026-09-11 | 202609 | 25-118 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Sep 11 | 0 | 0
502241 | 2026-09-11 | 202609 | 25-118 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Sep 11 | 175.7 | 12474.37
502303 | 2026-09-11 | 202609 | 25-121 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Sep 11 | 370.3 | 34071.31
502368 | 2026-09-11 | 202609 | 25-121 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Sep 11 | 284.1 | 21026.03
502410 | 2026-09-11 | 202609 | 25-121 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Sep 11 | 244.2 | 17336.12
502446 | 2026-09-11 | 202609 | 26-124 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Sep 11 | 328.8 | 30252.55
502500 | 2026-09-11 | 202609 | 26-124 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Sep 11 | 98.1 | 7261
502534 | 2026-09-11 | 202609 | 26-124 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Sep 11 | 29.3 | 2077.45
502562 | 2026-09-11 | 202609 | 26-127 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Sep 11 | 156.1 | 14362.15
502599 | 2026-09-11 | 202609 | 26-127 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Sep 11 | 77.6 | 5738.81
502609 | 2026-09-11 | 202609 | 26-127 | 03-200 | Material | AP | V1092 | Reinforcing Steel Supplier C | Invoice 37253 | 0 | 24309.97
502624 | 2026-09-11 | 202609 | 26-127 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Sep 11 | 3.3 | 234.22
502641 | 2026-09-11 | 202609 | 26-130 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Sep 11 | 98.5 | 9061.52
502648 | 2026-09-11 | 202609 | 26-130 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 72995 | 0 | 6959.28
502661 | 2026-09-11 | 202609 | 26-130 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Sep 11 | 411.9 | 30480.32
501192 | 2026-09-12 | 202609 | 24-107 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 78712 | 0 | 1244.99
500569 | 2026-09-13 | 202609 | 24-101 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 33916 | 0 | 8853.03
501781 | 2026-09-13 | 202609 | 25-112 | 03-300 | Material | AP | V1051 | Cast-in-Place Concrete Supplier F | Invoice 78724 | 0 | 0
502250 | 2026-09-13 | 202609 | 25-118 | 08-100 | Material | AP | V1074 | Doors Supplier D | Invoice 26923 | 0 | 27747.29
502517 | 2026-09-13 | 202609 | 26-124 | 03-200 | Material | AP | V1086 | Reinforcing Steel Supplier A | Invoice 64368 | 0 | 18676.19
502618 | 2026-09-13 | 202609 | 26-127 | 03-300 | Material | AP | V1093 | Cast-in-Place Concrete Supplier A | Invoice 18222 | 0 | 28847.55
502386 | 2026-09-14 | 202609 | 25-121 | 03-200 | Material | AP | V1079 | Reinforcing Steel Supplier C | Invoice 57605 | 0 | 6426.52
500998 | 2026-09-15 | 202609 | 24-104 | 03-300 | Material | AP | V1022 | Cast-in-Place Concrete Supplier F | Invoice 64605 | 0 | 0
501194 | 2026-09-15 | 202609 | 24-107 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 80343 | 0 | 2127.3
502140 | 2026-09-15 | 202609 | 25-118 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 23275 | 0 | 18369.98
502324 | 2026-09-15 | 202609 | 25-121 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 60494 | 0 | 17925.34
502667 | 2026-09-15 | 202609 | 26-130 | 03-200 | Material | AP | V1099 | Reinforcing Steel Supplier C | Invoice 53432 | 0 | 23905.62
500568 | 2026-09-16 | 202609 | 24-101 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 53761 | 0 | 11467.59
500297 | 2026-09-17 | 202609 | 23-098 | 03-300 | Material | AP | V1003 | Cast-in-Place Concrete Supplier G | Invoice 45024 | 0 | 0.01
501193 | 2026-09-17 | 202609 | 24-107 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 24231 | 0 | 2151.05
502617 | 2026-09-17 | 202609 | 26-127 | 03-300 | Material | AP | V1093 | Cast-in-Place Concrete Supplier A | Invoice 11546 | 0 | 42932.22
502666 | 2026-09-17 | 202609 | 26-130 | 03-200 | Material | AP | V1099 | Reinforcing Steel Supplier C | Invoice 12287 | 0 | 34745.01
500298 | 2026-09-18 | 202609 | 23-098 | 03-300 | Material | AP | V1003 | Cast-in-Place Concrete Supplier G | Invoice 49685 | 0 | 0
500528 | 2026-09-18 | 202609 | 24-101 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Sep 18 | 158.4 | 14572.68
500730 | 2026-09-18 | 202609 | 24-101 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Sep 18 | 0 | 0
500751 | 2026-09-18 | 202609 | 24-101 | 08-100 | Material | AP | V1016 | Doors Supplier F | Invoice 15632 | 0 | 20045.15
500857 | 2026-09-18 | 202609 | 24-104 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Sep 18 | 127.5 | 11726.59
501050 | 2026-09-18 | 202609 | 24-104 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Sep 18 | 104.1 | 7391.13
501164 | 2026-09-18 | 202609 | 24-107 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Sep 18 | 70.3 | 6464.41
501425 | 2026-09-18 | 202609 | 25-110 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Sep 18 | 432.5 | 39793.43
501591 | 2026-09-18 | 202609 | 25-110 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Sep 18 | 549.9 | 39041.5
501671 | 2026-09-18 | 202609 | 25-112 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Sep 18 | 159.6 | 14687.41
501705 | 2026-09-18 | 202609 | 25-112 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 77442 | 0 | 6342.41
501905 | 2026-09-18 | 202609 | 25-115 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Sep 18 | 332 | 30545.12
502050 | 2026-09-18 | 202609 | 25-115 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Sep 18 | 262.2 | 18617.2
502121 | 2026-09-18 | 202609 | 25-118 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Sep 18 | 350.9 | 32283.38
502191 | 2026-09-18 | 202609 | 25-118 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Sep 18 | 0 | 0
502242 | 2026-09-18 | 202609 | 25-118 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Sep 18 | 266.3 | 18906.8
502304 | 2026-09-18 | 202609 | 25-121 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Sep 18 | 203.8 | 18747.66
502369 | 2026-09-18 | 202609 | 25-121 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Sep 18 | 147.7 | 10930.1
502411 | 2026-09-18 | 202609 | 25-121 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Sep 18 | 72.5 | 5149.73
502447 | 2026-09-18 | 202609 | 26-124 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Sep 18 | 80.9 | 7441.94
502501 | 2026-09-18 | 202609 | 26-124 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Sep 18 | 53.9 | 3986.92
502535 | 2026-09-18 | 202609 | 26-124 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Sep 18 | 51.9 | 3682.87
502563 | 2026-09-18 | 202609 | 26-127 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Sep 18 | 120.3 | 11069.9
502600 | 2026-09-18 | 202609 | 26-127 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Sep 18 | 246.9 | 18273.61
502625 | 2026-09-18 | 202609 | 26-127 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Sep 18 | 15 | 1068.39
502642 | 2026-09-18 | 202609 | 26-130 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Sep 18 | 75.1 | 6906.14
502662 | 2026-09-18 | 202609 | 26-130 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Sep 18 | 53.3 | 3941.92
501068 | 2026-09-19 | 202609 | 24-104 | 08-100 | Material | AP | V1026 | Doors Supplier B | Invoice 67239 | 0 | 63605.61
501452 | 2026-09-20 | 202609 | 25-110 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 97698 | 0 | 35778.24
502402 | 2026-09-20 | 202609 | 25-121 | 03-300 | Material | AP | V1080 | Cast-in-Place Concrete Supplier E | Invoice 36567 | 0 | 22505.93
500656 | 2026-09-21 | 202609 | 24-101 | 03-200 | Material | AP | V1012 | Reinforcing Steel Supplier E | Invoice 92479 | 0 | 0
501337 | 2026-09-21 | 202609 | 24-107 | 08-100 | Material | AP | V1035 | Doors Supplier D | Invoice 63832 | 0 | 5447.67
501780 | 2026-09-21 | 202609 | 25-112 | 03-300 | Material | AP | V1051 | Cast-in-Place Concrete Supplier F | Invoice 76769 | 0 | 0.01
501832 | 2026-09-21 | 202609 | 25-112 | 08-100 | Material | AP | V1055 | Doors Supplier B | Invoice 38565 | 0 | 31863.27
500655 | 2026-09-22 | 202609 | 24-101 | 03-200 | Material | AP | V1012 | Reinforcing Steel Supplier E | Invoice 47761 | 0 | 0.01
501069 | 2026-09-22 | 202609 | 24-104 | 08-100 | Material | AP | V1026 | Doors Supplier B | Invoice 16419 | 0 | 34495.33
502516 | 2026-09-22 | 202609 | 26-124 | 03-200 | Material | AP | V1086 | Reinforcing Steel Supplier A | Invoice 74585 | 0 | 12688.38
500973 | 2026-09-23 | 202609 | 24-104 | 03-200 | Material | AP | V1021 | Reinforcing Steel Supplier D | Invoice 63080 | 0 | 0
500997 | 2026-09-23 | 202609 | 24-104 | 03-300 | Material | AP | V1022 | Cast-in-Place Concrete Supplier F | Invoice 21337 | 0 | 0.01
501763 | 2026-09-24 | 202609 | 25-112 | 03-200 | Material | AP | V1050 | Reinforcing Steel Supplier A | Invoice 18632 | 0 | 0
502142 | 2026-09-24 | 202609 | 25-118 | 01-200 | Other | AP | V0999 | Site Services Vendor | Invoice 35568 | 0 | 5702.02
502388 | 2026-09-24 | 202609 | 25-121 | 03-200 | Material | AP | V1079 | Reinforcing Steel Supplier C | Invoice 92360 | 0 | 2458.94
500204 | 2026-09-25 | 202609 | 23-098 | 02-200 | Subcontract | AP | V1001 | Earthwork Subcontractor A | Progress claim Sep 2026 | 0 | 0.02
500308 | 2026-09-25 | 202609 | 23-098 | 04-200 | Subcontract | AP | V1004 | Masonry Subcontractor A | Progress claim Sep 2026 | 0 | 0.01
500377 | 2026-09-25 | 202609 | 23-098 | 07-200 | Subcontract | AP | V1006 | Roofing Subcontractor B | Progress claim Sep 2026 | 0 | 0.01
500529 | 2026-09-25 | 202609 | 24-101 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Sep 25 | 95.5 | 8784.36
500595 | 2026-09-25 | 202609 | 24-101 | 02-200 | Subcontract | AP | V1011 | Earthwork Subcontractor A | Progress claim Sep 2026 | 0 | 0.01
500731 | 2026-09-25 | 202609 | 24-101 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Sep 25 | 0 | 0
500758 | 2026-09-25 | 202609 | 24-101 | 09-200 | Subcontract | AP | V1017 | Drywall Subcontractor B | Progress claim Sep 2026 | 0 | 114475.43
500771 | 2026-09-25 | 202609 | 24-101 | 15-000 | Subcontract | AP | V1018 | Mechanical Subcontractor F | Progress claim Sep 2026 | 0 | 118949.22
500784 | 2026-09-25 | 202609 | 24-101 | 16-000 | Subcontract | AP | V1019 | Electrical Subcontractor G | Progress claim Sep 2026 | 0 | 133731.5
500858 | 2026-09-25 | 202609 | 24-104 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Sep 25 | 183.4 | 16871.33
500917 | 2026-09-25 | 202609 | 24-104 | 02-200 | Subcontract | AP | V1020 | Earthwork Subcontractor E | Progress claim Sep 2026 | 0 | 0.01
501051 | 2026-09-25 | 202609 | 24-104 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Sep 25 | 57.1 | 4054.87
501058 | 2026-09-25 | 202609 | 24-104 | 07-200 | Subcontract | AP | V1025 | Roofing Subcontractor F | Progress claim Sep 2026 | 0 | 0.01
501074 | 2026-09-25 | 202609 | 24-104 | 09-200 | Subcontract | AP | V1027 | Drywall Subcontractor F | Progress claim Sep 2026 | 0 | 394688.63
501085 | 2026-09-25 | 202609 | 24-104 | 15-000 | Subcontract | AP | V1028 | Mechanical Subcontractor B | Progress claim Sep 2026 | 0 | 147833.17
501096 | 2026-09-25 | 202609 | 24-104 | 16-000 | Subcontract | AP | V1029 | Electrical Subcontractor F | Progress claim Sep 2026 | 0 | 127494.37
501165 | 2026-09-25 | 202609 | 24-107 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Sep 25 | 57.9 | 5329.65
501323 | 2026-09-25 | 202609 | 24-107 | 07-200 | Subcontract | AP | V1034 | Roofing Subcontractor A | Progress claim Sep 2026 | 0 | 0.01
501343 | 2026-09-25 | 202609 | 24-107 | 09-200 | Subcontract | AP | V1036 | Drywall Subcontractor F | Progress claim Sep 2026 | 0 | 22754.02
501354 | 2026-09-25 | 202609 | 24-107 | 15-000 | Subcontract | AP | V1037 | Mechanical Subcontractor A | Progress claim Sep 2026 | 0 | 37550.94
501365 | 2026-09-25 | 202609 | 24-107 | 16-000 | Subcontract | AP | V1038 | Electrical Subcontractor A | Progress claim Sep 2026 | 0 | 45685.69
501426 | 2026-09-25 | 202609 | 25-110 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Sep 25 | 267.7 | 24631.88
501557 | 2026-09-25 | 202609 | 25-110 | 04-200 | Subcontract | AP | V1042 | Masonry Subcontractor G | Progress claim Sep 2026 | 0 | 60339.19
501566 | 2026-09-25 | 202609 | 25-110 | 05-100 | Subcontract | AP | V1043 | Structural Steel Subcontractor E | Progress claim Sep 2026 | 0 | 0.01
501592 | 2026-09-25 | 202609 | 25-110 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Sep 25 | 732.8 | 52027.99
501597 | 2026-09-25 | 202609 | 25-110 | 07-200 | Subcontract | AP | V1044 | Roofing Subcontractor D | Progress claim Sep 2026 | 0 | 353313.72
501600 | 2026-09-25 | 202609 | 25-110 | 09-200 | Subcontract | AP | V1046 | Drywall Subcontractor F | Progress claim Sep 2026 | 0 | 94023.73
501608 | 2026-09-25 | 202609 | 25-110 | 15-000 | Subcontract | AP | V1047 | Mechanical Subcontractor B | Progress claim Sep 2026 | 0 | 421360.94
501616 | 2026-09-25 | 202609 | 25-110 | 16-000 | Subcontract | AP | V1048 | Electrical Subcontractor E | Progress claim Sep 2026 | 0 | 303986.04
501672 | 2026-09-25 | 202609 | 25-112 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Sep 25 | 41.4 | 3812.07
501724 | 2026-09-25 | 202609 | 25-112 | 02-200 | Subcontract | AP | V1049 | Earthwork Subcontractor D | Progress claim Sep 2026 | 0 | 0.02
501836 | 2026-09-25 | 202609 | 25-112 | 09-200 | Subcontract | AP | V1056 | Drywall Subcontractor E | Progress claim Sep 2026 | 0 | 183722.62
501845 | 2026-09-25 | 202609 | 25-112 | 15-000 | Subcontract | AP | V1057 | Mechanical Subcontractor E | Progress claim Sep 2026 | 0 | 111003.13
501854 | 2026-09-25 | 202609 | 25-112 | 16-000 | Subcontract | AP | V1058 | Electrical Subcontractor G | Progress claim Sep 2026 | 0 | 79350.75
501906 | 2026-09-25 | 202609 | 25-115 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Sep 25 | 69.6 | 6399.19
502023 | 2026-09-25 | 202609 | 25-115 | 04-200 | Subcontract | AP | V1062 | Masonry Subcontractor G | Progress claim Sep 2026 | 0 | 39167.07
502051 | 2026-09-25 | 202609 | 25-115 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Sep 25 | 184 | 13065.51
502055 | 2026-09-25 | 202609 | 25-115 | 07-200 | Subcontract | AP | V1064 | Roofing Subcontractor B | Progress claim Sep 2026 | 0 | 157057.82
502061 | 2026-09-25 | 202609 | 25-115 | 09-200 | Subcontract | AP | V1066 | Drywall Subcontractor F | Progress claim Sep 2026 | 0 | 71850.96
502068 | 2026-09-25 | 202609 | 25-115 | 15-000 | Subcontract | AP | V1067 | Mechanical Subcontractor C | Progress claim Sep 2026 | 0 | 274740.16
502075 | 2026-09-25 | 202609 | 25-115 | 16-000 | Subcontract | AP | V1068 | Electrical Subcontractor D | Progress claim Sep 2026 | 0 | 141831.89
502122 | 2026-09-25 | 202609 | 25-118 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Sep 25 | 318.9 | 29335.18
502192 | 2026-09-25 | 202609 | 25-118 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Sep 25 | 0 | 0.01
502221 | 2026-09-25 | 202609 | 25-118 | 05-100 | Subcontract | AP | V1072 | Structural Steel Subcontractor D | Progress claim Sep 2026 | 0 | 0.01
502243 | 2026-09-25 | 202609 | 25-118 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Sep 25 | 190.8 | 13547.04
502247 | 2026-09-25 | 202609 | 25-118 | 07-200 | Subcontract | AP | V1073 | Roofing Subcontractor A | Progress claim Sep 2026 | 0 | 185235.04
502252 | 2026-09-25 | 202609 | 25-118 | 09-200 | Subcontract | AP | V1075 | Drywall Subcontractor G | Progress claim Sep 2026 | 0 | 77366.21
502259 | 2026-09-25 | 202609 | 25-118 | 15-000 | Subcontract | AP | V1076 | Mechanical Subcontractor E | Progress claim Sep 2026 | 0 | 451148.46
502266 | 2026-09-25 | 202609 | 25-118 | 16-000 | Subcontract | AP | V1077 | Electrical Subcontractor A | Progress claim Sep 2026 | 0 | 285482.86
502305 | 2026-09-25 | 202609 | 25-121 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Sep 25 | 348.1 | 32029.3
502370 | 2026-09-25 | 202609 | 25-121 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Sep 25 | 142.1 | 10516.01
502404 | 2026-09-25 | 202609 | 25-121 | 04-200 | Subcontract | AP | V1081 | Masonry Subcontractor E | Progress claim Sep 2026 | 0 | 147324.89
502408 | 2026-09-25 | 202609 | 25-121 | 05-100 | Subcontract | AP | V1082 | Structural Steel Subcontractor F | Progress claim Sep 2026 | 0 | 213102.62
502412 | 2026-09-25 | 202609 | 25-121 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Sep 25 | 461.1 | 32740.91
502415 | 2026-09-25 | 202609 | 25-121 | 15-000 | Subcontract | AP | V1083 | Mechanical Subcontractor E | Progress claim Sep 2026 | 0 | 107060.35
502418 | 2026-09-25 | 202609 | 25-121 | 16-000 | Subcontract | AP | V1084 | Electrical Subcontractor F | Progress claim Sep 2026 | 0 | 119321.96
502448 | 2026-09-25 | 202609 | 26-124 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Sep 25 | 309.9 | 28510.56
502476 | 2026-09-25 | 202609 | 26-124 | 02-200 | Subcontract | AP | V1085 | Earthwork Subcontractor E | Progress claim Sep 2026 | 0 | 0.01
502502 | 2026-09-25 | 202609 | 26-124 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Sep 25 | 220.9 | 16348.38
502532 | 2026-09-25 | 202609 | 26-124 | 05-100 | Subcontract | AP | V1088 | Structural Steel Subcontractor B | Progress claim Sep 2026 | 0 | 543447.09
502536 | 2026-09-25 | 202609 | 26-124 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Sep 25 | 21.1 | 1498.66
502539 | 2026-09-25 | 202609 | 26-124 | 15-000 | Subcontract | AP | V1089 | Mechanical Subcontractor C | Progress claim Sep 2026 | 0 | 97468.13
502542 | 2026-09-25 | 202609 | 26-124 | 16-000 | Subcontract | AP | V1090 | Electrical Subcontractor C | Progress claim Sep 2026 | 0 | 107222.98
502564 | 2026-09-25 | 202609 | 26-127 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Sep 25 | 192.4 | 17700.97
502584 | 2026-09-25 | 202609 | 26-127 | 02-200 | Subcontract | AP | V1091 | Earthwork Subcontractor A | Progress claim Sep 2026 | 0 | 0.01
502601 | 2026-09-25 | 202609 | 26-127 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Sep 25 | 326.4 | 24157.05
502620 | 2026-09-25 | 202609 | 26-127 | 04-200 | Subcontract | AP | V1094 | Masonry Subcontractor C | Progress claim Sep 2026 | 0 | 28087.4
502622 | 2026-09-25 | 202609 | 26-127 | 05-100 | Subcontract | AP | V1095 | Structural Steel Subcontractor D | Progress claim Sep 2026 | 0 | 269749.44
502626 | 2026-09-25 | 202609 | 26-127 | 06-100 | Labour | PR |  | Payroll | Payroll w/e Sep 25 | 9.2 | 650.95
502628 | 2026-09-25 | 202609 | 26-127 | 15-000 | Subcontract | AP | V1096 | Mechanical Subcontractor B | Progress claim Sep 2026 | 0 | 51874.95
502630 | 2026-09-25 | 202609 | 26-127 | 16-000 | Subcontract | AP | V1097 | Electrical Subcontractor F | Progress claim Sep 2026 | 0 | 39165.94
502643 | 2026-09-25 | 202609 | 26-130 | 01-100 | Labour | PR |  | Payroll | Payroll w/e Sep 25 | 88.7 | 8161.76
502655 | 2026-09-25 | 202609 | 26-130 | 02-200 | Subcontract | AP | V1098 | Earthwork Subcontractor D | Progress claim Sep 2026 | 0 | 71109.21
502663 | 2026-09-25 | 202609 | 26-130 | 03-100 | Labour | PR |  | Payroll | Payroll w/e Sep 25 | 216.5 | 16022.2
502670 | 2026-09-25 | 202609 | 26-130 | 03-300 | Material | AP | V1100 | Cast-in-Place Concrete Supplier B | Invoice 36822 | 0 | 17698.1
500750 | 2026-09-26 | 202609 | 24-101 | 08-100 | Material | AP | V1016 | Doors Supplier F | Invoice 98983 | 0 | 17581.66
500972 | 2026-09-26 | 202609 | 24-104 | 03-200 | Material | AP | V1021 | Reinforcing Steel Supplier D | Invoice 25189 | 0 | 0.01
501336 | 2026-09-27 | 202609 | 24-107 | 08-100 | Material | AP | V1035 | Doors Supplier D | Invoice 42180 | 0 | 1170.22
501996 | 2026-09-27 | 202609 | 25-115 | 03-200 | Material | AP | V1060 | Reinforcing Steel Supplier B | Invoice 84184 | 0 | 0.01
502249 | 2026-09-27 | 202609 | 25-118 | 08-100 | Material | AP | V1074 | Doors Supplier D | Invoice 56314 | 0 | 11411.01
500588 | 2026-09-30 | 202609 | 24-101 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 4140.76
500910 | 2026-09-30 | 202609 | 24-104 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 9976.15
501468 | 2026-09-30 | 202609 | 25-110 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 39685.82
501719 | 2026-09-30 | 202609 | 25-112 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 4106.24
501944 | 2026-09-30 | 202609 | 25-115 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 22872.99
502153 | 2026-09-30 | 202609 | 25-118 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 42365.58
502334 | 2026-09-30 | 202609 | 25-121 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 56234.84
502471 | 2026-09-30 | 202609 | 26-124 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 63416.51
502579 | 2026-09-30 | 202609 | 26-127 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 40585.42
502652 | 2026-09-30 | 202609 | 26-130 | 01-500 | Equipment | EQ |  | Internal equipment | Monthly equipment charge | 0 | 9226.83

## Data_Billings
invoice_no | invoice_date | fiscal_period | job_no | gross_billed | holdback_retained | net_receivable
INV-23-098-202406 | 2024-06-30 | 202406 | 23-098 | 41354.12 | 4135.41 | 37218.71
INV-23-098-202407 | 2024-07-31 | 202407 | 23-098 | 101455.73 | 10145.57 | 91310.16
INV-23-098-202408 | 2024-08-31 | 202408 | 23-098 | 196718.69 | 19671.87 | 177046.82
INV-23-098-202409 | 2024-09-30 | 202409 | 23-098 | 261620.38 | 26162.04 | 235458.34
INV-23-098-202410 | 2024-10-31 | 202410 | 23-098 | 365807.03 | 36580.7 | 329226.33
INV-23-098-202411 | 2024-11-30 | 202411 | 23-098 | 424141.02 | 42414.1 | 381726.92
INV-23-098-202412 | 2024-12-31 | 202412 | 23-098 | 474156.55 | 47415.65 | 426740.9
INV-23-098-202501 | 2025-01-31 | 202501 | 23-098 | 593859.7 | 59385.97 | 534473.73
INV-23-098-202502 | 2025-02-28 | 202502 | 23-098 | 553873.35 | 55387.33 | 498486.02
INV-23-098-202503 | 2025-03-31 | 202503 | 23-098 | 733027.19 | 73302.72 | 659724.47
INV-23-098-202504 | 2025-04-30 | 202504 | 23-098 | 754750.62 | 75475.06 | 679275.56
INV-23-098-202505 | 2025-05-31 | 202505 | 23-098 | 760584.22 | 76058.42 | 684525.8
INV-23-098-202506 | 2025-06-30 | 202506 | 23-098 | 814737.86 | 81473.79 | 733264.07
INV-23-098-202507 | 2025-07-31 | 202507 | 23-098 | 902535.5 | 90253.55 | 812281.95
INV-23-098-202508 | 2025-08-31 | 202508 | 23-098 | 954895.62 | 95489.56 | 859406.06
INV-23-098-202509 | 2025-09-30 | 202509 | 23-098 | 916197.29 | 91619.73 | 824577.56
INV-23-098-202510 | 2025-10-31 | 202510 | 23-098 | 1006109.93 | 100610.99 | 905498.94
INV-23-098-202511 | 2025-11-30 | 202511 | 23-098 | 850788.29 | 85078.83 | 765709.46
INV-23-098-202512 | 2025-12-31 | 202512 | 23-098 | 898561.07 | 89856.11 | 808704.96
INV-23-098-202601 | 2026-01-31 | 202601 | 23-098 | 917126.43 | 91712.64 | 825413.79
INV-23-098-202602 | 2026-02-28 | 202602 | 23-098 | 765108.43 | 76510.84 | 688597.59
INV-23-098-202603 | 2026-03-31 | 202603 | 23-098 | 767765.61 | 76776.56 | 690989.05
INV-23-098-202604 | 2026-04-30 | 202604 | 23-098 | 537130.85 | 53713.08 | 483417.77
INV-23-098-202605 | 2026-05-31 | 202605 | 23-098 | 350717.49 | 35071.75 | 315645.74
INV-23-098-202606 | 2026-06-30 | 202606 | 23-098 | 230829.7 | 23082.97 | 207746.73
INV-23-098-202607 | 2026-07-31 | 202607 | 23-098 | 123779.62 | 12377.96 | 111401.66
INV-23-098-202608 | 2026-08-31 | 202608 | 23-098 | 21955.17 | 2195.52 | 19759.65
INV-24-101-202503 | 2025-03-31 | 202503 | 24-101 | 171021.25 | 17102.12 | 153919.12
INV-24-101-202504 | 2025-04-30 | 202504 | 24-101 | 457316.79 | 45731.68 | 411585.11
INV-24-101-202505 | 2025-05-31 | 202505 | 24-101 | 952525 | 95252.5 | 857272.5
INV-24-101-202506 | 2025-06-30 | 202506 | 24-101 | 1048851.07 | 104885.11 | 943965.96
INV-24-101-202507 | 2025-07-31 | 202507 | 24-101 | 1189927.96 | 118992.8 | 1070935.16
INV-24-101-202508 | 2025-08-31 | 202508 | 24-101 | 1389876.71 | 138987.67 | 1250889.04
INV-24-101-202509 | 2025-09-30 | 202509 | 24-101 | 1511774.13 | 151177.41 | 1360596.72
INV-24-101-202510 | 2025-10-31 | 202510 | 24-101 | 1959820.04 | 195982 | 1763838.04
INV-24-101-202511 | 2025-11-30 | 202511 | 24-101 | 1665286.46 | 166528.65 | 1498757.81
INV-24-101-202512 | 2025-12-31 | 202512 | 24-101 | 1772071.45 | 177207.15 | 1594864.3
INV-24-101-202601 | 2026-01-31 | 202601 | 24-101 | 1551361.21 | 155136.12 | 1396225.09
INV-24-101-202602 | 2026-02-28 | 202602 | 24-101 | 1295717.88 | 129571.79 | 1166146.09
INV-24-101-202603 | 2026-03-31 | 202603 | 24-101 | 1478782.97 | 147878.3 | 1330904.67
INV-24-101-202604 | 2026-04-30 | 202604 | 24-101 | 1534215.78 | 153421.58 | 1380794.2
INV-24-101-202605 | 2026-05-31 | 202605 | 24-101 | 1247601.63 | 124760.16 | 1122841.47
INV-24-101-202606 | 2026-06-30 | 202606 | 24-101 | 1105705.45 | 110570.54 | 995134.91
INV-24-101-202607 | 2026-07-31 | 202607 | 24-101 | 1001736.46 | 100173.65 | 901562.81
INV-24-101-202608 | 2026-08-31 | 202608 | 24-101 | 790582.12 | 79058.21 | 711523.91
INV-24-101-202609 | 2026-09-30 | 202609 | 24-101 | 122146.09 | 12214.61 | 109931.48
INV-24-104-202505 | 2025-05-31 | 202505 | 24-104 | 68177.08 | 6817.71 | 61359.37
INV-24-104-202506 | 2025-06-30 | 202506 | 24-104 | 167525.68 | 16752.57 | 150773.11
INV-24-104-202507 | 2025-07-31 | 202507 | 24-104 | 341926.69 | 34192.67 | 307734.02
INV-24-104-202508 | 2025-08-31 | 202508 | 24-104 | 459244.18 | 45924.42 | 413319.76
INV-24-104-202509 | 2025-09-30 | 202509 | 24-104 | 504742.11 | 50474.21 | 454267.9
INV-24-104-202510 | 2025-10-31 | 202510 | 24-104 | 695070.88 | 69507.09 | 625563.79
INV-24-104-202511 | 2025-11-30 | 202511 | 24-104 | 840523.49 | 84052.35 | 756471.14
INV-24-104-202512 | 2025-12-31 | 202512 | 24-104 | 902892.37 | 90289.24 | 812603.13
INV-24-104-202601 | 2026-01-31 | 202601 | 24-104 | 1029454.53 | 102945.45 | 926509.08
INV-24-104-202602 | 2026-02-28 | 202602 | 24-104 | 990943.08 | 99094.31 | 891848.77
INV-24-104-202603 | 2026-03-31 | 202603 | 24-104 | 1187211.46 | 118721.15 | 1068490.31
INV-24-104-202604 | 2026-04-30 | 202604 | 24-104 | 1364054.06 | 136405.41 | 1227648.65
INV-24-104-202605 | 2026-05-31 | 202605 | 24-104 | 1259195.16 | 125919.52 | 1133275.64
INV-24-104-202606 | 2026-06-30 | 202606 | 24-104 | 1226724.03 | 122672.4 | 1104051.63
INV-24-104-202607 | 2026-07-31 | 202607 | 24-104 | 1111630.49 | 111163.05 | 1000467.44
INV-24-104-202608 | 2026-08-31 | 202608 | 24-104 | 1113083.3 | 111308.33 | 1001774.97
INV-24-104-202609 | 2026-09-30 | 202609 | 24-104 | 923836.88 | 92383.69 | 831453.19
INV-24-107-202506 | 2025-06-30 | 202506 | 24-107 | 119633.43 | 11963.34 | 107670.09
INV-24-107-202507 | 2025-07-31 | 202507 | 24-107 | 338216.68 | 33821.67 | 304395.01
INV-24-107-202508 | 2025-08-31 | 202508 | 24-107 | 562575.65 | 56257.57 | 506318.09
INV-24-107-202509 | 2025-09-30 | 202509 | 24-107 | 663534.31 | 66353.43 | 597180.88
INV-24-107-202510 | 2025-10-31 | 202510 | 24-107 | 824257.36 | 82425.74 | 741831.62
INV-24-107-202511 | 2025-11-30 | 202511 | 24-107 | 913405.8 | 91340.58 | 822065.22
INV-24-107-202512 | 2025-12-31 | 202512 | 24-107 | 986744.39 | 98674.44 | 888069.95
INV-24-107-202601 | 2026-01-31 | 202601 | 24-107 | 972745 | 97274.5 | 875470.5
INV-24-107-202602 | 2026-02-28 | 202602 | 24-107 | 796913.35 | 79691.34 | 717222.02
INV-24-107-202603 | 2026-03-31 | 202603 | 24-107 | 869306.3 | 86930.63 | 782375.67
INV-24-107-202604 | 2026-04-30 | 202604 | 24-107 | 857914.69 | 85791.47 | 772123.22
INV-24-107-202605 | 2026-05-31 | 202605 | 24-107 | 822029.11 | 82202.91 | 739826.2
INV-24-107-202606 | 2026-06-30 | 202606 | 24-107 | 578813.27 | 57881.33 | 520931.94
INV-24-107-202607 | 2026-07-31 | 202607 | 24-107 | 497968.03 | 49796.8 | 448171.23
INV-24-107-202608 | 2026-08-31 | 202608 | 24-107 | 285468.45 | 28546.85 | 256921.61
INV-24-107-202609 | 2026-09-30 | 202609 | 24-107 | 69815.15 | 6981.51 | 62833.63
INV-25-110-202508 | 2025-08-31 | 202508 | 25-110 | 116795.53 | 11679.55 | 105115.98
INV-25-110-202509 | 2025-09-30 | 202509 | 25-110 | 270888.34 | 27088.83 | 243799.51
INV-25-110-202510 | 2025-10-31 | 202510 | 25-110 | 643296.48 | 64329.65 | 578966.83
INV-25-110-202511 | 2025-11-30 | 202511 | 25-110 | 809862.34 | 80986.23 | 728876.11
INV-25-110-202512 | 2025-12-31 | 202512 | 25-110 | 1054119.9 | 105411.99 | 948707.91
INV-25-110-202601 | 2026-01-31 | 202601 | 25-110 | 1195993.54 | 119599.35 | 1076394.19
INV-25-110-202602 | 2026-02-28 | 202602 | 25-110 | 1378605.55 | 137860.56 | 1240745
INV-25-110-202603 | 2026-03-31 | 202603 | 25-110 | 1752909.8 | 175290.98 | 1577618.82
INV-25-110-202604 | 2026-04-30 | 202604 | 25-110 | 1858649.16 | 185864.92 | 1672784.24
INV-25-110-202605 | 2026-05-31 | 202605 | 25-110 | 1890897.71 | 189089.77 | 1701807.94
INV-25-110-202606 | 2026-06-30 | 202606 | 25-110 | 1860549.03 | 186054.9 | 1674494.13
INV-25-110-202607 | 2026-07-31 | 202607 | 25-110 | 1954836.61 | 195483.66 | 1759352.95
INV-25-110-202608 | 2026-08-31 | 202608 | 25-110 | 1735765.36 | 173576.54 | 1562188.82
INV-25-110-202609 | 2026-09-30 | 202609 | 25-110 | 1987968.18 | 198796.82 | 1789171.36
INV-25-112-202509 | 2025-09-30 | 202509 | 25-112 | 48340.7 | 4834.07 | 43506.63
INV-25-112-202510 | 2025-10-31 | 202510 | 25-112 | 194220.53 | 19422.05 | 174798.48
INV-25-112-202511 | 2025-11-30 | 202511 | 25-112 | 337395.94 | 33739.59 | 303656.35
INV-25-112-202512 | 2025-12-31 | 202512 | 25-112 | 525261.69 | 52526.17 | 472735.52
INV-25-112-202601 | 2026-01-31 | 202601 | 25-112 | 649977.09 | 64997.71 | 584979.38
INV-25-112-202602 | 2026-02-28 | 202602 | 25-112 | 649008.28 | 64900.83 | 584107.45
INV-25-112-202603 | 2026-03-31 | 202603 | 25-112 | 838671.62 | 83867.16 | 754804.46
INV-25-112-202604 | 2026-04-30 | 202604 | 25-112 | 949905.68 | 94990.57 | 854915.11
INV-25-112-202605 | 2026-05-31 | 202605 | 25-112 | 974198.34 | 97419.83 | 876778.51
INV-25-112-202606 | 2026-06-30 | 202606 | 25-112 | 938586.63 | 93858.66 | 844727.97
INV-25-112-202607 | 2026-07-31 | 202607 | 25-112 | 888334.27 | 88833.43 | 799500.84
INV-25-112-202608 | 2026-08-31 | 202608 | 25-112 | 808536.55 | 80853.66 | 727682.9
INV-25-112-202609 | 2026-09-30 | 202609 | 25-112 | 557352.53 | 55735.25 | 501617.28
INV-25-115-202510 | 2025-10-31 | 202510 | 25-115 | 53059.85 | 5305.99 | 47753.86
INV-25-115-202511 | 2025-11-30 | 202511 | 25-115 | 169539.87 | 16953.99 | 152585.88
INV-25-115-202512 | 2025-12-31 | 202512 | 25-115 | 392084.18 | 39208.42 | 352875.76
INV-25-115-202601 | 2026-01-31 | 202601 | 25-115 | 529238.3 | 52923.83 | 476314.47
INV-25-115-202602 | 2026-02-28 | 202602 | 25-115 | 643746.15 | 64374.62 | 579371.54
INV-25-115-202603 | 2026-03-31 | 202603 | 25-115 | 864627.61 | 86462.76 | 778164.85
INV-25-115-202604 | 2026-04-30 | 202604 | 25-115 | 821488.78 | 82148.88 | 739339.9
INV-25-115-202605 | 2026-05-31 | 202605 | 25-115 | 864017.34 | 86401.73 | 777615.61
INV-25-115-202606 | 2026-06-30 | 202606 | 25-115 | 856140.09 | 85614.01 | 770526.08
INV-25-115-202607 | 2026-07-31 | 202607 | 25-115 | 1093811.21 | 109381.12 | 984430.09
INV-25-115-202608 | 2026-08-31 | 202608 | 25-115 | 1087247.04 | 108724.7 | 978522.34
INV-25-115-202609 | 2026-09-30 | 202609 | 25-115 | 919925.6 | 91992.56 | 827933.04
INV-25-118-202511 | 2025-11-30 | 202511 | 25-118 | 234536.68 | 23453.67 | 211083.01
INV-25-118-202512 | 2025-12-31 | 202512 | 25-118 | 763402.33 | 76340.23 | 687062.1
INV-25-118-202601 | 2026-01-31 | 202601 | 25-118 | 1076078.18 | 107607.82 | 968470.36
INV-25-118-202602 | 2026-02-28 | 202602 | 25-118 | 1081308.28 | 108130.83 | 973177.45
INV-25-118-202603 | 2026-03-31 | 202603 | 25-118 | 1525934.17 | 152593.42 | 1373340.75
INV-25-118-202604 | 2026-04-30 | 202604 | 25-118 | 2035305.02 | 203530.5 | 1831774.52
INV-25-118-202605 | 2026-05-31 | 202605 | 25-118 | 2055692.85 | 205569.29 | 1850123.57
INV-25-118-202606 | 2026-06-30 | 202606 | 25-118 | 1581883.03 | 158188.3 | 1423694.73
INV-25-118-202607 | 2026-07-31 | 202607 | 25-118 | 1714446.4 | 171444.64 | 1543001.76
INV-25-118-202608 | 2026-08-31 | 202608 | 25-118 | 1760606.88 | 176060.69 | 1584546.19
INV-25-118-202609 | 2026-09-30 | 202609 | 25-118 | 1492924.44 | 149292.44 | 1343632
INV-25-121-202601 | 2026-01-31 | 202601 | 25-121 | 62886.15 | 6288.62 | 56597.54
INV-25-121-202602 | 2026-02-28 | 202602 | 25-121 | 178227.45 | 17822.75 | 160404.71
INV-25-121-202603 | 2026-03-31 | 202603 | 25-121 | 435022.16 | 43502.22 | 391519.94
INV-25-121-202604 | 2026-04-30 | 202604 | 25-121 | 630073.44 | 63007.34 | 567066.1
INV-25-121-202605 | 2026-05-31 | 202605 | 25-121 | 688592.53 | 68859.25 | 619733.28
INV-25-121-202606 | 2026-06-30 | 202606 | 25-121 | 806601.05 | 80660.11 | 725940.95
INV-25-121-202607 | 2026-07-31 | 202607 | 25-121 | 934345.89 | 93434.59 | 840911.3
INV-25-121-202608 | 2026-08-31 | 202608 | 25-121 | 1127333.89 | 112733.39 | 1014600.5
INV-25-121-202609 | 2026-09-30 | 202609 | 25-121 | 1138480.25 | 113848.03 | 1024632.22
INV-26-124-202603 | 2026-03-31 | 202603 | 26-124 | 191145.8 | 19114.58 | 172031.22
INV-26-124-202604 | 2026-04-30 | 202604 | 26-124 | 529464.58 | 52946.46 | 476518.12
INV-26-124-202605 | 2026-05-31 | 202605 | 26-124 | 843573.57 | 84357.36 | 759216.21
INV-26-124-202606 | 2026-06-30 | 202606 | 26-124 | 955247.36 | 95524.74 | 859722.62
INV-26-124-202607 | 2026-07-31 | 202607 | 26-124 | 1213490.52 | 121349.05 | 1092141.47
INV-26-124-202608 | 2026-08-31 | 202608 | 26-124 | 1469329.65 | 146932.96 | 1322396.69
INV-26-124-202609 | 2026-09-30 | 202609 | 26-124 | 1409275.1 | 140927.51 | 1268347.59
INV-26-127-202605 | 2026-05-31 | 202605 | 26-127 | 109563.97 | 10956.4 | 98607.57
INV-26-127-202606 | 2026-06-30 | 202606 | 26-127 | 370045.52 | 37004.55 | 333040.97
INV-26-127-202607 | 2026-07-31 | 202607 | 26-127 | 561761.3 | 56176.13 | 505585.17
INV-26-127-202608 | 2026-08-31 | 202608 | 26-127 | 742232.29 | 74223.23 | 668009.06
INV-26-127-202609 | 2026-09-30 | 202609 | 26-127 | 843906.18 | 84390.62 | 759515.56
INV-26-130-202607 | 2026-07-31 | 202607 | 26-130 | 48214.14 | 4821.41 | 43392.73
INV-26-130-202608 | 2026-08-31 | 202608 | 26-130 | 224231.03 | 22423.1 | 201807.93
INV-26-130-202609 | 2026-09-30 | 202609 | 26-130 | 342370.23 | 34237.02 | 308133.21